## 03Q2_casu_deliverables2
WP | CASU WP name /sub task / 03Q1 deliverable | name | weeks | end of quarter report | signed-off | ongoing
#
1 | ESO VISTA software interface deliverables and documentation
|  | PSB | 6
2 | management and definition of project responsibilities
2.1 | report to VISTA, UKIDSS, JAC, ATC, GSC
| set up work package spreadsheets | STH |  | constructed XL spreadsheets for WPs and Risks, also GANTT chart |  | Y
| instigate regular meetings | MJI |  | fortnightly meetings planned | Y
2.2 | interface control document between CASU and JAC
| agree provisional ICD with JAC | MJI |  | agreed | Y
2.3 | interface control document between CASU and WFAU
2.4 | define data structures and FITS headers
| write fits header document | JRL |  | discussions with ATC and JAC have lead to version 0.6 of FITS header document |  | Y
| create example MEFs with agreed FITS headers and CIRSI data | JRL |  | files created | Y
2.6 | liaise with UKIDSS & JAC on observing strategy
| investigate other observing strategies | DWE |  | discussions with USNO |  | Y
2.7 | liaise with UKIDSS & JAC on survey planning
| produce overviews (different projections) of UKIDSS surveys | DWE |  | done | Y
3 | pipeline infrastructure and pipeline progress monitoring tools
3.2 | high level scripts to interrogate headers
| script to interrogate FITS headers of processed INT WFC | STH |  | written with JMI | Y
| propogated results to ascii and html files | STH |  | written with JMI | Y
3.6 | group documentation on pipeline infrastructure
| programming notes for all modules | JRL |  | notes finished | Y
4 | set up and manage raw science archive
5 | set up and manage data processing system hardware
5.1 | investigate hardware alternatives |  |  |  |  | Y
| preliminary investigation |  |  | monitered hardware availability, RAID disk limits
6 | run standard pipeline
7 | development work for summit pipeline
7.1 | interface test pipelines in ORAC-DR
| deliver ORAC-DR routines for subset of UFTI recipes to JAC | JRL |  | delivered | Y
7.3 | documentation for ORAC-DR interface
| document modules for UFTI recipes | JRL |  | done | Y
8 | development and testing of standard 2d processing
8.1 | further development of standard pipeline
| discuss details of 2d processing steps | JRL |  | internal meetings and external with SJW |  | Y
| further testing with with existing WFC and CIRSI data | JRL |  |  |  | Y
| module version control | JRL |  | module version written to headers | Y
| provenence information in stacking/combining | JRL |  | Provenance now written to header of combined/stacked frames | Y
8.2 | liaison with WFCAM development team
| report from initial detector tests | STH |  | ongoing discussions on reset anomaly, crosstalk and lineaity |  | Y
8.6 | documentation for 2D processing software
| write user manuals for INT WFC and CIRSI pipelines | JRL |  | written | Y
8.7 | comparison between automated and manual data products
| define requirement | STH |  | produced requirement to test the quality of the 2D pipeline with manual reduction of same | Y
9 | development and testing of standard catalogue products
10 | setup trial and run further processing pipeline
11 | photometric standards and calibration
11.1 | agree on primary standards
| research primary standards | STH |  | collated standard star lists |  | Y
12 | further development of DQC measures at summit and Cambridge
12.4 | master calibration frames for detector monitoring
| bad pixel mask | JRL |  | developed basic bad pixel mask generating methods | Y
13 | co-located list driven photometry
13.1 | test methods for master catalogue generation
| deep stacking | MJI |  | devised and produced method for based on deep stacking | Y
13.2 | develop basic WCS-based list driven photometer
| produce basic x-y photometer | MJI |  | used 13.1 to develop x-y based algorithm | Y
14 | stacking and mosaicing
14.1 | develop benchmark simple stacking/mosaicing framework
| produce a working algorithm | MJI |  | first version completed
14.2 | NN algorithm with simple rejection
| complete and deliver version 1 | MJI |  | version 1.0 delivered to WFAU
15 | continuum subtraction and basic difference imaging
16 | interpolation techniques and PSF modeling
16.1 | investigate alternative interpolation/PSF schemes
| review alternative strategies | DWE |  | ongoing |  | Y
16.4 | oversampled PSF generation per detector
| assess alternative published strategies | DWE |  | onging |  | Y