## 03Q2_casu_deliverables2
WP | CASU WP name /sub task / 03Q2 deliverable | name | weeks | end of quarter report | signed-off | ongoing
#
1 | ESO VISTA software interface deliverables and documentation
|  | PSB | 6
2 | management and definition of project responsibilities
2.1 | report to VISTA, UKIDSS, JAC, ATC, GSC
| provide monthly reports on progress | MJI
2.2 | interface control document between CASU and JAC
| finalise ICD with JAC after summit hardware review | MJI
2.3 | interface control document between CASU and WFAU
| complete file transfer specification and finalise ICD | MJI
2.4 | define data structures and FITS headers
| produce final agreed FITS header specification document | JRL
| create example MEFs with agreed FITS headers and dummy WFCAM size data | JRL
2.5 | define observing protocols
| formalise agreement on allowed observing protocols | STH
2.6 | liaise with UKIDSS & JAC on observing strategy
| in consultation with UKIDSS, JAC, ATC produce draft observing plan | DWE
2.7 | liaise with UKIDSS & JAC on survey planning
| help update UKIDSS diagrams and produce equivalent for 2 year plan | DWE
2.8 | liaise with UKIDSS and JAC on survey progress DB
| work with JAC to resolve connectivity issues | JRL
| create mirror copy of progress DB in Sybase | JRL
3 | pipeline infrastructure and pipeline progress monitoring tools
3.2 | high level scripts to interrogate headers
| convert to work with expected WFCAM/VISTA data and modify output | STH
3.6 | group documentation on pipeline infrastructure
| stress test documentation and update as necessary | JRL
| write general infrastructure document (programmers manual) | JRL
4 | set up and manage raw science archive
5 | set up and manage data processing system hardware
5.1 | investigate hardware alternatives
| write report on suggested hardware configuration for pipeline | NEW
6 | run standard pipeline
7 | development work for summit pipeline
7.1 | interface test pipelines in ORAC-DR
| deliver updated set of routines and recipes to CVS at JAC | JRL
| fix inconsistencies in current ORAC-DR recipes as per recommendations | JRL
7.3 | documentation for ORAC-DR interface
| deliver updated documentation as development proceeds | JRL
8 | development and testing of standard 2d processing
8.1 | further development of standard pipeline
| test alternative processing strategies, tabulate output changes | JRL
| implement new version of imcore to include full parameter set. | JRL
| convert existing prototype modules for crosstalk correction | JRL
| devise persistence correction strategies | JRL
8.2 | liaison with WFCAM development team
| assess engineering test data for above problems and report | STH
8.3 | partake in planning commissioning observations
| liaise with ATC/JAC and draw up draft plan emphasising calibration requirements | STH
8.6 | documentation for 2D processing software
| stress test documentation and update as needed | JRL
8.7 | comparison between automated and manual data products
| in collaboration with SJW trial UFTI/CIRPASS data through pipeline, compare with manually reduced data, write report | STH
9 | development and testing of standard catalogue products
9.1 | add in new measures requested
| produce first version of catalogue software with extra measures | MJI
9.3 | generate model simulations of expected data
| generate noisy (WFCAM/VISTA characteristics) images of simple objects (stars, ellipses) at the correct resolutions | STH
| produce more detailed simulated UKIRT observations of high and low latitude fields | STH
9.4 | assess catalogue parameter reliability
| run prototype pipeline on simulations and compare derived parameters with model data, write report | DWE
9.5 | intercomparison of catalogue products with other packages
| agree detailed trials using INT WFC data and report on catalogue extraction and classification software comparisons | STH
9.7 | documentation of catalogue software and products
| produce draft document of above | MJI
| stress test documentation and amend as necessary | MJI
10 | setup trial and run further processing pipeline
11 | photometric standards and calibration
11.1 | agree on primary standards
| investigate requirements for VISTA+WFCAM and possible shortcomings e.g. colour range | STH
| in consultation produce draft list suitable for WFCAM and VISTA | STH
11.2 | choose secondary standard fields
| find out which UKIDSS survey modes require these and in consultation with JAC+ATC propose secondary standard fields list | STH
12 | further development of DQC measures at summit and Cambridge
12.3 | implement 2mass for throughput measurement
| produce prototype 2mass NIR data calibrator test on CIRSI data | MJI
12.4 | master calibration frames for detector monitoring
| assess and report if current methods work on engineering WFCAM data | JRL
13 | co-located list driven photometry
13.1 | test methods for master catalogue generation
| extend to include different wavebands, document | MJI
13.2 | develop basic WCS-based list driven photometer
| extend above to WCS-based driven and deliver prototype to WFAU for evaluation | MJI
14 | stacking and mosaicing
14.1 | develop benchmark simple stacking/mosaicing framework
| improve to account for new WCS framework | MJI
14.2 | NN algorithm with simple rejection
| produce version 2 with new WCS and deliver to WFAU | MJI
15 | continuum subtraction and basic difference imaging
15.2 | investigate and apply different interpolation methods
| write WCS-based difference imaging driver software | MJI
| write software using 16.1 to compare effect on difference imaging produce preliminary report | MJI
16 | interpolation techniques and PSF modeling
16.1 | investigate alternative interpolation/PSF schemes
| finish review and write short report on alternatives | DWE
16.3 | implications for deriving catalogues and parameters
| assess and write report on errors in catalogue parameters arising from using different interpolation schemes | DWE
16.4 | oversampled PSF generation per detector
| write first pass PSF generator using optical test data | DWE