## 03Q2_casu_deliverables2
WP | CASU WP name /sub task / 03Q2 deliverable | name | date | end of month report | % done
#
1 | management and definition of project responsibilities
1.1 | report to VISTA, UKIDSS, JAC, ATC, GSC
| provide monthly reports on progress | MJI | 2003-05-02 | STH+MJI produced spreadsheets of the costs of the deliverables and continued maintenance of the WP spreadsheets and Gantt charts. MJI - ongoing - and set up to do via the fortnightly meetings, minutes and monthly reports
|  | MJI | 2003-06-03 | ongoing
1.2 | interface control document between CASU and JAC |  |  |  | 50
|  | MJI | 2003-06-03 | no further progress, awaiting final JAC decision on hardware
| finalise ICD with JAC after summit hardware review | MJI | 2003-05-02 | Discussed and agreed baseline transfer mechanism of data from JAC to CASU; and outline hardware setup for data acquisition and summit pipeline
1.3 | interface control document between CASU and WFAU |  |  |  | 50
| complete file transfer specification and finalise ICD | MJI | 2003-05-02
|  | MJI | 2003-06-03 | no further progress
1.4 | define data structures and FITS headers |  |  |  | 50
| produce final agreed FITS header specification document | JRL | 2003-05-02 | discussion with JAC task re grouping of observations into contiguous tiles
|  | JRL | 2003-06-03 | Good progress on tile issue, PV keywords need amending
| create example MEFs with agreed FITS headers and dummy WFCAM size data | JRL
|  | JRL | 2003-06-03 | MEFs created with headers confirming to the most recent iteration of the header document. Using CIRSI data (so images 1/4 of WFCAM size)
1.5 | define observing protocols |  |  |  | 50
| formalise agreement on allowed observing protocols | STH | 2003-05-02 | ongoing - progress with JRL and Paul Hirst on tile keyword propagation
|  | STH | 2003-06-03 | ongoing - converging on tile issue
1.6 | liaise with UKIDSS & JAC on observing strategy
| in consultation with UKIDSS, JAC, ATC produce draft observing plan | DWE | 2003-05-02 | discussed with SJW the responsibility division between the UKIDSS survey scientist and the manager: ongoing
1.7 | liaise with UKIDSS & JAC on survey planning
| help update UKIDSS diagrams and produce equivalent for 2 year plan | DWE | 2003-05-02 | UKIDSS survey planning: altered UKIDSS survey coverage plotting programme so that user defined areas can be added. Equivalent 2yr plan plotting programme has been written. Coverage of DR1 for SDSS has been incorporated into these programmes. Plots have been placed on the web and sent to SJW
1.8 | liaise with UKIDSS and JAC on survey progress DB |  |  |  | 10
| work with JAC to resolve connectivity issues | JRL | 2003-05-02 | solved connectivity problem with JAC's archive server. Working towards mirroring of comments and progress database.
|  |  | 2003-06-03 | connectivity restores
| create mirror copy of progress DB in Sybase | JRL
|  | JRL | 2003-06-03 | have begun discourse with JAC personnel
1.9 | System documentation | DWE | 2003-05-02 | Updated www pages | 50
2 | ESO VISTA software interface deliverables and documentation
2.1 | VDFS user requirements document | PSB | 2003-05-02 | document structures in place, meeting arranged with WJS | 10
| write first draft | PSB | 2003-06-03 | draft document for PDR being fleshed out
2.2 | data reduction specification document
| write first draft | PSB | 2003-06-03 | very outline document started | 0
2.3 | calibration plan document |  |  |  | 0
| write first draft | PSB | 2003-06-03 | Outline document being prepared, off-sky calibration being made compatible with AIT
2.9 | Liase with VISTA IR camera development team
|  | PSB | 2003-06-03 | Liaised with camera team regarding ovrlap between pipeline and camera AIT requirements, brainstorming session with WJS about telescope/camera technical details | 10
3 | pipeline infrastructure and pipeline progress monitoring tools
3.2 | high level scripts to interrogate headers |  |  |  | 50
| convert to work with expected WFCAM/VISTA data and modify output | STH | 2003-05-02 | basic INT procedures in place
|  | STH | 2003-06-03 | ongoing
3.6 | group documentation on pipeline infrastructure |  |  |  | 50
| stress test documentation and update as necessary | JRL
| write general infrastructure document (programmers manual) | JRL
4 | set up and manage raw science archive
5 | set up and manage data processing system hardware
5.1 | investigate hardware alternatives |  |  |  | 50
| write report on suggested hardware configuration for pipeline | MTB
|  | MTB | 2003-06-03 | Outline plan in place for individual rack mounted PCs + associated RAID5 disk systems with server level PCs + ultrium ta[p store system and larger RAID5 disk systems
6 | run standard pipeline
6.7 | Monitor product data transfer to WFAU |  |  |  | 0
| Initial tests | PSB | 2003-06-03 | Liaised with ROE EHS and Horst M. about network tuning and assisted in some testing
7 | development work for summit pipeline
7.1 | interface test pipelines in ORAC-DR |  |  |  | 50
| deliver updated set of routines and recipes to CVS at JAC | JRL | 2003-05-02 | discussion with JAC re methods to aid in the synchronisation of pipeline modules between CASU and JAC. CVS software modules - CVS repository at JAC
|  | JRL | 2003-06-03 | A version has been deposited, but not the latest, will be upgraded soon
| fix inconsistencies in current ORAC-DR recipes as per recommendations | JRL
|  | JRL | 2003-06-03 | no progress
7.2 | implement WFCAM pipeline at summit | JRL | 2003-05-02 | evaluating image compression schemes to speed up data flow | 10
7.3 | documentation for ORAC-DR interface |  |  |  | 50
| deliver updated documentation as development proceeds | JRL
8 | development and testing of standard 2d processing
8.1 | further development of standard pipeline |  |  |  | 50
| test alternative processing strategies, tabulate output changes | JRL | 2003-05-02 | ongoing investigation of optimal ways of removing instrumental signature with flats from various sources (sky, dome etc) and sky subtraction
|  | JRL | 2003-06-03 | ongoing
| convert existing prototype modules for crosstalk correction | JRL | 2003-05-02 | devised, wrote and tested general purpose pipeline module for correcting crosstalk
|  | JRL | 2003-06-03 | Written and tested. Finished
| devise persistence correction strategies | JRL | 2003-05-02 | ongoing work on general purpose pipeline module for persistance
|  | JRL | 2003-06-03 | Written and tested. Finished
8.2 | liaison with WFCAM development team
| assess engineering test data for above problems and report | STH
|  | STH | 2003-06-03 | Updated report on first WFCAM device made available by ATC. Second device in Edinburgh, third expected this month
8.3 | partake in planning commissioning observations |  |  |  | 50
| liaise with ATC/JAC and draw up draft plan emphasising calibration requirements | STH
|  | STH | 2003-06-03 | Draft plan for photometric calibration plan written. Document being drafted for 2d calibration plan. Both to be presented in ROE 12-13 June
8.6 | documentation for 2D processing software |  |  |  | 50
| stress test documentation and update as needed | JRL
8.7 | comparison between automated and manual data products |  |  |  | 0
| in collaboration with SJW trial UFTI/CIRPASS data through pipeline, compare with manually reduced data, write report | STH
|  | STH | 2003-06-03 | Not started
9 | development and testing of standard catalogue products
9.1 | add in new measures requested |  |  |  | 0
| produce first version of catalogue software with extra measures | MJI
|  | MJI | 2003-06-03 | No progres
9.3 | generate model simulations of expected data |  |  |  | 0
| generate noisy (WFCAM/VISTA characteristics) images of simple objects (stars, ellipses) at the correct resolutions | STH
|  | STH | 2003-06-03 | Not started
| produce more detailed simulated UKIRT observations of high and low latitude fields | STH
|  | STH | 2003-06-03 | Not started
9.4 | assess catalogue parameter reliability |  |  |  | 0
| run prototype pipeline on simulations and compare derived parameters with model data, write report | DWE
9.5 | intercomparison of catalogue products with other packages |  |  |  | 10
| agree detailed trials using INT WFC data and report on catalogue extraction and classification software comparisons | STH
|  | STH | 2003-06-03 | Not started
9.7 | documentation of catalogue software and products |  |  |  | 50
| produce draft document of above | MJI | 2003-06-03 | Documentation well underway
| stress test documentation and amend as necessary | STH | 2003-06-03 | No progress
10 | setup trial and run further processing pipeline
11 | photometric standards and calibration
11.1 | agree on primary standards |  |  |  | 50
| investigate requirements for VISTA+WFCAM and possible shortcomings e.g. colour range | STH | 2003-05-02 | Began document to take off from where NCH doc left off. Have arranged handover of this task with NCH and informed working group chair (Paul Hewett.
|  | STH | 2003-06-03 | Draft document completed and ready for circulation. Will be presented in ROE on 12-13 June
| in consultation produce draft list suitable for WFCAM and VISTA | STH | 2003-05-02 | draft list in preparation
|  | STH | 2003-06-03 | Primary standards will be UKIRT FS and Persson standards for (YZ)JHK filters. Narrow band filter standards not cosen yet
11.2 | choose secondary standard fields |  |  |  | 50
| find out which UKIDSS survey modes require these and in consultation with JAC+ATC propose secondary standard fields list | STH | 2003-05-02 | investigating 2MASS calib fields versus new fields using globular clusters. Discussion with Paul Hirst re viability of observing these pre-WFCAM using UFTI/UIST
|  | STH | 2003-06-03 | narrowing down choice of secondary standard fields. Will be discussed at ROE June 12-13
12 | further development of DQC measures at summit and Cambridge
12.3 | implement 2mass for throughput measurement |  |  |  | 50
| produce prototype 2mass NIR data calibrator test on CIRSI data | MJI | 2003-05-02 | has arranged the acquisition of the 2MASS data products. This is about 80Gb and will be supplied asap
|  | MJI | 2003-06-03 | 2MASS data acquired and read onto disk. Will be ingested into SYBASE and alternative efficient sorted file-based system as basis for calibration tests
12.4 | master calibration frames for detector monitoring |  |  |  | 0
| assess and report if current methods work on engineering WFCAM data | JRL
13 | co-located list driven photometry
13.1 | test methods for master catalogue generation |  |  |  | 50
| extend to include different wavebands, document | MJI | 2003-05-02 | devised a procedure for creating master catalogues for multi-band data and incorporated it in pipeline toolkit development software
|  | MJI | 2003-06-03 | no change
13.2 | develop basic WCS-based list driven photometer |  |  |  | 10
| extend above to WCS-based driven and deliver prototype to WFAU for evaluation | MJI | 2003-05-02 | design conceived
|  | MJI | 2003-06-03 | no change
14 | stacking and mosaicing
14.1 | develop benchmark simple stacking/mosaicing framework |  |  |  | 100
| improve to account for new WCS framework | MJI | 2003-05-02 | bug fixed and enhanced current version 1.0 stacking and mosaicing software. Propagating changes into release (i.e C) version of code. Dumped current (old) verson already distributed to WFAU into CVS
|  | MJI | 2003-06-03 | Finished
14.2 | NN algorithm with simple rejection |  |  |  | 50
| produce version updated with new WCS and deliver to WFAU | MJI
|  | MJI | 2003-06-03 | Can't release until new WCS form can be read by standard image browsers, documentation needed
15 | continuum subtraction and basic difference imaging
15.2 | investigate and apply different interpolation methods |  | 2003-05-02 | MJI contacted Pierre Astier from the S.Ne Cosmology project about acquiring the S.Ne adaptive kernel matching code. This is in parallel with DWE's work with Ian Bond's code. | 10
| write WCS-based difference imaging driver software | MJI
| write software using 16.1 to compare effect on difference imaging produce preliminary report | MJI
16 | interpolation techniques and PSF modeling
16.1 | investigate alternative interpolation/PSF schemes |  |  |  | 10
| finish review and write short report on alternatives | DWE
16.3 | implications for deriving catalogues and parameters |  |  |  | 10
| assess and write report on errors in catalogue parameters arising from using different interpolation schemes | DWE
16.4 | oversampled PSF generation per detector |  |  |  | 10
| write first pass PSF generator using optical test data | DWE