## 03Q2_casu_deliverables2
WP | CASU WP name /sub task / 03Q2 deliverable | name | date | end of month report | % done
#
1 | management and definition of project responsibilities
1.1 | report to VISTA, UKIDSS, JAC, ATC, GSC |  |  |  | 50
| provide monthly + quarterly reports on progress | MJI | 2003-05-02 | STH+MJI produced spreadsheets of the costs of the deliverables and continued maintenance of the WP spreadsheets and Gantt charts. And set up to do via the fortnightly meetings, minutes and monthly reports
|  | MJI | 2003-06-03 | ongoing
|  | MJI | 2003-07-01 | Produced quarterly report | 100
www.ast.cam.ac.uk/~wfcam/
1.2 | interface control document between CASU and JAC |  |  |  | 50
| finalise ICD with JAC after summit hardware review | MJI | 2003-05-02 | Discussed and agreed baseline transfer mechanism of data from JAC to CASU; and outline hardware setup for data acquisition and summit pipeline
|  | MJI | 2003-06-03 | waiting for final decision on hardware
|  | MJI | 2003-07-01 | details of ICD agreed, awaiting sign off. | 50
www.jach.hawaii.edu/JACpublic/UKIRT/instruments/wfcam/ICD
1.3 | interface control document between CASU and WFAU |  |  |  | 50
| complete file transfer specification and finalise ICD | MJI | 2003-05-02
|  | MJI | 2003-06-03 | no further progress
|  | MJI | 2003-07-01 | updates sent to WFAU, awaiting agreement on output formats and completion of document. | 50
1.4 | define data structures and FITS headers |  |  |  | 50
| produce final agreed FITS header specification document | JRL | 2003-05-02 | discussion with JAC re grouping of observations into contiguous tiles
|  | JRL | 2003-06-03 | Good progress on tile issue, PV keywords need amending
|  | JRL | 2003-07-01 | A 'final' FITS header has been agreed upon between CASU and Edinburgh. Document completed including full specification and will be published by Alan Pickup ASAP. The document will continue to evolve subject to minor mods in headers. | 50
| create example MEFs with agreed FITS headers and dummy WFCAM size data | JRL
|  | JRL | 2003-06-03 | MEFs created with headers confirming to the most recent iteration of the header document. Using CIRSI data (so images 1/4 of WFCAM size) | 100
www.ast.cam.ac.uk/~jrl/wfcamdummy/
1.5 | define observing protocols |  |  |  | 100
| formalise agreement on allowed observing protocols | STH | 2003-07-01 | Discussion with JAC. At ROE meeting agreed that all WFCAM users must use UKIRT Observing Tool. Also agreed that WFCAM project will impose global calibration plan on all observers. This is now in the hands of JAC. | 100
1.6 | liaise with UKIDSS & JAC on observing strategy |  |  |  | 50
| in consultation with UKIDSS, JAC, ATC produce draft observing plan | DWE | 2003-05-02 | discussed with SJW the responsibility division between the UKIDSS survey scientist and the manager: ongoing
|  | DWE | 2003-06-03 | attended meeting with SJW and AA concerning overall survey strategy issues. SJW and AA clarified their ideas regarding survey manager
|  | DWE | 2003-07-01 | Draft observing plan now responsibility of UKIDSS survey manager. | 100
1.7 | liaise with UKIDSS & JAC on survey planning |  |  |  | 50
| help update UKIDSS diagrams and produce equivalent for 2 year plan | DWE | 2003-05-02 | UKIDSS survey planning: altered UKIDSS survey coverage plotting programme so that user defined areas can be added. Equivalent 2yr plan plotting programme has been written. Coverage of DR1 for SDSS has been incorporated into these programmes. Plots have been placed on the web and sent to SJW. Completed | 100
www.ast.cam.ac.uk/~wfcam/survey.html
| Survey simulator | DWE | 2003-06-03 | No need for DWE to write survey completion simulator - some work on this has already been carried out (and best place for this to be undertaken is JAC). Completed | 100
1.8 | liaise with UKIDSS and JAC on survey progress DB |  |  |  | 50
| work with JAC to resolve connectivity issues | JRL | 2003-05-02 | solved connectivity problem with JAC's archive server. Working towards mirroring of comments and progress database.
|  |  | 2003-06-03 | connectivity restored | 100
| create mirror copy of progress DB in Sybase | JRL
|  | JRL | 2003-06-03 | have begun discourse with JAC personnel
|  | JRL | 2003-07-01 | Awaiting reponse from JAC staff before full mirroring can take place | 10
1.9 | system documentation
| maintain WWW pages | DWE | 2003-05-02 | Updated WWW pages
|  | DWE | 2003-06-03 | Updated WWW pages
|  | DWE | 2003-07-01 | Updated WWW pages - reorgnaised links to all documentation
www.ast.cam.ac.uk/~wfcam
| further funding bids | STH | 2003-06-03 | Further updates of WPs for future planning for VDFS
|  | STH | 2003-07-01 | Generation of new WPs, Gantt charts and spreadhseets for VEGA
2 | ESO VISTA software interface deliverables and documentation
2.1 | VDFS user requirements document | PSB | 2003-05-02 | document structures in place, meeting arranged with WJS | 50
| write first outline draft | PSB | 2003-06-03 | draft document for PDR being fleshed out
|  | PSB | 2003-07-01 | Outline draft in place | 100
www.ast.cam.ac.uk/~wfcam/documentation.html
2.2 | data reduction specification document |  |  |  | 10
| write first outline draft | PSB | 2003-06-03 | very outline document started
|  |  | 2003-07-01 | Outline draft in progress | 10
2.3 | calibration plan document |  |  |  | 10
| write first outline draft | PSB | 2003-06-03 | Outline document being prepared, off-sky calibration being made compatible with AIT
|  |  | 2003-07-01 | Outline draft in progress | 10
2.8 | liaise with VISTA IR camera development team
| preliminary discussions | PSB | 2003-06-03 | Liaised with camera team regarding overlap between pipeline and camera AIT requirements, brainstorming session with WJS about telescope/camera technical details
|  | PSB | 2003-07-01 | meetings with project scientist and PI to discuss user requirements
3 | pipeline infrastructure and pipeline progress monitoring tools
3.2 | high level scripts to interrogate headers |  |  |  | 50
| convert to work with expected WFCAM/VISTA data and modify output | STH | 2003-05-02 | basic INT procedures in place
|  | STH | 2003-06-03 | ongoing
|  | STH | 2003-07-01 | WFCAM pipeline monitoring scripts in place – current status and DQC info reported to WWW pages. Progressed as far as possible without real data | 100
www.ast.cam.ac.uk/~wfcam/docs/campipehardware.html
3.6 | group documentation on pipeline infrastructure |  |  |  | 50
| write general infrastructure document (programmers manual) | JRL | 2003-07-01 | Version 0.6 programmer's manual written | 100
www.ast.cam.ac.uk/~wfcam/documentation.html
| stress test documentation and update as necessary | JRL | 2003-07-01 | Documentantion stress tested by JMI (feedback sent to JRL) | 50
4 | set up and manage raw science archive
5 | set up and manage data processing system hardware
5.1 | investigate hardware alternatives |  |  |  | 50
| write report on suggested hardware configuration for pipeline | MTB
|  | MTB | 2003-06-03 | Outline plan in place for individual rack mounted PCs + associated RAID5 disk systems with server level PCs + Ultrium tape store system and larger RAID5 disk systems
|  | MTB | 2003-07-01 | WWW document on hardware configuration and processing logistics written | 100
www.ast.cam.ac.uk/~wfcam/docs/campipehardware.html
6 | run standard pipeline
6.7 | Monitor product data transfer to WFAU |  |  |  | 0
| Initial tests | MJI | 2003-05-02 | Tested various transfer methods between Cambridge and Leicester and liaised with EHS at WFAU
|  | PSB | 2003-06-03 | Liaised with ROE EHS and Horst M. about network tuning and assisted in some testing
7 | development work for summit pipeline
7.1 | interface test pipelines in ORAC-DR |  |  |  | 50
| deliver updated set of routines and recipes to CVS at JAC | JRL | 2003-05-02 | discussion with JAC re methods to aid in the synchronisation of pipeline modules between CASU and JAC. CVS software modules - CVS repository at JAC
|  | JRL | 2003-06-03 | A version has been deposited, but not the latest, will be upgraded soon
|  | JRL | 2003-07-01 | A pipeline to reduce dummy WFCAM data has been written and deposited in the JAC CVS repository. The latest versions of the CIRDR reduction modules are also in the CVS | 100
| fix inconsistencies in current ORAC-DR recipes as per recommendations | JRL
|  | JRL | 2003-06-03 | no progress
|  | JRL | 2003-07-01 | fixed ORAC-DR recipes | 100
7.2 | implement WFCAM pipeline at summit
| Evaluate image compression schemes | JRL | 2003-05-02 | evaluating image compression schemes to speed up data flow
|  | JRL | 2003-07-01 | Tested various schemes and chose Rice tile algorithm. Agreed with JAC and WFAU
7.3 | documentation for ORAC-DR interface |  |  |  | 50
| deliver updated documentation as development proceeds | JRL | 2003-07-01 | Update documentation delivered | 100
8 | development and testing of standard 2d processing
8.1 | further development of standard pipeline |  |  |  | 50
| test alternative processing strategies, tabulate output changes | JRL | 2003-05-02 | ongoing investigation of optimal ways of removing instrumental signature with flats from various sources (sky, dome etc) and sky subtraction
|  | JRL | 2003-06-03 | ongoing
|  | JRL | 2003-07-01 | further tests still required - anticipate that this task will continue to run even when WFCAM is generating on-sky data | 50
| convert existing prototype modules for crosstalk correction | JRL | 2003-05-02 | devised, wrote and tested general purpose pipeline module for correcting crosstalk
|  | JRL | 2003-06-03 | Written and tested. Finished | 100
| devise persistence correction strategies | JRL | 2003-05-02 | ongoing work on general purpose pipeline module for persistance
|  | JRL | 2003-06-03 | Written and tested. Finished | 100
| incorporated front-end standard pipeline modules in WFCAM trial pipeline | JRL | 2003-07-01 | Done | 100
8.2 | liaison with WFCAM development team
| assess engineering test data for above problems and report | STH
|  | STH | 2003-06-03 | Updated report on first WFCAM device made available by ATC. Second device in Edinburgh, third expected this month
|  | STH | 2003-07-01 | no further test data received | 10
8.3 | partake in planning commissioning observations |  |  |  | 50
| liaise with ATC/JAC and draw up draft plan emphasising calibration requirements | STH
|  | STH | 2003-06-03 | Draft plan for photometric calibration plan written. Document being drafted for 2d calibration plan. Both to be presented in ROE 12-13 June
|  | STH | 2003-07-01 | See photometric calibration document. Also agreed 'on sky characterisation' period for WFCAM. Draft plan for key steps in characterisation agreed. Mark Casali is collating input for comissioning plan. | 100
www.ast.cam.ac.uk/~wfcam/docs/photom.pdf
8.6 | documentation for 2D processing software |  |  |  | 50
| write documentation | JRL | 2003-07-01 | documentation built into code - filtered into html when compiled | 100
| stress test documentation and update as needed | STH | 2003-07-01 | stress testing in progress | 50
8.7 | comparison between automated and manual data products |  |  |  | 0
| in collaboration with SJW trial UFTI/CIRPASS data through pipeline, compare with manually reduced data, write report | STH
|  | STH | 2003-06-03 | Not started
|  | STH | 2003-07-01 | Need to agree suitable test data to use in trial. Best to defer until real WFCAM data acquired. | 0
9 | development and testing of standard catalogue products
9.1 | add in new measures requested |  |  |  | 10
| produce first version of catalogue software with extra measures | MJI
|  | MJI | 2003-06-03 | no progress
|  | MJI | 2003-07-01 | Header structure defined and put in place. | 10
9.3 | generate model simulations of expected data |  |  |  | 50
| generate noisy (WFCAM/VISTA characteristics) images of simple objects (stars, ellipses) at the correct resolutions | STH
|  | STH | 2003-06-03 | Not started
|  | STH | 2003-07-01 | Produced script to generate assorted test images containing stars and galaxies using ARTDATA within IRAF. | 100
| produce more detailed simulated UKIRT observations of high and low latitude fields | STH
|  | STH | 2003-06-03 | Not started
|  | STH | 2003-07-01 | No progress | 0
9.4 | assess catalogue parameter reliability |  |  |  | 10
| run prototype pipeline on simulations and compare derived parameters with model data, write report | DWE
|  | DWE | 2003-07-01 | Infrastructure in place, awaiting simulations from 9.3 | 10
9.5 | intercomparison of catalogue products with other packages |  |  |  | 10
| agree detailed trials using INT WFC data and report on catalogue extraction and classification software comparisons | STH
|  | STH | 2003-06-03 | Not started
|  | STH | 2003-07-01 | Preliminary comparisons between Sextractor and imcore begun | 10
9.7 | documentation of catalogue software and products |  |  |  | 50
| produce draft document of above | MJI | 2003-06-03 | Documentation well underway
|  | MJI | 2003-07-01 | Version 0.6 document completed | 100
www.ast.cam.ac.uk/~wfcam/docs/pods/imcore_conf.pod
| stress test documentation and amend as necessary | STH | 2003-06-03 | No progress
|  | STH | 2003-07-01 | No progress | 0
10 | setup trial and run further processing pipeline
11 | photometric standards and calibration
11.1 | agree on primary standards |  |  |  | 50
| investigate requirements for VISTA+WFCAM and possible shortcomings e.g. colour range | STH | 2003-05-02 | Began document to take off from where NCH doc left off. Have arranged handover of this task with NCH and informed working group chair (Paul Hewett.
|  | STH | 2003-06-03 | Draft document completed and ready for circulation. Will be presented in ROE on 12-13 June
|  | STH | 2003-07-01 | version 1.1 photometry document completed | 100
| in consultation produce draft list suitable for WFCAM and VISTA | STH | 2003-05-02 | draft list in preparation
|  | STH | 2003-06-03 | Primary standards will be UKIRT FS and Persson standards for (YZ)JHK filters. Narrow band filter standards not chosen yet
|  | STH | 2003-07-01 | Document updated to include standard fields | 100
11.2 | choose secondary standard fields |  |  |  | 50
| find out which UKIDSS survey modes require these and in consultation with JAC+ATC propose secondary standard fields list | STH | 2003-05-02 | investigating 2MASS calib fields versus new fields using globular clusters. Discussion with Paul Hirst re viability of observing these pre-WFCAM using UFTI/UIST
|  | STH | 2003-06-03 | narrowing down choice of secondary standard fields. Will be discussed at ROE June 12-13
|  | STH | 2003-07-01 | V1 photometry document completed including choice of secondary standard fields | 100
12 | further development of DQC measures at summit and Cambridge
12.3 | implement 2mass for throughput measurement |  |  |  | 50
| produce prototype 2mass NIR data calibrator test on CIRSI data | MJI | 2003-05-02 | has arranged the acquisition of the 2MASS data products. This is about 80Gb and will be supplied asap
|  | MJI | 2003-06-03 | 2MASS data acquired and read onto disk. Being ingested into SYBASE and alternative efficient sorted file-based system as basis for calibration tests
|  | MJI | 2003-07-01 | 2MASS catalogues used to calibrate CIRSI data | 100
www.ast.cam.ac.uk/~wfcam/docs/wfcamtestphotom.html
12.4 | master calibration frames for detector monitoring |  |  |  | 10
| assess and report if current methods work on engineering WFCAM data | JRL
|  | JRL | 2003-07-01 | Ongoing. Devised naming comnvention plan for master calibration files. Awaiting suitable engineering test data | 10
13 | co-located list driven photometry
13.1 | test methods for master catalogue generation |  |  |  | 50
| extend to include different wavebands, document | MJI | 2003-05-02 | devised a procedure for creating master catalogues for multi-band data and incorporated it in pipeline toolkit development software
|  | MJI | 2003-06-03 | no change
|  | MJI | 2003-07-01 | Completed and documented. | 100
www.ast.cam.ac.uk/~wfcam/documentation.html
13.2 | develop basic WCS-based list driven photometer |  |  |  | 50
| extend above to WCS-based driven and deliver prototype to WFAU for evaluation | MJI | 2003-05-02 | design conceived
|  | MJI | 2003-06-03 | code development ongoing
|  | MJI | 2003-07-01 | version 0.6 code completed and documented. | 100
www.ast.cam.ac.uk/~wfcam/docs/pods/imcore_list.pod
14 | stacking and mosaicing
14.1 | develop benchmark simple stacking/mosaicing framework |  |  |  | 100
| improve to account for new WCS framework | MJI | 2003-05-02 | bugs fixed and enhanced current version 1.0 stacking and mosaicing software. Propagating changes into release (i.e C) version of code. Dumped current (old) verson already distributed to WFAU into CVS
|  | MJI | 2003-06-03 | Finished.
|  | MJI | 2003-07-01 | Documented | 100
www.ast.cam.ac.uk/~wfcam/docs/pods/
14.2 | NN algorithm with simple rejection |  |  |  | 100
| produce version updated with new WCS and deliver to WFAU | MJI
|  | MJI | 2003-06-03 | Can't release until new WCS form can be read by standard image browsers, documentation needed
|  | MJI | 2003-07-01 | code completed and documented. Deposited in CVS and delivered to WFAU | 100
www.ast.cam.ac.uk/~wfcam/docs/pods/
15 | continuum subtraction and basic difference imaging
15.1 | write WCS-based difference imaging driver software |  |  |  | 50
| Write software using 16.1 to compare effect of difference imaging and produce preliminary report | MJI | 2003-06-03 | Wrote prototype WCS_based difference imaging driver software
|  | MJI | 2003-07-01 | Version 0.6 driver software written and documented including simple scaled image subtraction scheme | 100
www.ast.cam.ac.uk/~wfcam/docs/pods/
15.2 | investigate and apply different interpolation methods |  |  |  | 50
| install and test existing difference imaging packages | DWE | 2003-05-02 | MJI contacted Pierre Astier from the S.Ne Cosmology project about acquiring the S.Ne adaptive kernel matching code. This is in parallel with DWE's work with Ian Bond's code.
|  | DWE | 2003-06-03 | Various implementations have been briefly looked at. Ian Bond's code has been installed and initial tests carried out.
|  | DWE | 2003-07-01 | Sne cosmology code installed and Initial tests complete. Tests also completed for Ian Bond's code. Now ready to commence intercomparison tests. | 100
16 | interpolation techniques and PSF modeling
16.1 | investigate alternative interpolation/PSF schemes |  |  |  | 10
| finish review and write short report on alternatives | DWE | 2003-05-02
|  | DWE | 2003-06-03 | Continuation of background reading and writing of test software concerning interleaving
|  | DWE | 2003-07-01 | code development ongoing. Investigation of test WFC data begun | 10
16.3 | implications for deriving catalogues and parameters |  |  |  | 10
| assess and write report on errors in catalogue parameters arising from using different interpolation schemes | DWE | 2003-07-01 | preliminary investigation started | 10
16.4 | oversampled PSF generation per detector |  |  |  | 10
| write first pass PSF generator using optical test data | DWE | 2003-07-01 | preliminary investigation started | 10
| Key |  |  | Hierarchy
| Workpackage Title |  | 12 | Workpackage
| Subtask incomplete |  | 12.1 | Task
| Subtask complete |  |  | subtask
Subtask added after quarter has started
| % subtask completed | 50
| % task completed | 50