## 03Q2_casu_deliverables2
WP | CASU WP name /sub task / 03Q3 deliverable | name | date | end of month report | % done
#
1 | Management and definition of project responsibilities
1.1 | report to VISTA, UKIDSS, JAC, ATC, GSC
| provide fornightly meeting minutes, monthly reports on progress + quarterly review reports and planning | MJI STH
1.2 | interface control document between CASU and JAC
| in conjunction with JAC produce and sign off hard copy | MJI
1.3 | interface control document between CASU and WFAU
| sign off Q2 ICD and finalise advanced processing product ICD | MJI
1.4 | define data structures and FITS headers
| update example MEF headers in reponse to feedback from ATC, JAC, WFAU | JRL
1.5 | define observing protocols | STH
1.6 | liaise with UKIDSS & JAC on observing strategy
| monitor progress | DWE
1.7 | liaise with UKIDSS & JAC on survey planning
| monitor progress | DWE
1.8 | liaise with UKIDSS and JAC on survey progress DB
| get feedback from JAC for mirroring of current progress database | JRL
| investigate use of Sybase Replication Server to perform the task | JRL
| deliver a working mirror copy of the OMP database | JRL
1.9 | system documentation
| update and maintain web pages of system docs | DWE
2 | ESO VISTA software interface deliverables and documentation
2.1 | VDFS user requirements document
| inc. QC and JPE and other feedback produce first real draft | PSB
2.2 | data reduction specification document
| produce first real draft of DRS document | PSB
2.3 | calibration plan document
| produce first real draft of calibration document | PSB
2.5 | ICD ESO/VPO
| draft version of Data Interface dictionary - esp. FITS header specification | PSB
2.8 | liaise with VISTA IR camera development team
| check camera documentation for conflicts/issues | PSB
| attend camera software design review and present CASU pipeline plans | PSB
3 | Pipeline infrastructure and pipeline progress monitoring tools
3.1 | interactive tools for running pipeline
| write a set of executable scripts for individual reduction tasks | JRL
| deliver a set of scripts that can be run to access individual tasks within CIRDR | JRL
3.2 | high level scripts to interrogate headers
| test and update using nights of CIRSI data | STH
3.3 | automatic progression of results to web pages
| interrogate pipeline progress database and produce test web page summaries | STH
3.6 | group documentation on pipeline infrastructure
| modify current documentation according to recommendations from stress tests. | JRL
4 | Set up and manage raw science archive
5 | Set up and manage data processing system hardware
5.2 | buy hardware and install
| tender for purchase and install data ingest server hardware/software | MTB
| with JAC conduct tests on Ultrium tapes as transport medium | MTB
6 | Run standard pipeline
7 | Development work for summit pipeline
7.1 | Interface test pipelines in ORAC-DR
| update and trial updated test pipelines | JRL
7.2 | implement WFCAM pipeline at summit
| CVS deposit and trial test ORACDR pipeline at JAC | JRL
7.3 | documentation for ORAC-DR interface
| continue to add to interface documentation as pipeline modules are written. These will appear in the CIRDR and ORACDR documentation sets | JRL
8 | Development and testing of standard 2d processing
8.1 | further development of standard pipeline
| process night(s) of CIRSI data with pseudo trial WFCAM pipeline | JRL
| rewrite routine for extraction of astrometric and photometric standards using 2MASS catalogue | JRL
| deliver report on flatfielding and sky subtraction strategies | JRL
| deliver new version of getstds | JRL
| write updated wrapper for improved version of catalogue software | JRL
8.2 | liaison with WFCAM development team
| assess engineering test data for reset anomaly, dark stability, cross-talk, image retention and linearity | JRL
8.3 | partake in planning commissioning/characterisation observations
| together with ATC/JAC finish calibration plan | STH
8.6 | documentation for 2D processing software
| drive test pipelines and update and deliver documentation as modules are written | JRL
8.7 | Comparison between automated and manual data products | STH
9 | Development and testing of standard catalogue products
9.1 | add in new measures requested
| Produce first version of catalogue software with all extra measures | MJI
9.2 | refine astrometric calibration model
| produce report on optical distortion simulations | MJI
9.3 | generate model simulations of expected data
| further development of simulations | STH
9.4 | assess catalogue parameter reliability
| run prototype pipeline on simulations and compare derived parameters with model data, write report | JMI
9.5 | intercomparison of catalogue products with other packages
| agree detailed trials using INT WFC data and report on catalogue extraction and classification software comparisons | JMI
9.7 | documentation of catalogue software and products
| update, fold in more detail and stress test | MJI
10 | Setup trial and run further processing pipeline
11 | Photometric standards and calibration
11.1 | agree on primary standards
| investigate and report on narrow-band filter calibration options | STH
11.2 | choose secondary standard fields
| incorporate feedback from working group on choice of secondary fields and update document | STH
12 | Further development of DQC measures at summit and Cambr
12.3 | implement 2mass for throughput measurement
| extend tests to night(s) of pseudo WFCAM pipeline processed CIRSI data | JMI
12.4 | master calibration frames for detector monitoring
| assess and report if current methods work on engineering WFCAM data | JRL
13 | Co-located list driven photometry
13.2 | develop basic WCS-based list driven photometer
| investigate practicalities and implement agreed ICD for parameters | MJI
14 | Stacking and mosaicing
14.1 | develop benchmark simple stacking/mosaicing framework
| bug fix and update as necessary | MJI
14.2 | NN algorithm with simple rejection
| bug fix and update as necessary | MJI
15 | Continuum subtraction and basic difference imaging
15.1 | write WCS-based difference imaging driver software
| bug fix and update as necessary | MJI
15.2 | investigate and apply different interpolation methods
| compare different software packages for difference imaging and produce report | DWE
16 | Interpolation techniques and PSF modeling
16.1 | investigate alternative interpolation/PSF schemes
| finish review and write short report on alternatives | DWE
16.3 | implications for deriving catalogues and parameters
| assess and write report on errors in catalogue parameters arising from using different interpolation schemes | DWE
16.4 | oversampled PSF generation per detector
| write first pass PSF generator using optical test data | DWE