## 03Q2_casu_deliverables2
WP | CASU WP name /sub task / 03Q3 deliverable | V.I.F. | name | date | end of month report | % done
#
1 | Management and definition of project responsibilities | 3
1.1 | report to VISTA, UKIDSS, JAC, ATC, GSC
| provide fornightly meeting minutes, monthly reports on progress + quarterly review reports and planning |  | MJI STH | 2003-07-31 | Continued maintainance of management spreadsheets and documents
1.2 | interface control document between CASU and JAC
| in conjunction with JAC produce and sign off hard copy |  | MJI
1.3 | interface control document between CASU and WFAU
| sign off Q2 ICD and finalise advanced processing product ICD |  | MJI
1.4 | define data structures and FITS headers |  |  |  |  | 50
| update example MEF headers in reponse to feedback from ATC, JAC, WFAU |  | JRL | 2003-07-31 | Creating complete night of data with WFCAM data and CIRSI images. Comments on headers from NCH being incorporated in minor revision of MEF headers | 50
1.5 | define observing protocols |  | STH |  | placeholder
1.6 | liaise with UKIDSS & JAC on observing strategy |  |  |  |  | 50
| monitor progress |  | DWE | 2003-07-31 | No contact | 0
1.7 | liaise with UKIDSS & JAC on survey planning |  |  |  |  | 50
| monitor progress |  | DWE | 2003-07-31 | No contact | 0
1.8 | liaise with UKIDSS and JAC on survey progress DB |  |  |  |  | 50
| get feedback from JAC for mirroring of current progress database |  | JRL | 2003-07-31 | No feedback yet from JAC | 0
| investigate use of Sybase Replication Server to perform the task |  | JRL | 2003-07-31 | Can't progress | 0
| deliver a working mirror copy of the OMP database |  | JRL | 2003-07-31 | Can't progress | 0
1.9 | system documentation |  |  |  |  | 50
| update and maintain web pages of system docs |  | DWE | 2003-07-31 | Updated as necessary | 50
2 | ESO VISTA software interface deliverables and documentation | 4
2.1 | VDFS user requirements document |  |  |  |  | 50
| inc. QC and JPE and other feedback produce first real draft |  | PSB | 2003-07-31 | first draft produced. Needs internal reviewing | 50
2.2 | data reduction specification document |  |  |  |  | 10
| produce first real draft of DRS document |  | PSB | 2003-07-31 | skeleton of first draft completed | 10
2.3 | calibration plan document |  |  |  |  | 10
| produce first real draft of calibration document |  | PSB | 2003-07-31 | Merged input from JRL, sourced ESO reference documents | 50
2.5 | ICD ESO/VPO |  |  |  |  | 10
| draft version of Data Interface dictionary - esp. FITS header specification |  | PSB | 2003-07-31 | Researched formats required by ESO, collected source docs | 10
2.8 | liaise with VISTA IR camera development team |  |  |  |  | 10
| check camera documentation for conflicts/issues |  | PSB | 2003-07-31 | Reviewed camera-control doc | 10
| attend camera software design review and present CASU pipeline plans |  | PSB
3 | Pipeline infrastructure and pipeline progress monitoring tools | 3.5
3.1 | interactive tools for running pipeline |  |  |  |  | 50
| write a set of executable scripts for individual reduction tasks |  | JRL | 2003-07-31 | Some instrument specific routines remain to be done | 50
| deliver a set of scripts that can be run to access individual tasks within CIRDR |  | JRL | 2003-07-31 | Generic routines finished and documented | 100
3.2 | high level scripts to interrogate headers |  |  |  |  | 50
| test and update using nights of CIRSI data |  | STH + JMI | 2003-07-31 | No progress - awaiting the generation of a night's worth of data | 0
3.3 | automatic progression of results to web pages |  |  |  |  | 10
| interrogate pipeline progress database and produce test web page summaries |  | STH + JMI | 2003-07-31 | Infrastructure in place and test WWW pages generated - need whole night of test data to progress and refine | 50
3.6 | group documentation on pipeline infrastructure |  |  |  |  | 50
| modify current documentation according to recommendations from stress tests. |  | JRL | 2003-07-31 | Incorporated feedback from JMI. More thorough revision will be put in place Aug/Sep | 50
4 | Set up and manage raw science archive | 0
5 | Set up and manage data processing system hardware | 2
5.2 | buy hardware and install
| tender for purchase and install data ingest server hardware/software |  | MTB
| with JAC conduct tests on Ultrium tapes as transport medium |  | MTB
6 | Run standard pipeline | 2.5
7 | Development work for summit pipeline | 1
7.1 | Interface test pipelines in ORAC-DR |  |  |  |  | 50
| update and trial updated test pipelines |  | JRL | 2003-07-31 | No feedback from JAC on current implementation so no revisions have been made. The next stage of the pipeline development is well underway | 50
7.2 | implement WFCAM pipeline at summit |  |  |  |  | 10
| CVS deposit and trial test ORACDR pipeline at JAC |  | JRL | 2003-07-31 | Awaiting completion of 7.1 | 0
7.3 | documentation for ORAC-DR interface |  |  |  |  | 50
| continue to add to interface documentation as pipeline modules are written. These will appear in the CIRDR and ORACDR documentation sets |  | JRL | 2003-07-31 | in progress | 50
8 | Development and testing of standard 2d processing | 4
8.1 | further development of standard pipeline |  |  |  |  | 50
| process night(s) of CIRSI data with pseudo trial WFCAM pipeline |  | JRL | 2003-07-31 | Part of a night processed. Now awaiting completion of 1.4 | 50
| rewrite routine for extraction of astrometric and photometric standards using 2MASS catalogue |  | JRL | 2003-07-31 | Not started | 0
| deliver report on flatfielding and sky subtraction strategies |  | JRL | 2003-07-31 | Not started | 0
| write updated wrapper for improved version of catalogue software |  | JRL | 2003-07-31 | Awaiting latest version of catalogue generation from MJI | 0
8.2 | liaison with WFCAM development team |  |  |  |  | 10
| assess engineering test data for reset anomaly, dark stability, cross-talk, image retention and linearity |  | JRL | 2003-07-31 | No feedback from ATC. Will push for some results during Aug | 0
8.3 | partake in planning commissioning/characterisation observations |  |  |  |  | 50
| together with ATC/JAC finish calibration plan |  | STH | 2003-07-31 | In discussion with Sandy Leggett (ATC) - she will shortly furnish me with several nights worth of calibration photometry to refine calibration plan and examine nightly behaviour | 10
8.6 | documentation for 2D processing software |  |  |  |  | 50
| drive test pipelines and update and deliver documentation as modules are written |  | JRL | 2003-07-31 | Revised documentation tree to fix inter-doc linking errors. Added tree for standalone script documentation (3.1) | 50
8.7 | Comparison between automated and manual data products |  |  |  |  | 10
| acquire suitable pre-WFCAM test datasets |  | STH | 2003-07-31 | Obtained FIRES (VLT ISAAC) raw data and calibration frames. Contacted Steve Warren with proposals for data sets. | 50
| pipeline process datasets |  | STH | 2003-07-31 | No progress yet
9 | Development and testing of standard catalogue products | 4
9.1 | add in new measures requested
| Produce first version of catalogue software with all extra measures |  | MJI
9.2 | refine astrometric calibration model
| produce report on optical distortion simulations |  | MJI
9.3 | generate model simulations of expected data |  |  |  |  | 50
| further development of simulations |  | STH + JMI | 2003-07-31 | Thorough investigations of Skymaker and ARTDATA completed. Skymaker used to generate detailed simulations of stellar fields, Simulations include microstepping tests. Galaxy generation still under investigation | 50
9.4 | assess catalogue parameter reliability |  |  |  |  | 50
| run prototype pipeline on simulations and compare derived parameters with model data, write report |  | JMI | 2003-07-31 | Preliminary report written, includes input--output comparison | 50
www.ast.cam.ac.uk/~wfcam/internal/reports/simul/
9.5 | intercomparison of catalogue products with other packages |  |  |  |  | 10
| agree detailed trials using INT WFC data and report on catalogue extraction and classification software comparisons |  | JMI | 2003-07-31 | Sextractor vs Imcore comparisons made using simulations. | 10
9.7 | documentation of catalogue software and products
| update, fold in more detail and stress test |  | MJI
10 | Setup trial and run further processing pipeline | 3
11 | Photometric standards and calibration | 3
11.1 | agree on primary standards |  |  |  |  | 50
| investigate and report on narrow-band filter calibration options |  | STH | 2003-07-31 | No progress.
11.2 | choose secondary standard fields
| incorporate feedback from working group on choice of secondary fields and update document |  | STH | 2003-07-31 | Updated document following ROE meeting. Used 2MASS dataset to refine choice of standard fields. Now awaiting results of discussion with Sandy Leggett and analysis of UFTI data.
12 | Further development of DQC measures at summit and Cambr | 2
12.3 | implement 2mass for throughput measurement |  |  |  |  | 50
| extend tests to night(s) of pseudo WFCAM pipeline processed CIRSI data |  | JMI | 2003-07-31 | Awaiting data (1.4) | 0
12.4 | master calibration frames for detector monitoring |  |  |  |  | 10
| assess and report if current methods work on engineering WFCAM data |  | JRL | 2003-07-31 | Awaiting engineering data from ATC | 0
13 | Co-located list driven photometry | 3
13.2 | develop basic WCS-based list driven photometer
| investigate practicalities and implement agreed ICD for parameters |  | MJI
14 | Stacking and mosaicing | 4
14.1 | develop benchmark simple stacking/mosaicing framework
| bug fix and update as necessary |  | MJI
14.2 | NN algorithm with simple rejection
| bug fix and update as necessary |  | MJI
15 | Continuum subtraction and basic difference imaging | 4
15.1 | write WCS-based difference imaging driver software
| bug fix and update as necessary |  | MJI
15.2 | investigate and apply different interpolation methods |  |  |  |  | 50
| compare different software packages for difference imaging and produce report |  | DWE | 2003-07-31 | JMI has made progress on the report. Initial tests have been carried out on the three software packages under consideration using two datasets | 50
www.ast.cam.ac.uk/~wfcam/internal/reports/subtract
16 | Interpolation techniques and PSF modeling | 4
16.1 | investigate alternative interpolation/PSF schemes |  |  |  |  | 10
| finish review and write short report on alternatives |  | DWE | 2003-07-31 | Evaluating Swarp for use in interpolation tests | 10
16.3 | implications for deriving catalogues and parameters |  |  |  |  | 10
| assess and write report on errors in catalogue parameters arising from using different interpolation schemes |  | DWE | 2003-07-31 | No progress | 0
16.4 | oversampled PSF generation per detector |  |  |  |  | 10
| write first pass PSF generator using optical test data |  | DWE | 2003-07-31 | No progress | 0