## 03Q2_casu_deliverables2
WP | CASU WP name /sub task / 03Q3 deliverable | V.I.F. | name | date | end of month report | % done
#
1 | Management and definition of project responsibilities | 3
1.1 | report to VISTA, UKIDSS, JAC, ATC, GSC
| provide fornightly meeting minutes, monthly reports on progress + quarterly review reports and planning |  | MJI STH | 2003-07-31 | continued maintainance of management spreadsheets and documents
|  |  | MJI, STH | 2003-08-31 | ongoing
1.2 | interface control document between CASU and JAC |  |  |  |  | 50
| in conjunction with JAC produce and sign off hard copy |  | MJI | 2003-07-31 | no progress | 0
|  |  | MJI | 2003-08-31 | still not finished | 0
1.3 | interface control document between CASU and WFAU |  |  |  |  | 50
| sign off Q2 ICD and finalise advanced processing product ICD |  | MJI | 2003-07-31 | no progress | 0
|  |  | MJI | 2003-08-31 | still not finished | 0
1.4 | define data structures and FITS headers |  |  |  |  | 50
| update example MEF headers in reponse to feedback from ATC, JAC, WFAU |  | JRL | 2003-07-31 | comments on headers from NCH being incorporated in minor revision of MEF headers | 50
|  |  | JRL | 2003-08-31 | done. Further issues will apear close to commissioning so further tweaking will be needed then | 100
1.5 | define observing protocols |  | STH |  | placeholder
1.6 | liaise with UKIDSS & JAC on observing strategy |  |  |  |  | 50
| monitor progress |  | DWE | 2003-07-31 | ongoing | 0
|  |  | DWE | 2003-08-31 | ongoing | 50
1.7 | liaise with UKIDSS & JAC on survey planning |  |  |  |  | 50
| monitor progress |  | DWE | 2003-07-31 | ongoing | 0
|  |  | DWE | 2003-08-31 | ongoing | 50
1.8 | liaise with UKIDSS and JAC on survey progress DB |  |  |  |  | 50
| get feedback from JAC for mirroring of current progress database |  | JRL | 2003-07-31 | ongoing | 0
|  |  | JRL | 2003-08-31 | ongoing | 10
| investigate use of Sybase Replication Server to perform the task |  | JRL | 2003-07-31 | ongoing | 0
|  |  | JRL | 2003-08-31 | ongoing | 10
| deliver a working mirror copy of the OMP database |  | JRL | 2003-07-31 | ongoing | 0
|  |  | JRL | 2003-08-31 | ongoing | 10
1.9 | system documentation |  |  |  |  | 50
| update and maintain web pages of system docs |  | DWE | 2003-07-31 | updated as necessary | 50
|  |  | DWE | 2003-08-31 | Updated as necessary
2 | ESO VISTA software interface deliverables and documentation | 4
2.1 | VDFS user requirements document |  |  |  |  | 50
| inc. QC and JPE and other feedback produce first real draft |  | PSB | 2003-07-31 | first draft produced. Needs internal reviewing | 50
|  |  | PSB | 2003-08-31 | ongoing | 50
2.2 | data reduction specification document |  |  |  |  | 10
| produce first real draft of DRS document |  | PSB | 2003-07-31 | skeleton of first draft completed | 10
|  |  | PSB | 2003-08-31 | no progress | 10
2.3 | calibration plan document |  |  |  |  | 10
| produce first real draft of calibration document |  | PSB | 2003-07-31 | merged input from JRL, sourced ESO reference documents | 50
|  |  | PSB | 2003-08-31 | incorporated a number of changes to layout and content as a result of detailed discussion with local group | 50
2.5 | ICD ESO/VPO |  |  |  |  | 10
| draft version of Data Interface dictionary - esp. FITS header specification |  | PSB | 2003-07-31 | researched formats required by ESO, collected source docs | 10
|  |  | PSB | 2003-08-31 | produced DID-format file based on camera software document, and draft DID for primary headers including WFCAM-style observation markers. Used these and standard ESO TCS, IRACE detector and primary DID to produce draft dummy FITS header, which is the far easier way to let others digest the suggested record set | 50
2.8 | liaise with VISTA IR camera development team |  |  |  |  | 10
| check camera documentation for conflicts/issues |  | PSB | 2003-07-31 | reviewed camera-control doc | 10
|  |  | PSB | 2003-08-31 | some informal discussion | 10
| attend camera software design review and present CASU pipeline plans |  | PSB | 2003-07-31 | no progress | 0
|  |  | PSB | 2003-08-31 | no progress | 0
3 | Pipeline infrastructure and pipeline progress monitoring tools | 3.5
3.1 | interactive tools for running pipeline |  |  |  |  | 50
| write a set of executable scripts for individual reduction tasks |  | JRL | 2003-07-31 | some instrument specific routines remain to be done | 50
|  |  | JRL | 2003-08-31 | added a few more, not quite finished | 50
| deliver a set of scripts that can be run to access individual tasks within CIRDR |  | JRL | 2003-07-31 | generic routines finished and documented | 100
3.2 | high level scripts to interrogate headers |  |  |  |  | 50
| test and update using nights of CIRSI data |  | STH + JMI | 2003-07-31 | no progress - awaiting the generation of a night's worth of data | 0
|  |  | STH + JMI | 2003-08-31 | entire night of CIRSI data now run through pipeline and scripts tested and modified accordingly | 100
3.3 | automatic progression of results to web pages |  |  |  |  | 50
| interrogate pipeline progress database and produce test web page summaries |  | STH + JMI | 2003-07-31 | infrastructure in place and test WWW pages generated - need whole night of test data to progress and refine | 50
|  |  | STH + JMI | 2003-08-31 | web page summaries now updated to include results of complete night's worth of processing - see report | 100
http://www.ast.cam.ac.uk/~wfcam/documentation.html
3.6 | group documentation on pipeline infrastructure |  |  |  |  | 50
| modify current documentation according to recommendations from stress tests. |  | JRL | 2003-07-31 | incorporated feedback from JMI, more thorough revision will be put in place Aug/Sep | 50
|  |  | JRL | 2003-08-31 | no further progress | 50
4 | Set up and manage raw science archive | 0
5 | Set up and manage data processing system hardware | 2
5.2 | buy hardware and install |  |  |  |  | 50
| tender for purchase and install data ingest server hardware/software |  | MTB | 2003-07-31 | investigated alternative suppliers for data ingest server but awaiting test results on LTO-1/2's before proceeding | 10
|  |  | MTB | 2003-08-31 | about to place order for data ingest server and LTO-II system | 50
| conduct tests on Ultrium tapes as transport medium |  | MTB | 2003-07-31 | awaiting results | 10
|  |  | MTB | 2003-08-31 | preliminary test results from ROE encouraging., awaiting further test results | 50
6 | Run standard pipeline | 2.5
7 | Development work for summit pipeline | 1
7.1 | Interface test pipelines in ORAC-DR |  |  |  |  | 50
| update and trial updated test pipelines |  | JRL | 2003-07-31 | no feedback from JAC on current implementation so no revisions have been made, the next stage of the pipeline development is well underway | 50
|  |  | JRL | 2003-08-31 | still awaiting feedback from JAC | 50
7.2 | implement WFCAM pipeline at summit |  |  |  |  | 10
| CVS deposit and trial test ORACDR pipeline at JAC |  | JRL | 2003-07-31 | awaiting completion of 7.1 | 0
|  |  | JRL | 2003-08-31 | awaiting completion of 7.1 | 0
7.3 | documentation for ORAC-DR interface |  |  |  |  | 50
| continue to add to interface documentation as pipeline modules are written. These will appear in the CIRDR and ORACDR documentation sets |  | JRL | 2003-07-31 | in progress | 50
|  |  | JRL | 2003-08-31 | awaiting completion of 7.1 | 50
8 | Development and testing of standard 2d processing | 4
8.1 | further development of standard pipeline |  |  |  |  | 50
| process night(s) of CIRSI data with pseudo trial WFCAM pipeline |  | JRL | 2003-07-31 | part of a night processed. Now creating complete night(s) of data with WFCAM headers and CIRSI images | 50
|  |  | JRL | 2003-08-31 | completed | 100
| rewrite routine for extraction of astrometric and photometric standards using 2MASS catalogue |  | JRL | 2003-07-31 | JMI has written an efficient extraction procedure for 2MASS will incorporate | 50
|  |  | JRL | 2003-08-31 | completed. Integrated into standard pipeline | 100
| deliver report on flatfielding and sky subtraction strategies |  | JRL | 2003-07-31 | not started | 0
|  |  | JRL | 2003-08-31 | some simulations and tests done | 10
| write updated wrapper for improved version of catalogue software |  | JRL | 2003-07-31 | awaiting latest version of catalogue generation from MJI | 0
|  |  | JRL | 2003-08-31 | MJI's complete version of the catalogue software is under development. Tested and integrated intermediate version which generates catalogues in the correct format though with dummy values for the new parameters. | 50
8.2 | liaison with WFCAM development team |  |  |  |  | 10
| assess engineering test data for reset anomaly, dark stability, cross-talk, image retention and linearity |  | JRL | 2003-07-31 | no feedback from ATC, awaiting new test data | 0
|  |  | JRL | 2003-08-31 | no test results available from ATC | 0
8.3 | partake in planning commissioning/characterisation observations |  |  |  |  | 50
| together with ATC/JAC finish calibration plan |  | STH | 2003-07-31 | in discussion with Sandy Leggett (ATC) - she will shortly furnish me with several nights worth of calibration photometry to refine calibration plan and examine nightly behaviour | 10
|  |  | STH | 2003-08-31 | some data received from SKL, but have yet to begin analysis. characterisation plan document now in place, preliminary comments sent to ATC from CASU. | 50
http://www.jach.hawaii.edu/JACpublic/UKIRT/instruments/wfcam/commissioning
8.6 | documentation for 2D processing software |  |  |  |  | 50
| drive test pipelines and update and deliver documentation as modules are written |  | JRL | 2003-07-31 | revised documentation tree to fix inter-doc linking errors, added tree for standalone script documentation (3.1) | 50
|  |  | JRL | 2003-08-31 | no further work done this month | 50
8.7 | Comparison between automated and manual data products |  |  |  |  | 10
| acquire suitable pre-WFCAM test datasets |  | STH | 2003-07-31 | obtained FIRES (VLT ISAAC) raw data and calibration frames, contacted Steve Warren with proposals for data sets. | 50
|  |  | STH | 2003-08-31 | Steve Warren has proposed some UFTI data to test, discussions continuing | 50
| pipeline process datasets |  | STH | 2003-07-31 | no progress yet | 0
|  |  | STH | 2003-08-31 | no progress yet | 0
9 | Development and testing of standard catalogue products | 4
9.1 | add in new measures requested |  |  |  |  | 10
| Produce first version of catalogue software with all extra measures |  | MJI | 2003-07-31 | finished mods for FITS header changes | 10
|  |  | MJI | 2003-08-31 | stalled | 10
9.2 | refine astrometric calibration model |  |  |  |  | 10
| produce report on optical distortion simulations |  | MJI | 2003-07-31 | updated plots using more recent distortion data | 50
|  |  | MJI | 2003-08-31 | no progress | 50
9.3 | generate model simulations of expected data |  |  |  |  | 50
| further development of simulations |  | STH + JMI | 2003-07-31 | thorough investigations of Skymaker and ARTDATA completed. Skymaker used to generate detailed simulations of stellar fields, simulations include microstepping tests. galaxy generation still under investigation | 50
|  |  | STH + JMI | 2003-08-31 | command line driven procedures in place to run simulations with choice of ARTDATA and Skymaker, succesfully tested by other group members. Application supports all WFCAM broadband filters with appropriate skybackground. | 100
9.4 | assess catalogue parameter reliability |  |  |  |  | 50
| run prototype pipeline on simulations and compare derived parameters with model data, write report |  | JMI | 2003-07-31 | preliminary report written, includes input--output comparison | 50
|  |  | JMI | 2003-08-31 | report completed | 100
www.ast.cam.ac.uk/~wfcam/internal/reports/simul/
9.5 | intercomparison of catalogue products with other packages |  |  |  |  | 10
| agree detailed trials using INT WFC data and report on catalogue extraction and classification software comparisons |  | JMI | 2003-07-31 | sextractor vs imcore comparisons made using simulations. | 10
|  |  | JMI | 2003-08-31 | results of comparison test incorporated in simulation report (9.4) | 100
9.6 | Completeness and error estimates |  |  |  |  | 50
| report on completeness and error estimates as a function of seeing and sky brightness |  | JMI | 2003-07-31 | simulations modified to incorporate seeing variations, sky brightness changes, and source density. Results included in report (9.4) | 50
|  |  | JMI | 2003-08-31 | report scrutinised by group and updated | 50
www.ast.cam.ac.uk/~wfcam/documentation.html
9.7 | documentation of catalogue software and products |  |  |  |  | 50
| update, fold in more detail and stress test |  | MJI | 2003-07-31 | no progress | 0
|  |  |  | 2003-08-31 | ongoing | 50
10 | Setup trial and run further processing pipeline | 3
11 | Photometric standards and calibration | 3
11.1 | agree on primary standards |  |  |  |  | 50
| investigate and report on narrow-band filter calibration options |  | STH | 2003-07-31 | no progress. | 0
|  |  | STH | 2003-08-31 | no progress. | 0
11.2 | choose secondary standard fields |  |  |  |  | 50
| incorporate feedback from working group on choice of secondary fields and update document |  | STH | 2003-07-31 | updated document following ROE meeting, used 2MASS dataset to refine choice of standard fields, now awaiting results of discussion with Sandy Leggett and analysis of UFTI data. | 50
|  |  |  | 2003-08-31 | no progress | 50
12 | Further development of DQC measures at summit and Cambr | 2
12.3 | implement 2mass for throughput measurement |  |  |  |  | 50
| extend tests to night(s) of pseudo WFCAM pipeline processed CIRSI data |  | JMI | 2003-07-31 | awaiting data (8.1) | 0
|  |  | JMI | 2003-08-31 | available data set now extended to one complete night. processed using latest version of pipeline. | 100
12.4 | master calibration frames for detector monitoring |  |  |  |  | 10
| assess and report if current methods work on engineering WFCAM data |  | JRL | 2003-07-31 | awaiting engineering data from ATC | 0
|  |  | JRL | 2003-08-31 | no test results available from ATC | 0
13 | Co-located list driven photometry | 3
13.2 | develop basic WCS-based list driven photometer |  |  |  |  | 50
| investigate practicalities and implement agreed ICD for parameters |  | MJI | 2003-07-31 | using INT WFC data to assess practical implementation methods | 10
|  |  | MJI | 2003-08-31 | developed this further on real data and have schema for practical implementation | 50
14 | Stacking and mosaicing | 4
14.1 | develop benchmark simple stacking/mosaicing framework |  |  |  |  | 100
| bug fix and update as necessary |  | MJI | 2003-07-31 | updated and fixed the odd bugs | 50
|  |  | MJI | 2003-08-31 | in conjunction with JMI fixing bugs and improving with results of extensive use and feedback. JMI has now produced prototype mosaicer that can produce arbitrarily large mosaics limited only by disk space. | 50
14.2 | NN algorithm with simple rejection |  |  |  |  | 100
| bug fix and update as necessary |  | MJI | 2003-07-31 | updated and fixed the odd bugs | 50
|  |  | MJI | 2003-08-31 | extensively tested and bug fixed with input from JMI. | 50
15 | Continuum subtraction and basic difference imaging | 4
15.1 | write WCS-based difference imaging driver software |  |  |  |  | 50
| bug fix and update as necessary |  | MJI | 2003-07-31 | updated and being used in package intercomparisons | 50
|  |  | MJI | 2003-08-31 | produced first CASU adaptive kernel version of fitsio_subtract for difference imaging using confidence maps correctly. Compared with Sne (Toads) and IAB version. Further improvements planned but initial results are promising | 50
15.2 | investigate and apply different interpolation methods |  |  |  |  | 50
| compare different software packages for difference imaging and produce report |  | DWE + JMI | 2003-07-31 | JMI has made progress on the report. Initial tests have been carried out on the three software packages under consideration using two datasets | 50
|  |  | DWE + JMI | 2003-08-31 | JMI has completed the report incorporating four software packages using 2 pairs of datasets
[5 empty] | www.ast.cam.ac.uk/~wfcam/documentation.html | 50
16 | Interpolation techniques and PSF modeling | 4
16.1 | investigate alternative interpolation/PSF schemes |  |  |  |  | 10
| finish review and write short report on alternatives |  | DWE | 2003-07-31 | evaluating Swarp for use in interpolation tests | 10
|  |  | DWE | 2003-08-31 | Swarp and artdata now set up to carry out simulations | 10
16.3 | implications for deriving catalogues and parameters |  |  |  |  | 10
| assess and write report on errors in catalogue parameters arising from using different interpolation schemes |  | DWE | 2003-07-31 | no progress | 0
|  |  | DWE | 2003-08-31 | no progress | 0
16.4 | oversampled PSF generation per detector |  |  |  |  | 10
| write first pass PSF generator using optical test data |  | DWE | 2003-07-31 | no progress | 0
|  |  | DWE | 2003-08-31 | no progress | 0