## WPs
WP # | WP Title | Resp | 2003 V1 |  |  |  | 2004 V2 |  |  |  | 2005 V3 |  |  |  | FTE V1 | FTE V2 | FTE V3 | dwe 2003 | dwe 2004 | jrl 2003 | jrl 2004 | mji 2003 | mji 2004 | rwa 2003 | rwa 2004 | sth 2003 | sth 2004 | mtb 2003 | mtb 2004 | psb 2003 | psb 2004 | jmi 2003 | jmi 2004 | VISTA Ind
|  |  | JFM | AMJ | JAS | OND | JFM | AMJ | JAS | OND | JFM | AMJ | JAS | OND | [19 empty] | 0-4
1 | Management and Definition of Responsibilities
|  | MJI | [12 empty] | 0.5 | 0.5 | 0.2 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 |  |  | 0.2 | 0.2 | [6 empty] | 3
1.1 | Report to VISTA Board, GSC
MJI
1.2 | Interface Control Document between CASU and JAC
MJI | bar: 2003 V1 JFM to 2003 V1 OND
1.3 | Interface Control Document between CASU and WFAU
MJI | bar: 2003 V1 JFM to 2003 V1 AMJ
1.4 | Define data structures and FITS headers
JRL | bar: 2003 V1 JFM to 2003 V1 AMJ
1.5 | Define observing protocols
STH | bar: 2003 V1 JFM to 2003 V1 AMJ
1.6 | Liaise with UKIDSS & JAC on observing strategy
DWE
1.7 | Liaise with UKIDSS & JAC on survey planning
DWE
1.8 | Liaise with UKIDSS & JAC on survey progress database
JRL
1.9 | System Documentation
STH
2 | ESO VISTA software deliverables and documentation
|  | PSB | [12 empty] | 0.5 | 0.5 | [13 empty] | 0.5 | 0.5 |  |  | 4
2.1 | DFS user requirements document
PSB | bar: 2003 V1 JFM to 2003 V1 OND
2.2 | Data reduction specification
PSB | bar: 2003 V1 JFM to 2003 V1 OND
2.3 | Calibration plan document for ESO
PSB | bar: 2003 V1 JFM to 2003 V1 OND
2.4 | Specification of calibration procedures for ESO
PSB | bar: 2003 V1 JFM to 2003 V1 OND
2.5 | Interface control document ESO/VPO (Data Interface Dictionary)
PSB | bar: 2003 V1 JAS to 2004 V2 OND
2.6 | Instrument specification and interface documents
PSB | bar: 2004 V2 JFM to 2004 V2 OND
2.7 | Delivery software modules Exposure Time Calculator
PSB | bar: 2004 V2 JFM to 2004 V2 OND
2.8 | Liase with VISTA IR camera development team
PSB | bar: 2003 V1 JFM to 2004 V2 OND
2.9 | Development of DQC measures
PSB | bar: 2004 V2 JFM to 2004 V2 OND
3 | Pipeline Infrastructure and Progress Monitoring Tools
|  | JRL | [12 empty] | 0.4 | 0.3 | 0.2 |  |  | 0.2 | 0.1 |  |  |  |  | 0.1 | 0.1 |  |  |  |  | 0.1 | 0.1 | 3.5
3.1 | Interactive tools for running pipeline
JRL | bar: 2003 V1 JAS to 2004 V2 AMJ
3.2 | High level scripts to interrogate headers
STH | bar: 2003 V1 JFM to 2003 V1 JAS; 2004 V2 AMJ
3.3 | Develop automatic progression of results to WWW pages
STH | bar: 2003 V1 JAS to 2004 V2 JAS
3.4 | Automate checks to spot failures of pipeline
STH | bar: 2003 V1 OND to 2004 V2 JAS
3.5 | Tools for fixing problem datasets
JRL | bar: 2004 V2 JFM to 2004 V2 OND
3.6 | Group Documentation for above
JRL | bar: 2003 V1 JFM to 2004 V2 OND
3.7 | Reprocessing after bug fixes or improvements to algorithms
RWA | bar: 2005 V3 JFM to 2005 V3 OND
4 | Set up and Manage Raw Science Archive
|  | RWA | [12 empty] | 0.1 | 0.1 | 0.1 |  |  | 0.1 |  |  |  |  | 0.1 | [8 empty] | 0
4.1 | Extend current UKIRT archive to cope with WFCAM
JRL | bar: 2003 V1 OND to 2004 V2 JAS
4.2 | Ingest and verify WFCAM data
RWA | bar: 2004 V2 JFM to 2005 V3 OND
5 | Set up and Manage Data Processing System Hardware
|  | MTB | [12 empty] | 0.2 | 0.2 | 0.2 | [10 empty] | 0.2 | 0.2 |  |  |  |  | 2
5.1 | Investigate alternatives (benchmarking, reliability etc)
MTB | bar: 2003 V1 JFM to 2003 V1 JAS
5.2 | Buy hardware and install software
MTB | bar: 2003 V1 JAS to 2003 V1 OND
5.3 | Integration and testing
MTB | bar: 2003 V1 OND to 2004 V2 JFM
5.4 | Manage day-to-day, maintenance and upgrades
MTB | bar: 2004 V2 JFM to 2005 V3 OND
5.5 | Hardware additions for further data processing system
MTB | bar: 2004 V2 JFM to 2005 V3 OND
6 | Run Standard Pipeline
|  | RWA | [12 empty] | 0 | 1 | 1 |  | 0.1 |  | 0.1 |  |  |  | 0.6 |  | 0.1 | [5 empty] | 0.1 | 2.5
6.1 | Ingest and verify data
RWA | bar: 2004 V2 JFM to 2005 V3 OND
6.2 | Update master calibration frames
JRL | bar: 2004 V2 JFM to 2005 V3 OND
6.3 | Monitor detector performance
JRL | bar: 2004 V2 JFM to 2005 V3 OND
6.4 | Oversee standard processing
RWA | bar: 2004 V2 JFM to 2005 V3 OND
6.5 | Astrometric calibration
DWE | bar: 2004 V2 JFM to 2005 V3 OND
6.6 | Photometric calibration
STH | bar: 2004 V2 JFM to 2005 V3 OND
6.7 | Verify science products and monitor DQC measures
RWA | bar: 2004 V2 JFM to 2005 V3 OND
6.8 | Monitor product data transfer to WFAU
JRL | bar: 2004 V2 JFM to 2005 V3 OND
7 | Development Work for Summit Pipeline
|  | JRL | [12 empty] | 0.2 | 0.1 | 0.1 |  |  | 0.2 | 0.1 | [12 empty] | 1
7.1 | Interface test pipelines to ORAC-DR
JRL | bar: 2003 V1 JFM to 2003 V1 JAS
7.2 | Implement WFCAM pipeline at summit
JRL | bar: 2003 V1 JAS to 2004 V2 JFM
7.3 | Documentation of interface
JRL | bar: 2003 V1 JFM to 2004 V2 JFM
7.4 | Upgrade and maintain summit pipeline
JRL | bar: 2004 V2 JFM to 2005 V3 OND
8 | Development and Testing of Standard 2D Processing
|  | STH | [12 empty] | 0.5 | 0.2 | 0 |  |  | 0.2 | 0.1 | 0.1 | 0.1 |  |  | 0.1 | [5 empty] | 0.1 |  | 4
8.1 | Further development of standard pipeline
JRL | bar: 2003 V1 JFM to 2003 V1 OND
8.2 | Liaison with WFCAM development team
JRL | bar: 2003 V1 JFM to 2003 V1 OND
8.3 | Partake in planning commissioning observations
STH | bar: 2003 V1 AMJ to 2003 V1 OND
8.4 | Participate directly in commissioning
STH | bar: 2003 V1 OND to 2004 V2 JFM
8.5 | Tuning pipeline during commissioning and after
JRL | bar: 2003 V1 OND to 2004 V2 JAS
8.6 | Documentation of 2D processing software
JRL | bar: 2003 V1 JFM to 2003 V1 OND
8.7 | Comparison between automated and manual data products
STH | bar: 2003 V1 JAS to 2004 V2 AMJ
9 | Development and Testing of Standard Catalogue Products
|  | DWE | [12 empty] | 0.5 | 0.2 | 0 | 0.1 |  | 0.1 |  | 0.1 | 0.1 |  |  | 0.2 | 0.1 | [6 empty] | 4
9.1 | Add in new measures requested
MJI | bar: 2003 V1 AMJ to 2004 V2 JFM
9.2 | Refine astrometric calibration model
MJI | bar: 2003 V1 JAS to 2004 V2 OND
9.3 | Generate model simulations of expected data
STH | bar: 2003 V1 AMJ to 2003 V1 OND
9.4 | Assess catalogue parameter reliability
DWE | bar: 2003 V1 AMJ to 2003 V1 OND
9.5 | Intercomparison of catalogue products with other packages
STH | bar: 2003 V1 JFM to 2004 V2 OND
9.6 | Completeness and error estimates
MJI | bar: 2003 V1 JAS to 2004 V2 OND
9.7 | Documentation of catalogue software and products
MJI | bar: 2003 V1 JFM to 2004 V2 OND
10 | Set up, Trial, and Run Further Processing Software
|  | MJI | [12 empty] | 0.1 | 0.4 | 1.5 |  |  |  | 0.1 | 0.1 | 0.1 | [9 empty] | 0.2 | 3
10.1 | Manage and run further processing stages
MJI | bar: 2004 V2 JFM to 2005 V3 OND
10.2 | Development and assessment of PSF options 1,2
MJI | bar: 2003 V1 OND to 2004 V2 OND
10.3 | Develop 1D/2D PSF-deconvolved Sersic profile fits
MJI | bar: 2004 V2 JFM to 2004 V2 OND
10.4 | Develop LSBG/nebulosity detection/parameterisation
MJI | bar: 2004 V2 JFM to 2005 V3 OND
10.5 | Full iterative profile fitting for stellar images
TBD | bar: 2005 V3 JFM to 2005 V3 OND
10.6 | Develop and optimise Bayesian image classification
TBD | bar: 2005 V3 JFM to 2005 V3 OND
10.7 | Modelling and simulations of further processing steps
STH | bar: 2004 V2 AMJ to 2005 V3 JFM
11 | Photometric Standards and Calibration
|  | STH | [12 empty] | 0.2 | 0.3 | 0.1 |  | 0.1 | [6 empty] | 0.2 | 0.2 | [6 empty] | 3
11.1 | Agree on primary standards
STH | bar: 2003 V1 JFM to 2003 V1 OND
11.2 | Choose secondary standard fields
STH | bar: 2003 V1 JFM to 2003 V1 OND
11.3 | Take part in commissioning observations
STH | bar: 2004 V2 JFM
11.4 | Reduce data, compute zero points and colour equations
STH | bar: 2004 V2 JFM to 2004 V2 AMJ
11.5 | Update, maintain and extend secondary standards system
STH | bar: 2004 V2 AMJ to 2005 V3 OND
11.6 | Investigate photometric calibration field systematics
STH | bar: 2004 V2 JFM to 2004 V2 JAS
11.7 | Assess extinction monitoring methods and develop measures
DWE | bar: 2003 V1 OND to 2004 V2 OND
12 | Further Development of DQC Measures at Summit and Cam
|  | JRL | [12 empty] | 0.2 | 0.2 | 0 |  |  | 0.1 | 0.1 | 0.1 | 0.1 | [10 empty] | 2
12.1 | Develop extra systematic noise measures
MJI | bar: 2003 V1 OND to 2004 V2 AMJ
12.2 | Refine current measures for WFCAM/VISTA data
JRL | bar: 2003 V1 OND to 2004 V2 JAS
12.3 | Implement 2MASS - cf. for throughput measures
MJI | bar: 2003 V1 AMJ to 2004 V2 AMJ
12.4 | Master calibration frames for detector monitoring
JRL | bar: 2003 V1 JFM to 2004 V2 JFM
13 | Co-Located List Driven Photometry
|  | MJI | [12 empty] | 0.2 | 0.1 | 0.5 |  |  |  |  | 0.1 | 0.1 | [8 empty] | 0.1 |  | 3
13.1 | Test methods for master catalogue generation
MJI | bar: 2003 V1 JFM to 2003 V1 AMJ
13.2 | Develop basic WCS-based list driven photometer
MJI | bar: 2003 V1 JFM to 2003 V1 OND
13.3 | Externally driven WCS photometry and define parameter set
MJI | bar: 2004 V2 JFM to 2004 V2 OND
14 | Stacking and Mosaicing
|  | MJI | [12 empty] | 0.2 | 0.3 | 0.5 |  |  |  | 0.1 | 0.1 | 0.1 | [8 empty] | 0.1 | 0.1 | 4
14.1 | Develop benchmark simple stacking/mosaicing framework
MJI | bar: 2003 V1 JFM to 2003 V1 AMJ
14.2 | Nearest neighbour algorithm with simple rejection
MJI | bar: 2003 V1 AMJ to 2003 V1 JAS
14.3 | More sophisticated rejection dealing with pixellation
MJI | bar: 2003 V1 OND to 2004 V2 JAS
14.4 | Stacking with optimum weighting and defect rejection
MJI | bar: 2004 V2 JFM to 2004 V2 OND
14.5 | Advanced stacking/image restoration for variable PSF
TBD | bar: 2005 V3 JFM to 2005 V3 OND
15 | Continuum Subtraction and Basic Difference Imaging
|  | STH | [12 empty] | 0.1 | 0.1 | 0.5 |  | 0.1 |  |  | 0.1 | [11 empty] | 4
15.1 | Simple WCS-based subtraction techniques
MJI | bar: 2003 V1 AMJ to 2003 V1 JAS; 2004 V2 AMJ
15.2 | Investigate and apply different interpolation methods
DWE | bar: 2003 V1 JFM to 2003 V1 JAS; 2004 V2 AMJ
15.3 | Develop adaptive kernel matching option
TBD | bar: 2005 V3 JFM to 2005 V3 OND
15.4 | Transient event detection
STH | bar: 2004 V2 JAS; 2005 V3 JFM to 2005 V3 OND
16 | Interpolation Techniques and PSF Modelling
|  | DWE | [12 empty] | 0.4 | 0.2 | 0 | 0.4 | 0.2 | [14 empty] | 4
16.1 | Investigate alternative interpolation/PSF schemes
DWE | bar: 2003 V1 JFM to 2003 V1 JAS
16.2 | Implications for different stacking methods
DWE | bar: 2003 V1 JAS to 2003 V1 OND
16.3 | Implications for deriving catalogues and parameters
DWE | bar: 2003 V1 JFM to 2003 V1 OND
16.4 | Oversampled PSF generation per detector
DWE | bar: 2003 V1 JFM to 2004 V2 OND
16.5 | Develop oversampled spatially varying PSF model
DWE | bar: 2004 V2 JFM to 2004 V2 OND
[15 empty] | 4.3 | 4.7 | 4.9 | 0.6 | 0.6 | 1 | 0.8 | 0.8 | 0.7 | 0 | 0.7 | 0.8 | 0.7 | 0.2 | 0.2 | 0.5 | 0.5 | 0.4 | 0.5
[18 empty] | dwe 2003 | dwe 2004 | jrl 2003 | jrl 2004 | mji 2003 | mji 2004 | rwa 2003 | rwa 2004 | sth 2003 | sth 2004 | mtb 2003 | mtb 2004 | psb 2003 | psb 2004 | mr new 2003 | mr new 2004
YEAR |  |  | DWE | JRL | MJI | MTB | PSB | RWA | STH | NEW | Total | [19 empty] | mean |  |  | 2.75
2003 | VDFS funded |  | 0.6 | 1 | 0.8 | 0.2 | 0.5 |  | 0.8 | 0.4 | 4.3 | [19 empty] | mode |  |  | 4
2004 | VDFS funded |  | 0.6 | 0.8 | 0.7 | 0.2 | 0.5 | 0.7 | 0.7 | 0.5 | 4.7 | [19 empty] | median |  |  | 3

## Resource
|  | available | 180 | 74.4658 | 105.5342
0 | men available | 0.4 | 18 | 7.4466 | 10.5534
1 | men available | 0 | 0 | 0 | 0
2 | men available | 1.3 | 58.5 | 24.2014 | 34.2986
3 | men available | 0.7 | 31.5 | 13.0315 | 18.4685
4 | men available | 0.5 | 22.5 | 9.3082 | 13.1918
5 | men available | 1 | 45 | 18.6164 | 26.3836
6 | men available | 0 | 0 | 0 | 0 | 0
7 | men available | 0.1 | 4.5 | 1.8616 | 2.6384
| Total mp available man yrs | 4 | 180 | 74.4658 | 105.5342
|  | from | 2002-10-01 | 2002-10-01 | 2002-10-01 | 2003-03-01 | 2003-10-01
|  | to | 2003-10-01 | 2003-10-01 | 2003-03-01 | 2003-10-01 | 2003-10-01
| 45 | works weeks to calendatr year |  | wks | pro rata | pro rata
|  | weeks to Mar 03 to Sep 03 |  | 52.1429 | 21.5714 | 30.5714 | 0
2 | Pipeline infrastructure and database progress monitoring development | [6 empty] | 22.5 | 9.3082 | 13.1918 | 13.2

## details_jpe
WORK | 2003 |  | 2003 |  | 2003 |  | 2003
| Jan-Mar | person | Apr-Jun | person | Jul-Sep |  | Oct-Dec
| Q1 | name | Q2 | name | Q3 | v1 | Q4 | v2 | v3
[6 empty] | FTE |  | FTE | FTE
-o- management and definition of project responsibilities:
report to VISTA, UKIDSS, VPO, JAC, VPB, GSC | 0.025 | Irwin | 0.025 | Irwin |  | 0.05 |  | 0.1 | 0.07
ICD between JAC and CASU | [5 empty] | 0.06
ICD between CASU and WFAU | [5 empty] | 0.06
FITS headers and data definition | [5 empty] | 0.05
define observing protocols | [5 empty] | 0.06
liaise on observing strategy and survey planning | [5 empty] | 0.06 |  | 0.1 | 0.07
liaise with JAC on DB progress monitoring | [5 empty] | 0.06 |  | 0.1 | 0.06
-o- pipeline infrastructure and pipeline progress monitoring tools:
interactive tools for running pipeline | [5 empty] | 0.16 |  | 0.08
develop high level scripts to interrogate headers | [5 empty] | 0.17
progress results to web page interface | [7 empty] | 0.07
automate checks to spot failures of pipeline | [7 empty] | 0.07
tools for fixing problem datasets | [7 empty] | 0.08
group documentation for above | [5 empty] | 0.17
reprocessing after bug fixes, new trials | [8 empty] | 0.2
-o- set up and manage raw science archive:
extend current UKIRT archive to cope with WFCAM | [5 empty] | 0.1 |  | 0.1
ingest and verify WFCAM data | [7 empty] | 0.1 | 0.1
-o- set up and manage data processing system hardware:
further investigate alternatives | [5 empty] | 0.1
buy hardware and install software | [5 empty] | 0.1
manage day-to-day, maintenance and upgrades | [7 empty] | 0.1 | 0.1
hardware additions for further data processing system | [7 empty] | 0.1 | 0.1
-o- run standard pipeline:
ingest and verify data | [7 empty] | 0.12 | 0.12
update master calibration frames | [7 empty] | 0.12 | 0.12
monitor detector performance | [7 empty] | 0.12 | 0.12
oversee standard processing | [7 empty] | 0.12 | 0.12
astrometric calibration | [7 empty] | 0.13 | 0.13
photometric calibration | [7 empty] | 0.13 | 0.13
verify science products and monitor DQC measures | [7 empty] | 0.13 | 0.13
monitor product data transfer to WFAU | [7 empty] | 0.13 | 0.13
-o- development work for summit pipeline:
interface test pipeline to ORAC DR | [5 empty] | 0.06
implement WFCAM pipeline at summit | [5 empty] | 0.07
documentation of interface | [5 empty] | 0.07
upgrade and maintain summit pipeline | [7 empty] | 0.1 | 0.1
-o- development and testing of standard 2d processing
further development of standard pipeline | [5 empty] | 0.06
liaison with WFCAM development team | [5 empty] | 0.07
partake in planning commissioning observations | [5 empty] | 0.07
participate directly in commissioning | [5 empty] | 0.07
tuning pipeline during commissioning and after | [5 empty] | 0.07 |  | 0.2
documentation of software | [5 empty] | 0.06
-o- development and testing of standard catalogue products:
add in new measures requested | [5 empty] | 0.08
refine astrometric calibration model | [5 empty] | 0.08 |  | 0.11
generate model simulations of observations | [5 empty] | 0.08
intercomparison of catalogue products | [5 empty] | 0.08 |  | 0.11
completeness and error estimates | [5 empty] | 0.09 |  | 0.1
documentation of software | [5 empty] | 0.09
-o- settup trial and run further processing pipeline:
manage and run further processing stages | [7 empty] | 0.15 | 0.5
development and assessment of PSF options 1,2 | [5 empty] | 0.1 |  | 0.15
develop 1D/2D PSF-deconvolved Sersic profile fits | [7 empty] | 0.15
develop LSBG/nebulosity detection/parameterisation | [7 empty] | 0.15 | 0.5
full iterative profile fitting for stellar images | [8 empty] | 0.5
develop and optimise Bayesian image classification | [8 empty] | 0.5
-o- photometric standards and calibration:
agree on primary standards | [5 empty] | 0.05
choose secondary standard fields | [5 empty] | 0.05
take part in commissioning observations | [5 empty] | 0.05
reduce data compute zero-points colour equations | [5 empty] | 0.05
update maintain and extend secondary standards system | [7 empty] | 0.1 | 0.1
investigate photometric calibration field systematics | [7 empty] | 0.2
assess extinction monitoring methods | [7 empty] | 0.1
-o- further development of DQC measures at summit and Cambridge:
develop extra systematic noise measures | [5 empty] | 0.05 |  | 0.05
refine current measures for WFCAM data | [5 empty] | 0.05 |  | 0.05
implement 2MASS cf. for throughput measures | [5 empty] | 0.05 |  | 0.05
local calibration frames for detector monitoring | [5 empty] | 0.05 |  | 0.05
-o- co-located list driven photometry:
test methods for master catalogue generation | [5 empty] | 0.15
develop basic WCS based WFCAM list driven photometer | [5 empty] | 0.15
externally driven WCS co-located photometry+params | [7 empty] | 0.2
GRID enable cross-photometry on non-WFCAM 2D datasets | [8 empty] | 0.5
-o- stacking and mosaicing:
develop benchmark simple stacking/mosaicing framework | [5 empty] | 0.1
nearest neighbour algorithm with simple rejection | [5 empty] | 0.1
more sophisticated rejection dealing with pixellation | [7 empty] | 0.25
stacking with optimum weighting and defect rejection | [7 empty] | 0.25
advanced stacking/image restoration for variable PSF | [8 empty] | 0.5
-o- continuum subtraction and basic difference imaging:
simple WCS based subtraction techniques | [5 empty] | 0.05 |  | 0.05
investigate different interpolation methods | [5 empty] | 0.05 |  | 0.05
develop adaptive kernel matching option | [8 empty] | 0.25
transient event detection | [8 empty] | 0.25
-o- interpolation techniques and PSF modelling:
find out what do other groups do | [5 empty] | 0.1
implications for different stacking methods | [5 empty] | 0.1
implications for deriving catalogues and parameters | [5 empty] | 0.1
oversampled PSF generation per detector | [5 empty] | 0.1 |  | 0.1
develop oversampled spatially varying PSF mdel | [7 empty] | 0.1
-o- modelling and simulations:
assessment of image processing cf. with interactive | [5 empty] | 0.1
assessment of image catalogue parameter reliability | [5 empty] | 0.1
modelling and simulations of further processing stages | [7 empty] | 0.2 | 0.1
-----------------------------------------------------------------------------------
WFCAM/VISTA | [5 empty] | 4 |  | 5.02 | 5.5
-----------------------------------------------------------------------------------
ESO specific (VISTA only)
-o- ESO VISTA software interface deliverables and documention: | [5 empty] | 0.5 |  | 0.5 | 0.5
interface control document (ICD) ESO/ATC/CASU
further development of DQC measures
specification of calibration procedures for ESO
calibration plan document for ESO
instrument specification and interface documents
delivery software modules exposure time calculator
liaise with VISTA IR camera development team
DFS user requirements document
[ESO stuff needs its own time framework - its not V1 or V2 or anything
that is WFCAM specific. Note that V1 was originally designed to
coincide with WFCAM science commissioning. When realistically is that ?]
-----------------------------------------------------------------------------------
ESO specific (VISTA only) | [5 empty] | 0.5 |  | 0.5 | 0.5
-----------------------------------------------------------------------------------
I've only detailed V1 and V2 stuff for WFCAM/VISTA and some of these naturally
carry over into V3 activities.
General things still to do:
- define more detailed timelines for all tasks
- set up discussion/information distribution forum on internal web page
- establish points of contact for various issues arising ??
- software distribution, other than JAC and WFAU do we ??
-----------------------------------------------------------------------------------
WFCAM/VISTA
Version 1: Ready for last quarter of 2003 with some continuation
Version 2: Develop during year after survey operations begin and
finalise by notionally end of 2004
Version 3. Rollout sometime (TBD) later though some developments
will be concurrent. V3's noted but not complete yet
just broad brush estimates for now.

## whole_jpe
WP # | WP Title | WP Start event | WP end Event |  |  | WP M'ger | Org'n'n Res'ble | WP Aims | Inputs | Outputs | Tasks | CW | SW | Matl£
[11 empty] | Total resource needed | 0 | 571.5 | 0
| Survey Parameters Definition |  | v1 |  |  |  | SPG/ VISTA
S1 | [Survey Planning Tools - ESO] |  | v1 |  |  |  | TBD
S1.1 |  |  | v1 |  |  |  | VISTA |  |  |  | agree nature with ESO
S1.2 |  |  | v1 | [7 empty] | Liason with IR Camera WP 6.8.4 Observation Software
S1.3 |  |  | v1 |  |  | Beard | TBD |  |  |  | do work
C2 | [Interaction with ESO/JAC]
C2.1 | DQC measures |  | v1 |  |  |  | CASU |  |  |  | Further development of DQC measures at telescope (UKIRT/VISTA) |  | 2.5
|  |  | v1 |  |  |  | CASU |  |  |  | Further development of DQC measures near telescope (JAC/Garching) |  | 1
C2.2 | Calibration Processing at JAC/Garching |  | v1 | [7 empty] | Interaction with ESO |  | 22.5
|  | v1 | v2 | [7 empty] | Interaction with ESO |  | 22.5
ICD | Data Interface to Camera |  | v1 |  |  |  | CASU/ATC /RAL
C2 | Telescope DQC and overseas Calibration pipelines |  | v1 |  |  |  | CASU
C2.1 | DFS User Requirements document |  | v1
C2.2 | Calibration Plan document |  | v1
C2.2.1 |  |  | v1 |  |  |  |  | definition of all N templates available for the instrument,
C2.2.2 |  |  | v1 |  |  |  |  | definition of formats of all raw data frames produced,
C2.2.3 |  |  | v1 |  |  |  |  | definition of data and procedures required for calibration,
C2.2.4 |  |  | v1 |  |  |  |  | definition of observing programs to acquire calibration data,
C2.2.5 |  |  | v1 |  |  |  |  | definition of procedures required for verification of instrument performance.
C2.3 | Template Signatures |  | v1 |  |  |  | Camera
C2.3.1 |  |  | v1 |  |  |  |  | one Template Signature file for each of the N templates defined in the Calibration Plan including detailed descriptions its function and parameters.
C2.4 | Instrument Description and Calibration Database |  | v1 |  |  |  | Camera
C2.4.1 |  |  | v1 |  |  |  |  | one file for each detector or optical component defining its properties,
C2.4.2 |  |  | v1 |  |  |  |  | one file for each physical data set defined in the Calibration Plan
C2.5 | Exposure Time Calculator |  | v1 |  |  |  | Camera
C2.5.1 |  |  | v1 |  |  |  |  | one instrument setup template including the associated dictionary,
C2.5.2 |  |  | v1 |  |  |  |  | one source code file for each component including full documentation,
C2.5.3 |  |  | v1 |  |  |  |  | one source code file of the instrument model with documentation
C2.5.4 |  |  | v1 |  |  |  |  | one file for each instrument setup with a verification procedure.
C2.6 | Data Interface Dictionary |  | v1
C2.6.1 |  |  | v1 |  |  |  |  | one file defining the Data Interface Dictionary for the instrument conforming to the DICB standard.
C2.7 | Data Reduction Specifications |  | v1 |  |  |  | CASU
C2.7.1 |  |  | v1 |  |  |  |  | Data Reduction Specifications document
C2.8 | Data Reduction Procedures |  | v1 |  |  |  | CASU
C2.8.n |  |  | v1 | [7 empty] | for each data reduction procedure 1 to N
C2.8.n.1 |  |  | v1 | [7 empty] | one source code file including documentation,
C2.8.n.2 |  |  | v1 | [7 empty] | one set of test data
C2.8.n.3 |  |  | v1 | [7 empty] | one verification procedure
C2.9 | Test and Calibration Data |  | v1
C2.9.1 |  |  | v1 |  |  |  |  | one full set of raw data frames produced by each of the N templates,
C2.9.2 |  |  | v1 |  |  |  |  | one full data set required to generate each calibration frame defined by the Calibration Plan.
ESO# | Build above into summit and overseas pipelines |  | v1 |  |  |  | ESO/ JAC
ICD | Data Interface to ESO/JAC (defined in 2 above) |  | v1
C3 | UK Pipeline |  | v1 |  |  |  | CASU
C3.1 | Simulated Data (for tests) |  | v1 |  |  |  | CASU
D0 | Management & definition of project responsibilities |  |  |  |  | Irwin
| report to VISTA, UKIDSS, JAC, ATC, WFAP, GSC |  | 0.05 | 0.1 | 0.07
| ICD between JAC and CASU |  | 0.06
| ICD between CASU and WFAU |  | 0.06
| FITS headers and data definition |  | 0.05
| define observing protocols |  | 0.06
| liaise on observing strategy and survey planning |  | 0.06 | 0.1 | 0.07
| liaise with JAC on DB progress monitoring |  | 0.06 | 0.1 | 0.06
D7 | Liason ESO/JAC WFCAM/VISTA WFAU/Other Projects | [5 empty] | all
D7.C.1 | Liason with IR Camera WP 6.8.4 Observation Software (including data header)
C3.2 | Pipeline Infrastructure & pipeline progress monitoring tools | [5 empty] | CASU |  |  |  | Software
| interactive tools for running pipeline |  | 0.16 | 0.08
| develop high level scripts to interrogate headers |  | 0.17
| progress results to web page interface |  |  | 0.07
| automate checks to spot failures of pipeline |  |  | 0.07
| tools for fixing problem datasets |  |  | 0.08
| group documentation for above |  | 0.17
| reprocessing after bug fixes, new trials |  |  |  | 0.2
Hardware
Logging
22.5
C3.3 | set up & manage raw science archive | [5 empty] | CASU
| extend current UKIRT archive to cope with WFCAM |  | 0.1 | 0.1
| ingest and verify WFCAM data |  |  | 0.1 | 0.1
D0.CH | set up and manage data processing system hardware | [5 empty] | CASU
| further investigate alternatives |  | 0.1
| buy hardware and install software |  | 0.1
| manage day-to-day, maintenance and upgrades |  |  | 0.1 | 0.1
| hardware additions for further data processing system |  |  | 0.1 | 0.1
9
4.5
C3.4 | Visualisation tools |  | v1 |  |  |  | CASU
C3.5 | DQC measures at CASU |  | v1 |  |  |  | CASU
|  |  | v1 | [7 empty] | Further development of DQC measures at Cambridge |  | 1
| 2d Processing | [9 empty] | Development and testing of standard 2d processing |  | 22.5
C3.6 | Single chip processing |  | v1 |  |  |  | CASU |  |  |  | Non-linearity correction
|  |  | v1 |  |  |  | CASU |  |  |  | Master calibration frame maintenance
|  |  | v1 |  |  |  | CASU |  |  |  | Bad pixel replacement
|  |  | v1 |  |  |  | CASU |  |  |  | Dark correction
|  |  | v1 |  |  |  | CASU |  |  |  | Fatfield correction
|  |  | v1 |  |  |  | CASU |  |  |  | Confidence map
|  |  | v1 |  |  |  | CASU |  |  |  | Defringe correction
|  |  | v1 |  |  |  | CASU |  |  |  | Sky subtraction
|  |  | v1 |  |  |  | CASU |  |  |  | Reset Anomaly correction
|  |  | v1 |  |  |  | CASU |  |  |  | Image Retention correction
C3.7 | Combinations of dithers/microsteps |  | v1 |  |  |  | CASU
|  |  | v1 |  |  |  | CASU |  |  |  | Interleave
|  |  | v1 |  |  |  | CASU |  |  |  | Rough WCS
|  |  | v1 |  |  |  | CASU |  |  |  | WCS Fit (pass 1)
C3.8 | Combinations of detectors
|  |  | v1 |  |  |  | CASU |  |  |  | Gain correction
|  |  | v1 |  |  |  | CASU |  |  |  | Tiling
|  |  | v1 |  |  |  | CASU |  |  |  | Tile Object Catalogues (pass 1)
|  |  | v1 |  |  |  | CASU |  |  |  | WCS Fit (pass 2)
|  |  | v1 |  |  |  | CASU |  |  |  | Tile Object Catalogues (pass 2)
|  |  | v1 | [7 empty] | Development and testing of standard catalogue products |  | 22.5
|  | v1 | v2 | [7 empty] | Source extraction options on any specified subset or stack of pixel data |  | 18
|  | v1 | v2 | [7 empty] | Simple methods for LSBGs, nebulosity detection and parameterisation |  | 22.5
C3.9 | Astrometric calibration |  | v1 |  |  |  | CASU
|  | v1 | v2 | [7 empty] | Refine and improve astrometric calibrtation scheme |  | 4.5
C3.10 | Photometric calibration |  | v1 |  |  |  | CASU
|  |  | v1 | [7 empty] | Setting up photometric standard calibration fields |  | 9
|  |  | v2 | [7 empty] | Maintain, extend photometric secondary standard calibrators |  | 9
|  |  | v2 | [7 empty] | Assess direct, secondary and other extinction monitoring methods |  | 9
|  |  | v2 | [7 empty] | Investigate photometric calibration field position systermatics |  | 4.5
C3.11 | Integration and Test |  | v1 |  |  |  | CASU
|  |  | v1 | [7 empty] | Tuning and science verification during commissioning and after |  | 22.5
C4 | UK Pipeline Operations Plan |  | v1 |  |  |  | CASU
C4.1 | Production pipeline | v1 | v2 | [7 empty] | Ingestion of data, verification, running standard pipeline |  | 45
ICD | Data Interface to Science Archive (WFAU) |  | v1 |  |  |  | CASU/WFAU
C6.1 | Software deliverable to Science Archive |  | v1 |  |  |  | CASU
C4 | Data Interface to Raw Data Users | v1 | v2 |  |  |  | CASU
|  | v1 | v2 | [7 empty] | Setting up and managing raw science data archive |  | 9
|  | v1 | v2 | [7 empty] | Analysis of archive pixel data at arbitrary positions defined by an input list |  | 18
C5 | Functional Development |  | v1 |  |  |  | CASU
| Algorithm developments |  | v1 |  |  |  | CASU
|  |  | v1 | [7 empty] | Co-located list photometry
|  |  | v1 | [7 empty] | Master catalogue generation, co-located list driven photometry |  | 13.5
|  | v1 | v2 | [7 empty] | Externally driven WCS co-located phtometry |  | 9
|  | v1 | v2 | [7 empty] | Cross photometry on non-WFCAM 2d datasets - GRID enabled processing |  | 22.5
|  |  | v1 | [7 empty] | Parameter estimation
|  |  | v1 | [7 empty] | Modelling and simulations for assessment of parameter reliability |  | 13.5
|  | v1 | v2 | [7 empty] | More modeling and simulations parameter reliability assessment |  | 9
|  |  | v1 |  |  |  | CASU |  |  |  | PSF fitting algorithms
|  |  | v1 | [7 empty] | Development and testing of further processing options 1,2 psf fitting |  | 9
|  | v1 | v2 | [7 empty] | Develop oversampled spatially varying PSF characterisation |  | 9
|  | v1 | v2 | [7 empty] | Further development and assessment of psf fitting options 1,2 |  | 13.5
|  | v1 | v2 | [7 empty] | Develop PSF deconvolved Sersic profile fits for galaxies |  | 13.5
|  |  | v1 |  |  |  | CASU |  |  |  | Resampling algoritms
|  |  | v1 | [7 empty] | Interpolation techniques, implications for different stacking methods |  | 9
|  |  | v1 |  |  |  | CASU |  |  |  | Stacking algorithms
|  |  | v1 | [7 empty] | Further development of benchmark simple stacking algorithm |  | 4.5
|  | v1 | v2 | [7 empty] | Stacking with optimum weigthing and defect rejection |  | 22.5
|  | v1 | v2 | [7 empty] | User-specified options for stacking pixel data |  | 40.5
|  |  | v1 |  |  |  | CASU |  |  |  | Difference algorithms
|  |  | v1 | [7 empty] | Continuum subtraction and basic difference imaging |  | 4.5
|  | v1 | v2 | [7 empty] | Generalised difference imaging (and subsequent source analysis) |  | 18
|  |  | v1 |  |  |  | CASU |  |  |  | Extraction of Variables
|  |  | v1 |  |  |  | CASU |  |  |  | Mosaicing algorithms
|  |  | v1 | [7 empty] | Further development of benchmark simple mosaicing algorithm |  | 4.5
|  | v1 | v2 | [7 empty] | Arbitrary sized, mosaiced images |  | 40.5
Development pipeline
|  | v1 | v2 | [7 empty] | Setting up and trialing of further processing pipeline |  | 13.5
A6 | Archive |  | v1 |  |  |  | WFAU
| Software delivered from Pipeline (CASU) |  | v1 |  |  |  | CASU
| see separate WBS for archive |  | v1
Note | for each WP the general approaqch will be: | [9 empty] | Check Definition and understanding of Requirements, Design including test plan, Check interfaces to other components, Plan, review and Approval, Code & document, Implement test Plan, Release code & documentation, maintain