## 03Q2_casu_deliverables2
WP | CASU WP name /sub task / 03Q4 deliverable | V.I.F. | name | date | end of month report | % done
#
1 | Management and definition of project responsibilities | 3
1.1 | report to VISTA, UKIDSS, JAC, ATC, GSC
| provide fornightly meeting minutes, monthly reports on progress + quarterly review reports and planning |  | MJI + STH
| prepare for and attend PPRP meeting in Feb |  | MJI + STH
| define CASU programme for e-sciII bid |  | MJI + STH
1.2 | interface control document between CASU and JAC |  |  |  | completed | 100
1.3 | interface control document between CASU and WFAU |  |  |  | completed | 100
1.4 | define data structures and FITS headers |  |  |  | completed | 50
1.5 | define observing protocols |  |  |  |  | 50
| define sensible range of suggested MSBs in conjunction with UKIDSS and JAC |  | MJI + STH
1.6 | liaise with UKIDSS & JAC on observing strategy & survey planning |  |  |  |  | 60
| monitor progress |  | DWE
1.7 | liaise with UKIDSS & JAC on VDFS products |  |  |  |  | 50
| monitor progress |  | DWE
1.8 | liaise with UKIDSS and JAC on survey progress DB |  |  |  |  | 50
1.9 | system documentation |  |  |  |  | 50
| update and maintain web pages of system docs |  | DWE
| write wrapper for WFCAM fits header for ESO |  | JRL
2 | ESO VISTA software interface deliverables and documentation | 4
2.1 | VDFS user requirements document |  |  |  |  | 50
| update & prepare for PDR |  | PSB
2.2 | data reduction specification document |  |  |  |  | 50
| update & prepare for PDR |  | PSB
2.3 | calibration plan document |  |  |  |  | 50
| update & prepare for PDR |  | PSB
| report on QDITS & CPL -v- CASU module & CFITSIO |  | PSB
2.5 | ICD ESO/VPO |  |  |  |  | 50
| update draft version of Data Interface dictionary - especially FITS header specification |  | PSB
| work on templates/Obs |  | PSB
| use ISAAC example for translating pipeline DID keywords to ESO style |  | PSB
2.8 | liaise with VISTA IR camera development team |  |  |  |  | 50
3 | Pipeline infrastructure and pipeline progress monitoring tools | 3.5
3.1 | interactive tools for running pipeline |  | JRL |  | paused | 75
3.2 | high level scripts to interrogate headers |  | STH, JMI |  | paused | 75
3.3 | automatic progression of results to web pages |  | STH, JMI |  | paused | 50
3.6 | group documentation on pipeline infrastructure |  |  |  |  | 40
| modify current documentation according to recommendations from stress tests. |  | JRL
4 | Set up and manage raw science archive | 0
5 | Set up and manage data processing system hardware | 2
5.2 | buy hardware and install |  |  |  | paused | 50
5.3 | integrating and testing |  |  |  |  | 50
| finish installing and testing pipeline and toolkit on data ingest server |  | MTB
5.4 | Manage day-to-day maintenance and upgrades |  |  |  |  | 0
| upgrade remaining dvelopment PCs to Debian Linux OS |  | MTB
6 | Run standard pipeline | 2.5
7 | Development work for summit pipeline | 1
7.1 | Interface test pipelines in ORAC-DR |  |  |  | completed | 100
7.2 | implement WFCAM pipeline at summit |  |  |  |  | 65
| End-to-end comparitive pipeline tests (ORACDR/CASU/Starlink) |  | JRL
| Demonstrate catalogue and non-catalogue DQCs |  | JRL
7.3 | documentation for ORAC-DR interface |  | JRL |  |  | 60
continue to add to interface documentation as pipeline modules are written. These will appear in the CIRDR and ORACDR documentation sets
8 | Development and testing of standard 2d processing | 4
8.1 | further development of standard pipeline |  |  |  |  | 75
| finish & deliver report on flatfielding and sky subtraction strategies |  | JRL
| write updated wrapper for improved version of catalogue software |  | JRL
| finish incorporating extra parameter measures |  | JRL
8.2 | liaison with WFCAM development team |  |  |  |  | 25
| assess engineering test data for reset anomaly, dark stability, cross-talk, image retention and linearity |  | JRL
8.3 | partake in planning commissioning/characterisation observations |  | STH |  | paused | 80
8.6 | documentation for 2D processing software |  |  |  |  | 50
| updates docs as necessary and as a result of feedback |  | JRL
8.7 | Comparison between automated and manual data products |  |  |  |  | 50
| finish pipeline processing of FIRES data |  | STH
| pipeline process UFTI data as it comes |  | STH
9 | Development and testing of standard catalogue products | 4
9.1 | add in new measures requested |  |  |  |  | 50
| test and debug new catalogue parameter measures |  | MJI
9.2 | refine astrometric calibration model |  | MJI |  | paused | 75
9.3 | generate model simulations of expected data |  | STH, JMI |  | paused | 80
9.4 | assess catalogue parameter reliability |  |  |  |  | 70
| refine parameter error estimates and check for systematics in new parameters |  | JMI
9.5 | intercomparison of catalogue products with other packages |  | JMI |  | paused | 60
9.6 | Completeness and error estimates |  |  |  |  | 50
| refine parameter error estimates and check for systematics |  | JMI
9.7 | documentation of catalogue software and products |  |  |  |  | 50
| update catalogue products documentation |  | MJI
10 | Setup trial and run further processing pipeline | 3
10.2 | development and assessment of PSF options 1,2 |  |  |  |  | 0
| produce prototype PSF fitting code level 1 |  | MJI
11 | Photometric standards and calibration | 3
11.1 | agree on primary standards |  |  |  |  | 90
| complete narrow band filter calibration plan and update document |  | STH
11.2 | choose secondary standard fields |  |  |  |  | 80
| incorporate feedback from working group on choice of secondary fields and update document |  | STH
| complete choice of secondary standard fields for VISTA and update photometry document |  | STH
11.7 | assess extinction monitoring methods and develop measures |  |  |  |  | 50
| complete investigation of UKIRT archive and write report |  | STH
| prepare for calibration WG meeting and present report |  | STH
12 | Further development of DQC measures at summit and Cambr | 2
12.1 | develop extra systematic noise measures |  |  |  |  | 30
| linked with detector characterisation |  | MJI
12.2 | Refine current measures for WFCAM/VISTA data |  |  |  |  | 30
| linked with detector characterisation |  | JRL
12.3 | implement 2mass for throughput measurement |  | JMI |  | paused | 75
12.4 | master calibration frames for detector monitoring |  |  |  |  | 35
| assess and report if current methods work on engineering WFCAM data |  | JRL
13 | Co-located list driven photometry | 3
13.2 | develop basic WCS-based list driven photometer |  |  |  |  | 70
| investigate practicalities and implement agreed ICD for parameters |  | MJI
13.3 | externally driven WCS photometry and define parameter set |  |  |  |  | 50
| refine, test and debug list-driven parameter estimator |  | MJI
14 | Stacking and mosaicing | 4
14.1 | develop benchmark simple stacking/mosaicing framework |  | MJI |  | complete | 100
14.2 | NN algorithm with simple rejection |  | MJI |  | complete | 100
14.3 | More sophisticated rejection dealing with pixellation |  |  |  |  | 50
| continue development of better spurion rejection allowing for pixellation |  | MJI
15 | Continuum subtraction and basic difference imaging | 4
15.1 | Simple WCS-based subtraction techniques |  | MJI |  | completed | 100
15.2 | investigate and apply different interpolation methods |  | MJI |  | completed | 100
15.3 | develop adaptive kernel matching option |  |  |  |  | 60
| continue debugging and enhancements to adaptive kernel package |  | MJI
16 | Interpolation techniques and PSF modeling | 4
16.1 | investigate alternative interpolation/PSF schemes |  |  |  |  | 50
| investigate PSF fitting algorithms and write report |  | DWE
16.2 | implications for different stacking methods |  |  |  |  | 10
| quantify effects of interpolation on stacked image quality |  | MJI
16.3 | implications for deriving catalogues and parameters |  |  |  |  | 50
| test profile fitting parameters and write report |  | DWE
16.4 | oversampled PSF generation per detector |  |  |  |  | 10
| write first pass PSF generator using optical test data |  | DWE