## 03Q2_casu_deliverables2
WP | CASU WP name /sub task / 04Q2 deliverable | V.I.F. | name | date | end of month report | %sub | % task
#
1 | Management and definition of project responsibilities | 3
1.1 | report to VISTA, UKIDSS, JAC, ATC, GSC | [5 empty] | 62
| provide fornightly meeting minutes, monthly reports on progress + quarterly review reports and planning |  | STH, MJI
| prepare for and present paper at SPIE meeting |  | MJI
1.2 | interface control document between CASU and JAC |  |  |  | completed |  | 100
1.3 | interface control document between CASU and WFAU |  |  |  | completed |  | 100
1.4 | define WFCAM data structures and FITS headers |  |  |  | completed |  | 100
| check SDF example for completeness |  | JRL
| use to generate test FITS header |  | JRL
1.5a | define WFCAM observing protocols | [5 empty] | 75
| monitor and help update MSB guidelines |  | MJI + STH
| check first pass survey MSBs |  | MJI + STH
1.5b | define VISTA observing protocols
| help define science and user requirements |  | MJI + PSB
1.6a | liaise with UKIDSS&JAC on WFCAM obs strategy, surveys planning | [5 empty] | 75
| monitor progress |  | DWE
1.6b | liaise with Project Scientist on VISTA observing strategy & survey planning
| monitor progress |  | PSB
1.7a | liaise with VDUC on VDFS products for WFCAM | [5 empty] | 62
| monitor progress |  | STH + MJI
1.7b | liaise with VDUC on VDFS products for VISTA
| monitor progress |  | MJI + STH
1.8a | liaise with UKIDSS and JAC on survey progress DB |  | JRL |  | paused |  | 50
1.9 | system documentation | [5 empty] | 62
| update and maintain web pages of system docs |  | DWE
2 | ESO VISTA software interface deliverables and documentation | 4
2.1 | VDFS user requirements document | [5 empty] | 30
| compile RID response document |  | PSB
| prepare for and attend PDR, update docs as appropriate |  | PSB
2.2 | data reduction specification document | [5 empty] | 30
| compile RID response document |  | PSB
| prepare for and attend PDR, update docs as appropriate |  | PSB
2.3 | calibration plan document | [5 empty] | 60
| compile RID response document |  | PSB
| prepare for and attend PDR, update docs as appropriate |  | PSB
2.5 | ICD ESO/VPO | [5 empty] | 60
| update DID and write first draft of DID doc for FDR |  | PSB
2.8 | liaise with VISTA IR camera development team | [5 empty] | 62
| continue liaising |  | PSB
3 | Pipeline infrastructure and pipeline progress monitoring tools | 3.5
3.1 | interactive tools for running pipeline |  | JRL |  | paused |  | 50
3.2 | high level scripts to interrogate headers |  | STH, JMI |  | paused |  | 50
3.3 | automatic progression of results to web pages |  | STH, JMI |  | paused |  | 50
3.6 | group documentation on pipeline infrastructure | [5 empty] | 55
| stress test documentation and update as necessary |  | JRL
4 | Set up and manage raw science archive | 0
5 | Set up and manage data processing system hardware | 2
5.2 | buy hardware and install |  | MTB |  | paused |  | 70
5.3 | integrating and testing |  | MTB |  | paused |  | 55
5.4 | Manage day-to-day maintenance and upgrades |  | MTB |  | paused |  | 25
6 | Run standard pipeline | 2.5
7 | Development work for summit pipeline | 1
7.1 | Interface test pipelines in ORAC-DR |  | JRL |  | completed |  | 100
7.2a | implement WFCAM pipeline at summit | [5 empty] | 75
| demonstrate catalogue and non-catalogue DQCs |  | JRL
7.3a | documentation for ORAC-DR interface | [5 empty] | 60
| update and deliver documentation as development proceeds |  | JRL
7.4a | upgrade and maintain summit pipeline WFCAM
| upgrade and maintain |  | JRL
8 | Development and testing of standard 2d processing | 4
8.1a | further development of standard pipeline for WFCAM | [5 empty] | 80
| finish implementing new version of imcore to include full param set |  | JRL
8.2a | liaison with WFCAM development team | [5 empty] | 30
| continue discussion on reset anomaly, crosstalk and linearity |  | JRL
| assess engineering test data for above problems and report |  | JRL
8.2b | liaison with Project Scientist & VISTA development team
| develop and test methodology for non-linearity correction, write report |  | MJI
8.3a | partake in planning WFCAM commissioning observations | [5 empty] | 80
| continue liaising with ATC/JAC |  | STH
8.3b | partake in planning VISTA comissioning observations
| liaise and discuss with VISTA PS |  | STH
8.6 | documentation for 2D processing software | [5 empty] | 50
| updates docs as necessary and as a result of feedback |  | JRL
8.7 | Comparison between automated and manual data products | [5 empty] | 75
| finish pipeline processing of FIRES data |  | STH
| compare FIRES with published results and write report |  | STH
| in collaboration with SJW trial UFTI/CIRPASS data through the pipeline, compare with manually reduced data, write report |  | STH
9 | Development and testing of standard catalogue products | 4
9.1 | add in new measures requested | [5 empty] | 60
| finish testing and debugging new catalogue parameter measures |  | MJI
9.2 | refine astrometric calibration model |  | MJI |  | paused |  | 80
9.3 | generate model simulations of expected data |  | STH, JMI |  | paused |  | 80
9.4 | assess catalogue parameter reliability | [5 empty] | 70
| refine parameter error estimates and check for systematics in new parameters - finish in conjunction with 9.1 |  | MJI
9.5 | intercomparison of catalogue products with other packages |  | JMI |  | paused |  | 60
9.6 | Completeness and error estimates | [5 empty] | 50
| refine parameter error estimates and check for systematics - finish in conjunction with 9.1 and 9.4 |  | JMI
9.7 | documentation of catalogue software and products | [5 empty] | 55
| update catalogue products documentation |  | MJI
10 | Setup trial and run further processing pipeline | 3
10.2 | development and assessment of PSF options 1,2 | [5 empty] | 50
| produce robust version of code for PSF level 1 |  | MJI
| produce prototype for PSF level 2 |  | MJI
10.3 | develop 1D/2D PSF-deconvolved Sersic profile fits
| assess GALFIT interactive package |  | MJI
11 | Photometric standards and calibration | 3
11.1 | agree on primary standards | [5 empty] | 90
| complete narrow band filter calibration plan and update document |  | STH
11.2 | choose secondary standard fields | [5 empty] | 80
| finish updates to photom doc and circulate |  | STH
11.7 | assess extinction monitoring methods and develop measures | [5 empty] | 50
| complete investigation of UKIRT archive and write report |  | STH
| simulate from night(s) data and estimate expected accuracy |  | STH
12 | Further development of DQC measures at summit and Cambr | 2
12.1 | develop extra systematic noise measures | [5 empty] | 50
| linked with detector characterisation |  | MJI
12.2 | Refine current measures for WFCAM/VISTA data | [5 empty] | 20
| linked with detector characterisation |  | JRL
12.3 | implement 2mass for throughput measurement |  | JMI |  | paused |  | 75
12.4 | master calibration frames for detector monitoring | [5 empty] | 35
| assess and report if current methods work on engineering WFCAM data |  | JRL
13 | Co-located list driven photometry | 3
13.2 | develop basic WCS-based list driven photometer | [5 empty] | 90
| investigate practicalities and implement agreed ICD for parameters - finish |  | MJI
13.3 | externally driven WCS photometry and define parameter set | [5 empty] | 75
| refine, test and debug list-driven parameter estimator - finish |  | MJI
14 | Stacking and mosaicing | 4
14.1 | develop benchmark simple stacking/mosaicing framework |  | MJI |  | complete |  | 100
14.2 | NN algorithm with simple rejection |  | MJI |  | complete |  | 100
14.3 | More sophisticated rejection dealing with pixellation | [5 empty] | 60
| continue development of better spurion rejection allowing for pixellation - finish |  | MJI
14.4 | Stacking with optimum wighting and defect rejection
| refine current weighting method, test and report on alternative schemes |  | MJI
15 | Continuum subtraction and basic difference imaging | 4
15.1 | Simple WCS-based subtraction techniques |  | MJI |  | completed |  | 100
15.2 | investigate and apply different interpolation methods |  | MJI |  | completed |  | 100
15.3 | develop adaptive kernel matching option | [5 empty] | 80
| continue debugging and enhancements to adaptive kernel package |  | MJI
16 | Interpolation techniques and PSF modeling | 4
16.1 | investigate alternative interpolation/PSF schemes | [5 empty] | 70
| investigate PSF fitting algorithms and write report - finish |  | DWE
16.2 | implications for different stacking methods | [5 empty] | 20
| quantify effects of interpolation on stacked image quality |  | MJI
16.3 | implications for deriving catalogues and parameters | [5 empty] | 70
| test PSF fitting using optical data and include results within above report from 16.1 |  | DWE
16.4 | oversampled PSF generation per detector | [5 empty] | 50
| develop more robust oversampled PSF generator |  | DWE