## 03Q2_casu_deliverables2
WP | CASU WP name /sub task / 04Q3 deliverable | V.I.F. | name | date | end of month report | %sub | % task
#
1 | Management and definition of project responsibilities | 3
1.1 | report to VISTA, UKIDSS, JAC, ATC, GSC | [5 empty] | 75
| provide fornightly meeting minutes, monthly reports on progress + quarterly review reports and planning |  | STH, MJI | 2004-07-31 | minutes and report produced | 10
|  |  | STH, MJI | 2004-08-31 | meetings held, minutes and report produced | 50
| prepare for and present paper at ADASS meeting |  | JRL | 2004-07-31 | abstract written and submitted | 10
|  |  | JRL | 2004-08-31 | nothing further this month | 10
1.2 | interface control document between CASU and JAC |  |  |  | completed |  | 100
1.3 | interface control document between CASU and WFAU |  |  |  | completed |  | 100
1.4 | define WFCAM data structures and FITS headers |  |  |  | completed |  | 100
1.5a | define WFCAM observing protocols | [5 empty] | 75
| check OT generated MSBs and create diagrams |  | MJI + STH | 2004-07-31 | no progress | 0
|  |  | MJI + STH | 2004-08-31 | MSBs generated for GPS, began investigation | 10
1.5b | define VISTA observing protocols
| help define science and user requirements |  | MJI + PSB | 2004-07-31 | example science goals collated from VDUC to be included in UKURD | 10
|  |  | MJI + PSB | 2004-08-31 | sent detailed comments on UKURD to WJS | 50
1.6a | liaise with UKIDSS&JAC on WFCAM obs strategy, surveys planning | [5 empty] | 75
| monitor progress |  | DWE | 2004-07-31 | nothing to report | 10
|  |  | DWE | 2004-08-31 | continued telecons | 50
| investigate MKO sky brightness |  | STH | 2004-07-31 | no progress | 0
|  |  | STH | 2004-08-31 | no progress | 0
1.6b | liaise with Project Scientist on VISTA observing strategy & survey planning
| monitor progress |  | PSB | 2004-07-31 | PSB held discussions with WJS | 10
|  |  | PSB | 2004-08-31 | nothing to report | 50
1.7a | liaise with VDUC on VDFS products for WFCAM | [5 empty] | 75
| monitor progress + attend meetings as necessary |  | STH + MJI | 2004-07-31 | up to date | 10
|  |  | STH + MJI | 2004-08-31 | nothing to report | 50
1.7b | liaise with VDUC on VDFS products for VISTA
| monitor progress + attend meetings as necessary |  | MJI + STH | 2004-07-31 | up to date | 10
|  |  | MJI + STH | 2004-08-31 | nothing to report | 50
1.8a | liaise with UKIDSS and JAC on survey progress DB |  | JRL |  | paused until commissioning |  | 75
1.9 | system documentation | [5 empty] | 75
| update and maintain web pages of system docs |  | DWE | 2004-07-31 | documentation updated as necessary | 10
|  |  | DWE | 2004-08-31 | documentation updated as necessary | 50
2 | ESO VISTA software interface deliverables and documentation | 4
2.1 | VDFS user requirements document | [5 empty] | 70
| agree RIXs |  | PSB | 2004-07-31 | comments fed back to JPE | 50
|  |  | PSB | 2004-08-31 | no progress. awaiting final issue of RIX response document. | 50
| update docs |  | PSB | 2004-07-31 | clearcut alterations made, now awaiting agreement on RIXs | 10
|  |  | PSB | 2004-08-31 | still awaiting agreement on RIXs | 10
2.2 | data reduction specification document | [5 empty] | 70
| agree RIXs |  | PSB | 2004-07-31 | comments fed back to JPE | 50
|  |  | PSB | 2004-08-31 | no progress. awaiting final issue of RIX response document. | 50
| update docs |  | PSB | 2004-07-31 | clearcut alterations made, now awaiting agreement on RIXs | 10
|  |  | PSB | 2004-08-31 | no progress. awaiting final issue of RIX response document. | 10
| produce report on QFITS/CPL for ESO |  | PSB | 2004-08-31 | report written and sent to JPE for review | 50
2.3 | calibration plan document | [5 empty] | 70
| agree RIXs |  | PSB | 2004-07-31 | comments fed back to JPE | 50
|  |  | PSB | 2004-08-31 | no progress. awaiting final issue of RIX response document. | 50
| update docs |  | PSB | 2004-07-31 | uncontroversial alterations made, now awaiting agreement on RIXs | 10
|  |  | PSB | 2004-08-31 | no progress. awaiting final issue of RIX response document. | 10
2.5 | ICD ESO/VPO | [5 empty] | 60
| update DID and write first draft of DID doc for FDR |  | PSB | 2004-07-31 | first draft DID almost complete barring input from JMS on TCS | 10
|  |  | PSB | 2004-08-31 | first draft DID sent to JPE for release | 100
2.7 | Delivery software modules for exposure time calculator | [5 empty] | 0
| develop mathematical description for ETC |  | PSB | 2004-07-31 | no progress | 0
|  |  | PSB | 2004-08-31 | began investigation based on ISAAC ETC | 10
| define scope of ETC |  | PSB | 2004-07-31 | no progress | 0
|  |  | PSB | 2004-08-31 | began initial investigation | 10
| write report |  | PSB | 2004-07-31 | no progress | 0
|  |  | PSB | 2004-08-31 | no progress | 0
2.8 | liaise with VISTA IR camera development team | [5 empty] | 75
| continue liaising |  | PSB | 2004-07-31 | productive interaction with SB on DID | 10
|  |  | PSB | 2004-08-31 | lots of discussion with JMS | 50
3 | Pipeline infrastructure and pipeline progress monitoring tools | 3.5
3.1 | interactive tools for running pipeline | [5 empty] | 60
| develop tools and document |  | JRL | 2004-07-31 | some more tools written and documented | 10
|  |  | JRL | 2004-08-31 | some more tools written and documented. Local catalogue searching added. | 50
3.2 | high level scripts to interrogate headers | [5 empty] | 50
| develop with WFC data |  | STH, JMI | 2004-07-31 | programmes written to extract status from image and catalogue headers. needs work to speed up and optomize method. present version takes 30 mins to run on 3000 files. | 10
|  |  | STH, JMI | 2004-08-31 | some speed up achieved by using cats were poss. will need to rethink method if this is too slow. | 50
3.3 | automatic progression of results to web pages | [5 empty] | 50
| develop with WFC data |  | STH, JMI | 2004-07-31 | script reports results to www pages - by machine and by run number | 50
|  |  | STH, JMI | 2004-08-31 | some testing and feedback received - improvements and extra plots added, including expected parameters from WFCAM headers and value checking. Investigating interactive plots/database scheme. | 50
3.4 | automatic checks to spot failure of pipeline | [5 empty] | 0
| use WFC data to develop a scheme |  | JMI, STH | 2004-07-31 | existing scheme allows failures to be spotted and reason diagnosed. work to be done on DQC parameter checking - current version includes astrometry. | 50
|  |  | JMI, STH | 2004-08-31 | most checks now in place, and pipeline failures easy to spot - planning a more automated approach | 50
3.6 | group documentation on pipeline infrastructure | [5 empty] | 60
| stress test documentation and update as necessary |  | JRL | 2004-07-31 | JMI used pipeline to process IPHAS data and reported problems back to JRL for incorporation | 10
|  |  | JRL | 2004-08-31 | problems reported by JMI fixed. | 50
4 | Set up and manage raw science archive | 0
4.1 | extend UKIRT archive to cope with WFCAM data | [5 empty] | 50
| implement interface for ESO compatibility |  | JRL | 2004-07-31 | no progress | 0
|  |  | JRL | 2004-08-31 | keyword translation code finished, about to test using WFCAM frames | 50
5 | Set up and manage data processing system hardware | 2
5.2 | buy hardware and install | [5 empty] | 80
| purchase and install bulk storage devices |  | PSB, JMI | 2004-07-31 | no progress | 0
|  |  | PSB, JMI | 2004-08-31 | postponed
| purchase and install spare ultrium device |  | PSB, JMI | 2004-07-31 | no progress | 0
|  |  | PSB, JMI | 2004-08-31 | postponed
5.3 | integrating and testing | [5 empty] | 70
| integrate and test bulk storage devices |  | PSB, JMI | 2004-07-31 | no progress | 0
|  |  | PSB, JMI | 2004-08-31 | postponed
| integrate and test spare ultrium device |  | PSB, JMI | 2004-07-31 | no progress | 0
|  |  | PSB, JMI | 2004-08-31 | postponed
5.4 | Manage day-to-day maintenance and upgrades | [5 empty] | 50
| continue maintenance and upgrade programme |  | JMI, PSB | 2004-07-31 | implemented virtual consoles for processing machines | 10
|  |  | JMI, PSB | 2004-08-31 | maintenance and upgrades proceeding to plan | 50
| plan for APM refurbishment and move equipment |  | MJI, PSB | 2004-07-31 | rack mounted more CASU equipment | 10
|  |  | MJI, PSB | 2004-08-31 | some equipment moved, much clearing out and planning achieved, rest of equipment scheduled to be moved late september | 50
6 | Run standard pipeline | 2.5
7 | Development work for summit pipeline | 1
7.1 | Interface test pipelines in ORAC-DR |  | JRL |  | completed |  | 100
7.2a | implement WFCAM pipeline at summit | [5 empty] | 75
| demonstrate catalogue and non-catalogue DQCs |  | JRL | 2004-07-31 | continuing tests using CIRSI data with faked WFCAM headers | 10
|  |  | JRL | 2004-08-31 | still no suitable test data, unlikely to see any before late september | 10
7.3a | documentation for ORAC-DR interface | [5 empty] | 60
| update and deliver documentation as development proceeds |  | JRL | 2004-07-31 | documentation added for commissioning recipes written this month. | 10
|  |  | JRL | 2004-08-31 | no progress this month | 10
7.4a | upgrade and maintain summit pipeline WFCAM | [5 empty] | 20
| upgrade and maintain |  | JRL | 2004-07-31 | commissioning recipes and primitives being updated to deal with readout characteristics (persistance, linearity etc). | 10
|  |  | JRL | 2004-08-31 | continued work on sky subtraction algorithms | 50
8 | Development and testing of standard 2d processing | 4
8.1a | further development of standard pipeline for WFCAM | [5 empty] | 80
| finish implementing new version of imcore to include full param set |  | JRL | 2004-07-31 | no further progress | 0
|  |  | JRL | 2004-08-31 | no further progress | 0
8.2a | liaison with WFCAM development team | [5 empty] | 75
| continue discussion on reset anomaly, crosstalk and linearity |  | JRL | 2004-07-31 | progress on readout problems is being made now due to discussions with ATC staff. Real test data is still vital. | 10
|  |  | JRL | 2004-08-31 | some progress on dark stability using acceptance data. Expecting crosstalk data from JAC in September | 10
| assess engineering test data for above problems and report |  | JRL | 2004-07-31 | no further work on linearity of existing engineering data | 0
|  |  | JRL | 2004-08-31 | no progress | 0
8.2b | liaison with Project Scientist & VISTA development team
| assess detector engineering test data |  | MJI | 2004-07-31 | nothing to report | 10
|  |  | MJI | 2004-08-31 | nothing to report | 50
8.3a | partake in planning WFCAM commissioning observations | [5 empty] | 80
| continue liaising with ATC/JAC |  | STH | 2004-07-31 | nothing to report | 10
|  |  | STH | 2004-08-31 | responded to query from Paul Hirst, continued telecons. discussion with JAC on revised on-sky commissioning plan | 50
8.3b | partake in planning VISTA comissioning observations
| liaise and discuss with VISTA PS |  | STH | 2004-07-31 | nothing to report | 10
|  |  | STH | 2004-08-31 | nothing to report | 50
8.5 | Tuning pipeline during commissioning and after
| optimize and stress-test pipeline using IPHAS data |  | JMI | 2004-07-31 | good progress with IPHAS data shows that splitting by filter works well. have identified problems with using networked catalogues for crowded regions and planned to implement local versions. | 50
|  |  | JMI | 2004-08-31 | continued processing and reprocessing has helped tune and stress test the pipeline. Local catalogue access implemented. | 100
8.6 | documentation for 2D processing software | [5 empty] | 50
| updates docs as necessary and as a result of feedback |  | JRL | 2004-07-31 | no progress | 0
|  |  | JRL | 2004-08-31 | no progress | 0
8.7 | Comparison between automated and manual data products | [5 empty] | 75
| compare FIRES with published results and write report |  | STH | 2004-07-31 | no progress | 0
|  |  | STH | 2004-08-31 | MJI implementing alternative seeing-weighted image stacking algorithm to give better comparison with published FIRES dataset. | 10
| discuss results with CSV |  | STH | 2004-07-31 | no progress | 0
|  |  | STH | 2004-08-31 | nothing to report | 0
9 | Development and testing of standard catalogue products | 4
9.1 | add in new measures requested | [5 empty] | 60
| finish testing and debugging new catalogue parameter measures |  | MJI | 2004-07-31 | no progress | 0
|  |  | MJI | 2004-08-31 | more tests and progress on assorted flux measures and errors. As expected NIR data needs a different specification c.f. to optical | 50
9.2 | refine astrometric calibration model |  | MJI |  | paused |  | 85
9.3 | generate model simulations of expected data |  | STH, JMI |  | paused |  | 80
9.4 | assess catalogue parameter reliability | [5 empty] | 70
| refine parameter error estimates and check for systematics in new params |  | MJI | 2004-07-31 | no progress | 0
|  |  | MJI | 2004-08-31 | some further progress on error estimates and systematics for new parameters | 10
9.5 | intercomparison of catalogue products with other packages |  | JMI |  | paused |  | 60
9.6 | Completeness and error estimates |  |  |  | stopped - subsumed into 9.4
9.7 | documentation of catalogue software and products | [5 empty] | 55
| update catalogue products documentation |  | MJI | 2004-07-31 | updated PODs | 10
|  |  | MJI | 2004-08-31 | more software added to documentation set | 10
10 | Setup trial and run further processing pipeline | 3
10.2 | development and assessment of PSF options 1,2 | [5 empty] | 50
| produce robust version of code for PSF level 1 |  | MJI | 2004-07-31 | awaiting results from 16 | 0
|  |  | MJI | 2004-08-31 | robust versions of PSF generation code developed and good progress on level 1 PSF estimation code | 50
| produce prototype for PSF level 2 |  | MJI | 2004-07-31 | awaiting results from 16 | 0
|  |  | MJI | 2004-08-31 | good progress on level 2 PSF estimation code | 50
10.3 | develop 1D/2D PSF-deconvolved Sersic profile fits
| produce prototype code for sersic profile fits |  | MJI | 2004-07-31 | no progress | 0
|  |  | MJI | 2004-08-31 | no progress this month | 0
11 | Photometric standards and calibration | 3
11.1 | agree on primary standards | [5 empty] | 90
| complete narrow band filter calibration plan and update document |  | STH | 2004-07-31 | no progress | 0
|  |  | STH | 2004-08-31 | no progress | 0
11.2 | choose secondary standard fields | [5 empty] | 80
| finish updates to photom doc and circulate |  | STH | 2004-07-31 | no progress | 0
|  |  | STH | 2004-08-31 | no progress | 0
11.7 | assess extinction monitoring methods and develop measures | [5 empty] | 50
| complete investigation of UKIRT archive and write report |  | STH | 2004-07-31 | no progress | 0
|  |  | STH | 2004-08-31
| simulate from night(s) data and estimate expected accuracy |  | STH | 2004-07-31 | no progress | 0
|  |  | STH | 2004-08-31 | no progress | 0
12 | Further development of DQC measures at summit and Cambr | 2
12.1 | develop extra systematic noise measures | [5 empty] | 50
| trial software with real & simulated data |  | MJI | 2004-07-31 | using INT WFC data to test measures | 10
|  |  | MJI | 2004-08-31 | no progress this month | 10
12.2 | Refine current measures for WFCAM/VISTA data |  | JRL |  | paused pending appropriate data |  | 20
12.3 | implement 2mass for throughput measurement |  | JMI |  | paused |  | 75
12.4 | master calibration frames for detector monitoring | [5 empty] | 35
| assess and report on lab testing of detectors |  | JRL | 2004-07-31 | no data = no progress | 0
|  |  | JRL | 2004-08-31 | some progress on dark stability using acceptance data | 10
13 | Co-located list driven photometry | 3
13.2 | develop basic WCS-based list driven photometer | [5 empty] | 90
| investigate practicalities and implement agreed ICD for parameters |  | MJI | 2004-07-31 | no progress | 0
|  |  | MJI | 2004-08-31 | completed to level of earlier 32 parameter catalogue set, paused waiting for final version of 9.1 | 50
13.3 | externally driven WCS photometry and define parameter set | [5 empty] | 75
| refine, test and debug list-driven parameter estimator - finish |  | MJI | 2004-07-31 | no progress | 0
|  |  | MJI | 2004-08-31 | completed to level of earlier 32 parameter catalogue set, paused waiting for final version of 9.1 | 50
14 | Stacking and mosaicing | 4
14.1 | develop benchmark simple stacking/mosaicing framework |  | MJI |  | complete |  | 100
14.2 | NN algorithm with simple rejection |  | MJI |  | complete |  | 100
14.3 | More sophisticated rejection dealing with pixellation |  | MJI |  | complete |  | 100
14.4 | Stacking with optimum wighting and defect rejection | [5 empty] | 25
| refine current weighting method, test and report on alternative schemes |  | MJI | 2004-07-31 | no progress | 0
|  |  | MJI | 2004-08-31 | trialling seeing-weighted scheme for optimum point source detection and parameterisation | 50
15 | Continuum subtraction and basic difference imaging | 4
15.1 | Simple WCS-based subtraction techniques |  | MJI |  | completed |  | 100
15.2 | investigate and apply different interpolation methods |  | MJI |  | completed |  | 100
15.3 | develop adaptive kernel matching option | [5 empty] | 80
| continue debugging and enhancements to adaptive kernel package |  | MJI | 2004-07-31 | no more bugs this month | 10
|  |  | MJI | 2004-08-31 | on track, no new bugs found, now trialling on 15.4 | 50
15.4 | transit event detection | [5 empty] | 0
| assess difference imaging method (continuum subtraction) |  | STH | 2004-07-31 | no progress | 0
|  |  | STH | 2004-08-31 | MJI investigating undersampled time series data for variability/transit event detection | 10
16 | Interpolation techniques and PSF modeling | 4
16.1 | investigate alternative interpolation/PSF schemes | [5 empty] | 100
| investigate PSF fitting algorithms and write report - finish |  | DWE | 2004-07-31 | report released | 100
http://www.ast.cam.ac.uk/~wfcam/docs/reports/psf/
16.2 | implications for different stacking methods | [5 empty] | 20
| quantify effects of interpolation on stacked image quality |  | MJI | 2004-07-31 | doing tests in conjunction with 14.4 | 10
|  |  | MJI | 2004-08-31 | tried various schemes and found have little impact for well sampled images | 50
16.3 | implications for deriving catalogues and parameters | [5 empty] | 70
| test PSF photom and astrom using optical data and include in report (16.1) |  | DWE | 2004-07-31 | no progress | 0
|  |  | DWE | 2004-08-31 | update of astrometry being added to PSF fitting code | 10
16.4 | oversampled PSF generation per detector | [5 empty] | 50
| investigate modelling emprical PSF and add to report |  | DWE | 2004-07-31 | elliptical moffat profile fitting as part of PSF generator tested | 50
|  |  | DWE | 2004-08-31 | elliptical moffat profile fitting added to PSF fitting and formulation added to report | 100
16.5 | develop oversampled spatially varying PSF model | [5 empty] | 0
| measure spatial variation in optical/IR datasets |  | DWE | 2004-07-31 | no progress | 0
|  |  | DWE | 2004-08-31 | no progress
| design empirical model describing same |  | DWE | 2004-07-31 | no progress | 0
|  |  | DWE | 2004-08-31 | MJI devised elegant scheme based on adaptive kernal matching to incoporate spatial variation in PSF, if needed. | 10