## WPs
WP # | WP Title | Responsibility | 2003 |  |  |  | 2004 |  |  |  | 2005 |  |  |  | 2006 |  |  |  | 2007 |  |  |  | 2008 |  |  |  | 2003 FTEs | 2004 FTEs | 2005 FTEs | dwe 2003 | dwe 2004 | jrl 2003 | jrl 2004 | mji 2003 | mji 2004 | rwa 2003 | rwa 2004 | sth 2003 | sth 2004 | mtb 2003 | mtb 2004 | psb 2003 | psb 2004 | mr new 2003 | mr new 2004 | 2006 FTEs | 2007 FTEs | VISTA index | 2003 | 2004 | 2005 | 2006 | 2007
|  |  | v1 | v1 | v1 | v1 | v2 | v2 | v2 | v2 | v3 | v3 | v3 | v3 | v3 | v3 | v3 | v3 | v3 | v3 | v3 | v3 | v3 | v3 | v3 | v3
|  |  | JFM | AMJ | JAS | OND | JFM | AMJ | JAS | OND | JFM | AMJ | JAS | OND | JFM | AMJ | JAS | OND | JFM | AMJ | JAS | OND | JFM | AMJ | JAS | OND | [21 empty] | 0-4
1 | Management and Definition of Responsibilities | MJI | [24 empty] | 0.5 | 0.5 | 0.5 | 0.1 | 0.1 | 0.1 |  | 0.1 | 0.1 |  |  | 0.1 | [7 empty] | 0.5 | 0.5 | 3 | 0 | 0 | 0 | 0 | 0
1.1 | Report to VISTA Board, GSC | MJI | bar: JFM to OND
1.2 | Interface Control Document between CASU and JAC | MJI | bar: JFM to OND
1.3 | Interface Control Document between CASU and WFAU | MJI | bar: JFM to JAS
1.4a | Define WFCAM data structures and FITS headers | JRL | bar: JFM to JAS
1.4b | Define VISTA data structures and FITS headers | JRL | bar: OND to AMJ
1.5a | Define WFCAM observing protocols + MSB structure | STH | bar: JFM to JAS
1.5b | Define VISTA observing protocols | STH | bar: JAS to AMJ
1.6a | Liaise with UKIDSS & JAC on observing strategy | DWE | bar: JFM to AMJ
1.6b | Liaise with VDUC + ESO on observing strategy | DWE | bar: JFM to AMJ
1.7a | Liaise with UKIDSS & JAC on survey planning | DWE | bar: JFM to AMJ
1.7b | Liaise with VDUC + ESO on survey planning | DWE | bar: JFM to JAS
1.8a | Liaise with UKIDSS & JAC on survey progress database | JRL | bar: JFM to AMJ
1.8b | Liaise with VDUC + ESO on survey progress database | JRL | bar: JFM to JAS
1.9a | WFCAM System Documentation | STH | bar: JFM to JFM
1.9b | VDFS System Documentation | STH | bar: AMJ to OND
2 | ESO VISTA software deliverables and documentation | PSB | [24 empty] | 0.5 | 0.5 | 0.5 | [12 empty] | 0.5 | 0.5 |  |  | 0.5 | 0.25 | 4 | 0 | 0 | 0 | 0 | 0
2.1 | DFS user requirements document | PSB | bar: JFM to JAS
2.2 | Data reduction specification | PSB | bar: JFM to JAS
2.3 | Calibration plan document for ESO | PSB | bar: JFM to JAS
2.4 | Specification of calibration procedures for ESO | PSB | bar: OND to JAS
2.5 | Interface control document ESO/VPO | PSB | bar: JFM to OND
2.6 | Instrument specification and interface documents | PSB | bar: JFM to AMJ
2.7 | Delivery software modules summit | PSB | bar: JFM to JAS
2.8 | Delivery software modules Garching | PSB | bar: JFM to JFM
2.9 | Liase with VISTA IR camera development team | PSB | bar: JFM to AMJ
2.10 | Development of DQC measures | PSB | bar: JFM to OND; JAS to OND
2.11 | Documents for software modules | bar: JFM to AMJ
3 | Pipeline Infrastructure and Progress Monitoring Tools | JRL | [24 empty] | 0.4 | 0.3 | 0.2 |  |  | 0.2 | 0.1 |  |  |  |  | 0.2 | 0.1 |  |  |  |  | 0.1 | 0.1 | 0.2 | 0.2 | 3.5 | 0 | 0 | 0 | 0 | 0
3.1 | Interactive tools for running pipeline | JRL | bar: JAS to AMJ
3.2 | High level scripts to interrogate headers | STH | bar: JFM to AMJ; JFM to AMJ
3.3 | Develop automatic progression of results to WWW pages | STH | bar: OND to JAS
3.4 | Automate checks to spot failures of pipeline | STH | bar: OND to JAS
3.5a | Tools for fixing problem datasets | JRL | bar: JFM to OND
3.5b | Tools for fixing VISTA problem datasets | JRL | bar: AMJ to JAS
3.6 | Group Documentation for above | JRL | bar: JFM to OND
3.7a | Oversee reprocessing WFCAM data after bug fixes/improvements | RWA | bar: JFM to OND
3.7b | Oversee reprocessing VISTA data after bug fixes/improvements | RWA | bar: AMJ to OND
4 | Set up and Manage Raw Science Archive and Database | RWA | [24 empty] | 0.1 | 0.15 | 0.2 |  |  | 0.1 | 0.1 |  |  |  | 0.1 | [8 empty] | 0.2 | 0.2 | 0 | 0 | 0 | 0.2 | 0.2 | 0.2
4.1 | Extend current UKIRT archive to cope with WFCAM + VISTA | JRL | bar: OND to JAS
4.2a | Ingest and verify WFCAM data | RWA | bar: JAS to OND
4.2b | Ingest and verify VISTA data | RWA | bar: JAS to OND
5 | Set up and Manage Data Processing System Hardware | MTB | [24 empty] | 0.2 | 0.2 | 0.2 | [10 empty] | 0.2 | 0.2 |  |  |  |  | 0.2 | 0.2 | 2 | 0 | 0.1 | 0.2 | 0.2 | 0.2
5.1 | Investigate alternatives (benchmarking, reliability etc) | MTB | bar: JFM to JAS
5.2 | Buy hardware and install software | MTB | bar: JAS to OND
5.3 | Integration and testing | MTB | bar: OND to AMJ
5.4 | Manage day-to-day, maintenance and upgrades | MTB | bar: JFM to OND
5.5 | Hardware additions for further data processing system | MTB | bar: JAS to OND
6 | Run Standard Pipelines | RWA | [24 empty] | 0 | 0.75 | 1 |  | 0.1 |  | 0.1 |  |  |  | 0.6 |  | 0.1 | [5 empty] | 0.1 | 1.5 | 2 | 2.5 | 0 | 0.75 | 1 | 1.5 | 2
6.1a | Update WFCAM master calibration frames | JRL | bar: JAS to OND
6.1b | Update VISTA master calibration frames | JRL | bar: JAS to OND
6.2a | Monitor detector performance WFCAM | JRL | bar: JFM to OND
6.2b | Monitor detector performance VISTA | JRL | bar: JAS to OND
6.3a | Oversee standard processing WFCAM | RWA | bar: JAS to OND
6.3b | Oversee standard processing VISTA | RWA | bar: JAS to OND
6.4a | Astrometric calibration WFCAM | DWE | bar: JFM to OND
6.4b | Astrometric calibration VISTA | DWE | bar: JAS to OND
6.5a | Photometric calibration WFCAM | STH | bar: JFM to OND
6.5b | Photometric calibration VISTA | STH | bar: JAS to OND
6.6a | Verify science products and monitor DQC measures WFCAM | RWA | bar: JAS to OND
6.6b | Verify science products and monitor DQC measures VISTA | RWA | bar: JAS to OND
6.7 | Monitor product data transfer to WFAU | JRL | bar: JAS to OND
6.8a | Reprocess WFCAM data | bar: JFM to OND
6.8b | Reprocess VISTA data | bar: JFM to OND
7 | Development Work for Summit Pipelines | JRL | [24 empty] | 0.2 | 0.1 | 0.1 |  |  | 0.2 | 0.1 | [12 empty] | 0.1 | 0.1 | 1 | 0 | 0 | 0 | 0 | 0
7.1a | Interface test pipelines to ORAC-DR | JRL | bar: JFM to AMJ
7.1b | Interface test pipelines to VISTA summit DR | JRL | bar: JFM to AMJ
7.2a | Implement WFCAM pipeline at summit | JRL | bar: JAS to AMJ
7.2b | Implement VISTA pipeline at summit | JRL | bar: JAS to OND
7.3a | Documentation of interface WFCAM | JRL | bar: JFM to AMJ
7.3b | Documentation of interface VISTA | JRL | bar: JAS to JAS
7.4a | Upgrade and maintain summit pipeline WFCAM | JRL | bar: JAS to OND
7.4b | Upgrade and maintain summit pipeline VISTA | JRL | bar: JAS to OND
8 | Development and Testing of Standard 2D Processing | STH | [24 empty] | 0.5 | 0.2 | 0.2 |  |  | 0.2 | 0.1 | 0.1 | 0.1 |  |  | 0.1 | [5 empty] | 0.1 |  | 0.2 | 0.1 | 4 | 0 | 0 | 0 | 0 | 0
8.1a | Further development of WFCAM standard pipeline | JRL | bar: JFM to AMJ
8.1b | Development of VISTA specific packages | JRL | bar: AMJ to AMJ
8.2a | Liaison with WFCAM development team | JRL | bar: JFM to AMJ
8.2b | Liaison with VISTA camera development team | JRL | bar: AMJ to JFM
8.3a | Partake in planning commissioning observations WFCAM | STH | bar: AMJ to JAS
8.3b | Partake in planning commissioning observations VISTA | STH | bar: JAS to JFM
8.4a | Participate directly in commissioning WFCAM | STH | bar: AMJ to JAS
8.4b | Participate directly in commissioning VISTA | STH | bar: JFM to OND
8.5a | Tuning pipeline during commissioning and after WFCAM | JRL | bar: AMJ to JFM
8.5b | Tuning pipeline during commissioning and after VISTA | JRL | bar: JAS to AMJ
8.6a | Documentation of 2D processing software | JRL | bar: JFM to AMJ
8.6b | Documentation of additions to 2D processing | JRL | bar: JAS to AMJ
8.7 | Comparison between automated and manual data products | STH | bar: AMJ to AMJ
9 | Development and Testing of Standard Catalogue Products | DWE | [24 empty] | 0.5 | 0.2 | 0.1 | 0.1 |  | 0.1 |  | 0.1 | 0.1 |  |  | 0.2 | 0.1 | [6 empty] | 0.1 | 0.1 | 4 | 0 | 0 | 0 | 0 | 0
9.1 | Add in new measures requested | MJI | bar: AMJ to JFM; JAS to OND
9.2a | Refine astrometric calibration model | MJI | bar: JAS to OND
9.2b | Refine astrometric calibration model - VISTA specific | MJI | bar: JAS to AMJ
9.3 | Generate model simulations of expected data (WFCAM) | STH | bar: AMJ to OND
9.4 | Assess catalogue parameter reliability | DWE | bar: AMJ to JAS
9.5 | Intercomparison of catalogue products with other packages | STH | bar: JFM to OND
9.6 | Completeness and error estimates | MJI | bar: JAS to OND
9.7 | Documentation of catalogue software and products | MJI | bar: JFM to OND
10 | Set up, Trial, and Run Further Processing Software | MJI | [24 empty] | 0.1 | 0.4 | 1 |  |  |  | 0.1 | 0.1 | 0.1 |  |  |  | 0.1 | [5 empty] | 0.2 | 0.7 | 0.5 | 3 | 0 | 0 | 0.5 | 0.5 | 0.5
10.1 | Manage and run further processing stages | MJI | bar: JFM to OND
10.2 | Development and assessment of PSF options 1,2 | MJI | bar: JAS to OND
10.3 | Develop 1D/2D PSF-deconvolved Sersic profile fits | MJI | bar: JFM to AMJ
10.4 | Develop LSBG/nebulosity detection/parameterisation | MJI | bar: JFM to OND
10.5 | Full iterative profile fitting for stellar images | TBD | bar: JFM to AMJ
10.6 | Develop and optimise Bayesian image classification | TBD | bar: JFM to OND
10.7 | Modelling and simulations of further processing steps | STH | bar: AMJ to JFM
11 | Photometric Standards and Calibration | STH | [24 empty] | 0.2 | 0.3 | 0.2 |  | 0.1 | [6 empty] | 0.2 | 0.2 | [6 empty] | 0.2 | 0.2 | 3 | 0 | 0 | 0 | 0 | 0
11.1 | Agree on primary standards (WFCAM + VISTA) | STH | bar: JFM to JAS
11.2 | Choose secondary standard fields (WFCAM + VISTA) | STH | bar: JFM to JAS
11.3a | Take part in commissioning observations WFCAM | STH | bar: JAS
11.3b | Take part in commissioning observations VISTA | STH | bar: JAS to OND
11.4a | Reduce data, compute zero points and colour equations WFCAM | STH | bar: JAS to OND
11.4b | Reduce data, compute zero points and colour equations VISTA | STH | bar: JAS to JFM
11.5 | Update, maintain and extend secondary standards system | STH | bar: OND to AMJ
11.6 | Investigate photometric calibration field systematics WFCAM+VISTA | STH | bar: JAS to JFM; JAS to JFM
11.7 | Assess extinction monitoring methods and develop measures WFCAM + VISTA | DWE | bar: AMJ to AMJ; JAS to JFM
12 | Further Development of DQC Measures at Summit and Cam | JRL | [24 empty] | 0.2 | 0.2 | 0.1 |  |  | 0.1 | 0.1 | 0.1 | 0.1 | [10 empty] | 0.1 | 0.1 | 2 | 0 | 0 | 0 | 0 | 0
12.1 | Develop extra systematic noise measures | MJI | bar: JAS to AMJ
12.2 | Refine current measures for WFCAM/VISTA data | JRL | bar: AMJ to JFM
12.3 | Implement 2MASS - cf. for throughput measures | MJI | bar: JFM to AMJ; JAS to OND
12.4 | Master calibration frames for detector monitoring | JRL | bar: JFM to JAS
13 | Co-Located List Driven Photometry | MJI | [24 empty] | 0.2 | 0.2 | 0 |  |  |  |  | 0.1 | 0.1 |  |  |  | 0.1 |  |  |  |  | 0.1 |  | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0
13.1 | Test methods for master catalogue generation | MJI | bar: JFM to AMJ
13.2 | Develop basic WCS-based list driven photometer | MJI | bar: JFM to OND
13.3 | Externally driven WCS photometry and define parameter set | MJI | bar: JFM to OND
14 | Stacking and Mosaicing | MJI | [24 empty] | 0.2 | 0.3 | 0.5 |  |  |  | 0.1 | 0.1 | 0.1 | [8 empty] | 0.1 | 0.1 | 0.3 | 0.2 | 4 | 0 | 0 | 0 | 0 | 0
14.1 | Develop benchmark simple stacking/mosaicing framework | MJI | bar: JFM to AMJ
14.2 | Nearest neighbour algorithm with simple rejection | MJI | bar: AMJ to JAS
14.3 | More sophisticated rejection dealing with pixellation | MJI | bar: OND to JAS
14.4 | Stacking with optimum weighting and defect rejection | MJI | bar: JFM to AMJ
14.5 | Advanced stacking/image restoration for variable PSF | TBD | bar: JFM to JAS
15 | Continuum Subtraction and Difference Imaging | STH | [24 empty] | 0.1 | 0.2 | 0.2 |  | 0.1 |  |  | 0.1 | [11 empty] | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0
15.1 | Simple WCS-based subtraction techniques | MJI | bar: AMJ to JAS; AMJ
15.2 | Investigate and apply different interpolation methods | DWE | bar: JFM to JAS; AMJ
15.3 | Develop adaptive kernel matching option | TBD | bar: JFM to OND
15.4 | Transient event detection | STH | bar: JAS to OND
16 | Interpolation Techniques and PSF Modelling | DWE | [24 empty] | 0.4 | 0.2 | 0.1 | 0.4 | 0.2 | [14 empty] | 0.1 | 0.1 | 4 | 0 | 0 | 0 | 0 | 0
16.1 | Investigate alternative interpolation/PSF schemes | DWE | bar: JFM to AMJ
16.2 | Implications for different stacking methods | DWE | bar: JAS to AMJ
16.3 | Implications for deriving catalogues and parameters | DWE | bar: JFM to OND
16.4 | Oversampled PSF generation per detector | DWE | bar: JAS to AMJ; OND to JFM
16.5 | Develop oversampled spatially varying PSF model | DWE | bar: JFM to JFM; OND to JFM
17 | Astrogridding VDFS | [25 empty] | 0 | 0.25 | 0.2 | [16 empty] | 0.15 | 0.1 |  | 0 | 0 | 0 | 0 | 0
17.1 | Implement remote operation of pipeline | bar: JAS to JFM
17.2 | Export pipeline status in VO format | bar: JAS to JAS
17.3 | Export pipeline DQC in VO format | bar: JAS to AMJ
17.4 | Enable remote configuration of pipeline | bar: JFM to OND
[27 empty] | 4.3 | 4.95 | 5.3 | 0.6 | 0.6 | 1 | 0.8 | 0.8 | 0.7 | 0 | 0.7 | 0.8 | 0.7 | 0.2 | 0.2 | 0.5 | 0.5 | 0.4 | 0.5 | 5.05 | 4.85 | 47 | 0 | 0.85 | 1.9 | 2.4 | 2.9

## sth_staff_effort
WP# | WP Title | 2003 |  |  |  | 2004 |  |  |  | 2005 |  |  |  | 2006 |  |  |  | 2007 |  |  |  | Operations |  |  |  |  | Development |  |  |  |  | tot0304 | check | av03 | av04q1 | av04q2 | av04q3 | av04q4
|  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | 03 | 04 | 05 | 06 | 07 | 03 | 04 | 05 | 06 | 07
1 | Management | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 1 | 0.5 | 0.625 | 0.75 | 0.875 | 1
2 | ESO deliverables | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0.25 | 1 | 1 | 0.5 | 0.625 | 0.75 | 0.875 | 1
3 | Pipeline Infrastructure and Tools | 0.4 | 0.4 | 0.4 | 0.4 | 0.3 | 0.3 | 0.3 | 0.3 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0.4 | 0.3 | 0.2 | 0.2 | 0.2 | 0.7 | 0.7 | 0.4 | 0.475 | 0.55 | 0.625 | 0.7
4 | Raw Data Archive and Database | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0 | 0 | 0.2 | 0.2 | 0.2 | 0.1 | 0.15 | 0 | 0 | 0 | 0.25 | 0.25 | 0.1 | 0.125 | 0.15 | 0.2 | 0.25
5 | Data Processing System Hardware | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0 | 0.1 | 0.2 | 0.2 | 0.2 | 0.2 | 0.1 | 0 | 0 | 0 | 0.4 | 0.4 | 0.2 | 0.25 | 0.3 | 0.35 | 0.4
6 | Run Standard Pipelines | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0.75 | 1 | 1.5 | 2 | 0 | 0 | 0 | 0 | 0 | 0.75 | 0.75 | 0 | 0.125 | 0.25 | 0.5 | 0.75
7 | DevTest: VDFS Summit Pipelines | 0.2 | 0.2 | 0.2 | 0.2 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0.2 | 0.1 | 0.1 | 0.1 | 0.1 | 0.3 | 0.3 | 0.2 | 0.225 | 0.25 | 0.275 | 0.3
8 | DevTest: Standard 2D Processing | 0.5 | 0.5 | 0.5 | 0.5 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.1 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.2 | 0.2 | 0.2 | 0.1 | 0.7 | 0.7 | 0.5 | 0.55 | 0.6 | 0.65 | 0.7
9 | DevTest: Standard Catalogue Prod | 0.5 | 0.5 | 0.5 | 0.5 | 0.2 | 0.2 | 0.2 | 0.2 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.2 | 0.1 | 0.1 | 0.1 | 0.7 | 0.7 | 0.5 | 0.55 | 0.6 | 0.65 | 0.7
10 | DevRun: Further Processing Soft | 0.1 | 0.1 | 0.1 | 0.1 | 0.4 | 0.4 | 0.4 | 0.4 | 1 | 1 | 1 | 1 | 0.7 | 0.7 | 0.7 | 0.7 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0.1 | 0.4 | 0.5 | 0.2 | 0 | 0.5 | 0.5 | 0.1 | 0.2 | 0.3 | 0.4 | 0.5
11 | Phot Standards and Calibration | 0.2 | 0.2 | 0.2 | 0.2 | 0.3 | 0.3 | 0.3 | 0.3 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0.2 | 0.3 | 0.2 | 0.2 | 0.2 | 0.5 | 0.5 | 0.2 | 0.275 | 0.35 | 0.425 | 0.5
12 | DQC Measures at Summit and Cam | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0.2 | 0.2 | 0.1 | 0.1 | 0.1 | 0.4 | 0.4 | 0.2 | 0.25 | 0.3 | 0.35 | 0.4
13 | Co-Located List Driven Photom | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2 | 0.2 | 0 | 0 | 0 | 0.4 | 0.4 | 0.2 | 0.25 | 0.3 | 0.35 | 0.4
14 | Stacking and Mosaicing | 0.2 | 0.2 | 0.2 | 0.2 | 0.3 | 0.3 | 0.3 | 0.3 | 0.5 | 0.5 | 0.5 | 0.5 | 0.3 | 0.3 | 0.3 | 0.3 | 0.2 | 0.2 | 0.2 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0.2 | 0.3 | 0.5 | 0.3 | 0.2 | 0.5 | 0.5 | 0.2 | 0.275 | 0.35 | 0.425 | 0.5
15 | Difference Imaging | 0.1 | 0.1 | 0.1 | 0.1 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0.2 | 0.2 | 0 | 0 | 0.3 | 0.3 | 0.1 | 0.15 | 0.2 | 0.25 | 0.3
16 | Interpolation Techs + PSF Models | 0.4 | 0.4 | 0.4 | 0.4 | 0.2 | 0.2 | 0.2 | 0.2 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0.4 | 0.2 | 0.1 | 0.1 | 0.1 | 0.6 | 0.6 | 0.4 | 0.45 | 0.5 | 0.55 | 0.6
17 | Astrogridding VDFS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Development | 4.3 | 4.3 | 4.3 | 4.3 | 3.85 | 3.85 | 3.85 | 3.85 | 3.2 | 3.2 | 3.2 | 3.2 | 2.5 | 2.5 | 2.5 | 2.5 | 1.85 | 1.85 | 1.85 | 1.85 | [10 empty] | 8.15
| Operations | 0 | 0 | 0 | 0 | 0.85 | 0.85 | 0.85 | 0.85 | 1.9 | 1.9 | 1.9 | 1.9 | 2.4 | 2.4 | 2.4 | 2.4 | 2.9 | 2.9 | 2.9 | 2.9 | [10 empty] | 0.85
| Total | 4.3 | 4.3 | 4.3 | 4.3 | 4.4 | 4.4 | 5 | 5 | 5.1 | 5.1 | 5.1 | 5.1 | 4.4 | 4.4 | 5.4 | 5.4 | 5 | 5 | 4.5 | 4.5 | 0 | 0.85 | 1.9 | 2.4 | 2.9 | 4.3 | 3.85 | 3.2 | 2.5 | 1.85 | 9 | 9 | 4.3 | 5.4 | 6.5 | 7.75 | 9
secretarial @ 0.08
computing @ 0.1
consumables
management
uss + ni + overhead

## sth_staff_effort_actual
WP# | WP Title | 2003 |  |  |  | 2004 |  |  |  | 2005 |  |  |  | 2006 |  |  |  | 2007 |  |  |  | Operations |  |  |  |  | Development |  |  |  |  | tot0404 | check | av03 | av04q1 | av04q2 | av04q3 | av04q4
|  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | 03 | 04 | 05 | 06 | 07 | 03 | 04 | 05 | 06 | 07
1 | Management | 0.3 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0.45 | 0.5 | 0.5 | 0.5 | 0.5 | 0.95 | 0.95 | 0.45 | 0.575 | 0.7 | 0.825 | 0.95
2 | ESO deliverables | 0.2 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.425 | 0.5 | 0.5 | 0.5 | 0.25 | 0.925 | 0.925 | 0.425 | 0.55 | 0.675 | 0.8 | 0.925
3 | Pipeline Infrastructure and Tools | 0.4 | 0.4 | 0.4 | 0.4 | 0.3 | 0.3 | 0.3 | 0.3 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0.4 | 0.3 | 0.2 | 0.2 | 0.2 | 0.7 | 0.7 | 0.4 | 0.475 | 0.55 | 0.625 | 0.7
4 | Raw Data Archive and Database | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0.1 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0 | 0 | 0.2 | 0.2 | 0.2 | 0.1 | 0.05 | 0 | 0 | 0 | 0.15 | 0.15 | 0.1 | 0.125 | 0.125 | 0.125 | 0.15
5 | Data Processing System Hardware | 0 | 0.1 | 0.1 | 0.1 | 0.1 | 0.2 | 0.3 | 0.1 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0 | 0.0875 | 0.2 | 0.2 | 0.2 | 0.075 | 0.0875 | 0 | 0 | 0 | 0.25 | 0.25 | 0.075 | 0.1 | 0.15 | 0.225 | 0.25
6 | Run Standard Pipelines | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0.125 | 1 | 1.5 | 2 | 0 | 0 | 0 | 0 | 0 | 0.125 | 0.125 | 0 | 0 | 0 | 0.125 | 0.125
7 | DevTest: VDFS Summit Pipelines | 0.2 | 0.2 | 0.2 | 0.2 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0.2 | 0.1 | 0.1 | 0.1 | 0.1 | 0.3 | 0.3 | 0.2 | 0.225 | 0.25 | 0.275 | 0.3
8 | DevTest: Standard 2D Processing | 0.3 | 0.5 | 0.5 | 0.4 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.1 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0.425 | 0.2 | 0.2 | 0.2 | 0.1 | 0.625 | 0.625 | 0.425 | 0.475 | 0.525 | 0.575 | 0.625
9 | DevTest: Standard Catalogue Prod | 0.3 | 0.5 | 0.5 | 0.5 | 0.2 | 0.2 | 0.2 | 0.2 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0.45 | 0.2 | 0.1 | 0.1 | 0.1 | 0.65 | 0.65 | 0.45 | 0.5 | 0.55 | 0.6 | 0.65
10 | DevRun: Further Processing Soft | 0 | 0.1 | 0.1 | 0.1 | 0.4 | 0.4 | 0.4 | 0.4 | 1 | 1 | 1 | 1 | 0.7 | 0.7 | 0.7 | 0.7 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0.075 | 0.4 | 0.5 | 0.2 | 0 | 0.475 | 0.475 | 0.075 | 0.175 | 0.275 | 0.375 | 0.475
11 | Phot Standards and Calibration | 0 | 0.2 | 0.2 | 0.2 | 0.1 | 0.1 | 0.1 | 0.1 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0.15 | 0.1 | 0.2 | 0.2 | 0.2 | 0.25 | 0.25 | 0.15 | 0.175 | 0.2 | 0.225 | 0.25
12 | DQC Measures at Summit and Cam | 0.1 | 0.2 | 0.2 | 0.2 | 0.1 | 0.1 | 0.1 | 0.2 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0.175 | 0.125 | 0.1 | 0.1 | 0.1 | 0.3 | 0.3 | 0.175 | 0.2 | 0.225 | 0.25 | 0.3
13 | Co-Located List Driven Photom | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2 | 0.2 | 0 | 0 | 0 | 0.4 | 0.4 | 0.2 | 0.25 | 0.3 | 0.35 | 0.4
14 | Stacking and Mosaicing | 0.1 | 0.2 | 0.5 | 0.5 | 0.5 | 0.5 | 0.3 | 0.3 | 0.5 | 0.5 | 0.5 | 0.5 | 0.3 | 0.3 | 0.3 | 0.3 | 0.2 | 0.2 | 0.2 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0.325 | 0.4 | 0.5 | 0.3 | 0.2 | 0.725 | 0.725 | 0.325 | 0.45 | 0.575 | 0.65 | 0.725
15 | Difference Imaging | 0 | 0.1 | 0.2 | 0.2 | 0.3 | 0.3 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.125 | 0.25 | 0.2 | 0 | 0 | 0.375 | 0.375 | 0.125 | 0.2 | 0.275 | 0.325 | 0.375
16 | Interpolation Techs + PSF Models | 0 | 0.2 | 0.2 | 0.2 | 0.3 | 0.4 | 0.4 | 0.4 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0.15 | 0.375 | 0.1 | 0.1 | 0.1 | 0.525 | 0.525 | 0.15 | 0.225 | 0.325 | 0.425 | 0.525
17 | Astrogridding VDFS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2 | 0.15 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Development | 3.725 | 3.725 | 3.725 | 3.725 | 3.7875 | 3.7875 | 3.7875 | 3.7875 | 3.4 | 3.4 | 3.4 | 3.4 | 2.65 | 2.65 | 2.65 | 2.65 | 1.95 | 1.95 | 1.95 | 1.95 | [10 empty] | 7.5125 |  |  |  |  | 6.5656
| Operations | 0 | 0 | 0 | 0 | 0.2125 | 0.2125 | 0.2125 | 0.2125 | 1.9 | 1.9 | 1.9 | 1.9 | 2.4 | 2.4 | 2.4 | 2.4 | 2.9 | 2.9 | 2.9 | 2.9 | [10 empty] | 0.2125 |  |  |  |  | 0.15937
| Total | 2.2 | 4 | 4.4 | 4.3 | 3.9 | 4 | 4.3 | 3.8 | 5.3 | 5.3 | 5.3 | 5.3 | 4.6 | 4.6 | 5.5 | 5.5 | 5.1 | 5.1 | 4.6 | 4.6 | 0 | 0.2125 | 1.9 | 2.4 | 2.9 | 3.725 | 3.7875 | 3.4 | 2.65 | 1.95 | 7.725 | 7.725 | 3.725 | 4.7 | 5.7 | 6.775 | 7.725
secretarial @ 0.08
computing @ 0.1
consumables
management
uss + ni + overhead

## summary
WP | WP Title | PV | PV | PV | PV | PV | PV | AV | AV | AV | AV | AV | AV | %com | %com | %com | %com | %com | %com | EV | EV | EV | EV | EV | EV
|  | 02 | 03 | 04q1 | 04q2 | 04q3 | 04q4 | 02 | 03 | 04q1 | 04q2 | 04q3 | 04q4 | 02 | 03 | 04q1 | 04q2 | 04q3 | 04q4 | 02 | 03 | 04q1 | 04q2 | 04q3 | 04q4
1 | Management | 0 | 0.5 | 0.625 | 0.75 | 0.875 | 1 | 0 | 0.45 | 0.575 | 0.7 | 0.825 | 0.95 | 0% | 59% | 69% | 79% |  |  | 0 | 0.59 | 0.69 | 0.79 | 0 | 0
2 | ESO deliverables | 0 | 0.5 | 0.625 | 0.75 | 0.875 | 1 | 0 | 0.425 | 0.55 | 0.675 | 0.8 | 0.925 | 0% | 39% | 51% | 62% |  |  | 0 | 0.39 | 0.51 | 0.62
3 | Pipeline Infrastructure and Tools | 0 | 0.4 | 0.475 | 0.55 | 0.625 | 0.7 | 0 | 0.4 | 0.475 | 0.55 | 0.625 | 0.7 | 0% | 35% | 35% | 38% |  |  | 0 | 0.245 | 0.245 | 0.266
4 | Raw Data Archive and Database | 0 | 0.1 | 0.125 | 0.15 | 0.2 | 0.25 | 0 | 0.1 | 0.125 | 0.125 | 0.125 | 0.15 | 0% | 19% | 19% | 19% |  |  | 0 | 0.0475 | 0.0475 | 0.0475
5 | Data Processing System Hardware | 0 | 0.2 | 0.25 | 0.3 | 0.35 | 0.4 | 0 | 0.075 | 0.1 | 0.15 | 0.225 | 0.25 | 0% | 36% | 43% | 53% |  |  | 0 | 0.144 | 0.172 | 0.212
6 | Run Standard Pipelines | 0 | 0 | 0.125 | 0.25 | 0.5 | 0.75 | 0 | 0 | 0 | 0 | 0.125 | 0.125 | 0% | 0% | 0% | 0% |  |  | 0 | 0 | 0 | 0
7 | DevTest: VDFS Summit Pipelines | 0 | 0.2 | 0.225 | 0.25 | 0.275 | 0.3 | 0 | 0.2 | 0.225 | 0.25 | 0.275 | 0.3 | 0% | 49% | 54% | 57% |  |  | 0 | 0.147 | 0.162 | 0.171
8 | DevTest: Standard 2D Processing | 0 | 0.5 | 0.55 | 0.6 | 0.65 | 0.7 | 0 | 0.425 | 0.475 | 0.525 | 0.575 | 0.625 | 0% | 52% | 58% | 61% |  |  | 0 | 0.364 | 0.406 | 0.427
9 | DevTest: Standard Catalogue Prod | 0 | 0.5 | 0.55 | 0.6 | 0.65 | 0.7 | 0 | 0.45 | 0.5 | 0.55 | 0.6 | 0.65 | 0% | 64% | 64% | 64% |  |  | 0 | 0.448 | 0.448 | 0.448
10 | DevRun: Further Processing Soft | 0 | 0.1 | 0.2 | 0.3 | 0.4 | 0.5 | 0 | 0.075 | 0.175 | 0.275 | 0.375 | 0.475 | 0% | 8% | 11% | 15% |  |  | 0 | 0.04 | 0.055 | 0.075
11 | Phot Standards and Calibration | 0 | 0.2 | 0.275 | 0.35 | 0.425 | 0.5 | 0 | 0.15 | 0.175 | 0.2 | 0.225 | 0.25 | 0% | 47% | 47% | 47% |  |  | 0 | 0.235 | 0.235 | 0.235
12 | DQC Measures at Summit and Cam | 0 | 0.2 | 0.25 | 0.3 | 0.35 | 0.4 | 0 | 0.175 | 0.2 | 0.225 | 0.25 | 0.3 | 0% | 44% | 44% | 44% |  |  | 0 | 0.176 | 0.176 | 0.176
13 | Co-Located List Driven Photom | 0 | 0.2 | 0.25 | 0.3 | 0.35 | 0.4 | 0 | 0.2 | 0.25 | 0.3 | 0.35 | 0.4 | 0% | 82% | 86% | 86% |  |  | 0 | 0.328 | 0.344 | 0.344
14 | Stacking and Mosaicing | 0 | 0.2 | 0.275 | 0.35 | 0.425 | 0.5 | 0 | 0.325 | 0.45 | 0.575 | 0.65 | 0.725 | 0% | 50% | 53% | 68% |  |  | 0 | 0.25 | 0.265 | 0.34
15 | Difference Imaging | 0 | 0.1 | 0.15 | 0.2 | 0.25 | 0.3 | 0 | 0.125 | 0.2 | 0.275 | 0.325 | 0.375 | 0% | 80% | 86% | 86% |  |  | 0 | 0.24 | 0.258 | 0.258
16 | Interpolation Techs + PSF Models | 0 | 0.4 | 0.45 | 0.5 | 0.55 | 0.6 | 0 | 0.15 | 0.225 | 0.325 | 0.425 | 0.525 | 0% | 27% | 43% | 58% |  |  | 0 | 0.162 | 0.258 | 0.348
| Development |  | 0 | [17 empty] | 0 | 0
| Operations |  | 0 | [17 empty] | 0 | 0
| Total | 0 | 4.3 | 5.4 | 6.5 | 7.75 | 9 | 0 | 3.725 | 4.7 | 5.7 | 6.775 | 7.725 | [6 empty] | 0 | 3.8065 | 4.2715 | 4.7575
| Date | 2003-01-01 | 2003-12-31 | 2004-03-31 | 2004-06-30 | 2004-09-30 | 2004-12-31 |  |  |  |  | check= | 1.275
| Planned Value | 0 | 4.3 | 5.4 | 6.5 | 7.75 | 9
| Actual Value | 0 | 3.725 | 4.7 | 5.7 | 6.775 | 7.725
| EV | 0 | 3.8065 | 4.2715 | 4.7575
| Sched Var1 =(EV-PV)/PV | 0 | -0.11477 | -0.20898 | -0.26808
| Sched Var2 =(EV-AV)/AV | 0 | 0.021879 | -0.09117 | -0.16535
| %complete | 0 | 0.42294 | 0.47461 | 0.52861

## Resource
|  | available | 180 | 74.4658 | 105.5342
0 | men available | 0.4 | 18 | 7.4466 | 10.5534
1 | men available | 0 | 0 | 0 | 0
2 | men available | 1.3 | 58.5 | 24.2014 | 34.2986
3 | men available | 0.7 | 31.5 | 13.0315 | 18.4685
4 | men available | 0.5 | 22.5 | 9.3082 | 13.1918
5 | men available | 1 | 45 | 18.6164 | 26.3836
6 | men available | 0 | 0 | 0 | 0 | 0
7 | men available | 0.1 | 4.5 | 1.8616 | 2.6384
| Total mp available man yrs | 4 | 180 | 74.4658 | 105.5342
|  | from | 2002-10-01 | 2002-10-01 | 2002-10-01 | 2003-03-01 | 2003-10-01
|  | to | 2003-10-01 | 2003-10-01 | 2003-03-01 | 2003-10-01 | 2003-10-01
| 45 | works weeks to calendatr year |  | wks | pro rata | pro rata
|  | weeks to Mar 03 to Sep 03 |  | 52.1429 | 21.5714 | 30.5714 | 0
2 | Pipeline infrastructure and database progress monitoring development | [6 empty] | 22.5 | 9.3082 | 13.1918 | 13.2

## details_jpe
WORK | 2003 |  | 2003 |  | 2003 |  | 2003
| Jan-Mar | person | Apr-Jun | person | Jul-Sep |  | Oct-Dec
| Q1 | name | Q2 | name | Q3 | v1 | Q4 | v2 | v3
[6 empty] | FTE |  | FTE | FTE
-o- management and definition of project responsibilities:
report to VISTA, UKIDSS, VPO, JAC, VPB, GSC | 0.025 | Irwin | 0.025 | Irwin |  | 0.05 |  | 0.1 | 0.07
ICD between JAC and CASU | [5 empty] | 0.06
ICD between CASU and WFAU | [5 empty] | 0.06
FITS headers and data definition | [5 empty] | 0.05
define observing protocols | [5 empty] | 0.06
liaise on observing strategy and survey planning | [5 empty] | 0.06 |  | 0.1 | 0.07
liaise with JAC on DB progress monitoring | [5 empty] | 0.06 |  | 0.1 | 0.06
-o- pipeline infrastructure and pipeline progress monitoring tools:
interactive tools for running pipeline | [5 empty] | 0.16 |  | 0.08
develop high level scripts to interrogate headers | [5 empty] | 0.17
progress results to web page interface | [7 empty] | 0.07
automate checks to spot failures of pipeline | [7 empty] | 0.07
tools for fixing problem datasets | [7 empty] | 0.08
group documentation for above | [5 empty] | 0.17
reprocessing after bug fixes, new trials | [8 empty] | 0.2
-o- set up and manage raw science archive:
extend current UKIRT archive to cope with WFCAM | [5 empty] | 0.1 |  | 0.1
ingest and verify WFCAM data | [7 empty] | 0.1 | 0.1
-o- set up and manage data processing system hardware:
further investigate alternatives | [5 empty] | 0.1
buy hardware and install software | [5 empty] | 0.1
manage day-to-day, maintenance and upgrades | [7 empty] | 0.1 | 0.1
hardware additions for further data processing system | [7 empty] | 0.1 | 0.1
-o- run standard pipeline:
ingest and verify data | [7 empty] | 0.12 | 0.12
update master calibration frames | [7 empty] | 0.12 | 0.12
monitor detector performance | [7 empty] | 0.12 | 0.12
oversee standard processing | [7 empty] | 0.12 | 0.12
astrometric calibration | [7 empty] | 0.13 | 0.13
photometric calibration | [7 empty] | 0.13 | 0.13
verify science products and monitor DQC measures | [7 empty] | 0.13 | 0.13
monitor product data transfer to WFAU | [7 empty] | 0.13 | 0.13
-o- development work for summit pipeline:
interface test pipeline to ORAC DR | [5 empty] | 0.06
implement WFCAM pipeline at summit | [5 empty] | 0.07
documentation of interface | [5 empty] | 0.07
upgrade and maintain summit pipeline | [7 empty] | 0.1 | 0.1
-o- development and testing of standard 2d processing
further development of standard pipeline | [5 empty] | 0.06
liaison with WFCAM development team | [5 empty] | 0.07
partake in planning commissioning observations | [5 empty] | 0.07
participate directly in commissioning | [5 empty] | 0.07
tuning pipeline during commissioning and after | [5 empty] | 0.07 |  | 0.2
documentation of software | [5 empty] | 0.06
-o- development and testing of standard catalogue products:
add in new measures requested | [5 empty] | 0.08
refine astrometric calibration model | [5 empty] | 0.08 |  | 0.11
generate model simulations of observations | [5 empty] | 0.08
intercomparison of catalogue products | [5 empty] | 0.08 |  | 0.11
completeness and error estimates | [5 empty] | 0.09 |  | 0.1
documentation of software | [5 empty] | 0.09
-o- settup trial and run further processing pipeline:
manage and run further processing stages | [7 empty] | 0.15 | 0.5
development and assessment of PSF options 1,2 | [5 empty] | 0.1 |  | 0.15
develop 1D/2D PSF-deconvolved Sersic profile fits | [7 empty] | 0.15
develop LSBG/nebulosity detection/parameterisation | [7 empty] | 0.15 | 0.5
full iterative profile fitting for stellar images | [8 empty] | 0.5
develop and optimise Bayesian image classification | [8 empty] | 0.5
-o- photometric standards and calibration:
agree on primary standards | [5 empty] | 0.05
choose secondary standard fields | [5 empty] | 0.05
take part in commissioning observations | [5 empty] | 0.05
reduce data compute zero-points colour equations | [5 empty] | 0.05
update maintain and extend secondary standards system | [7 empty] | 0.1 | 0.1
investigate photometric calibration field systematics | [7 empty] | 0.2
assess extinction monitoring methods | [7 empty] | 0.1
-o- further development of DQC measures at summit and Cambridge:
develop extra systematic noise measures | [5 empty] | 0.05 |  | 0.05
refine current measures for WFCAM data | [5 empty] | 0.05 |  | 0.05
implement 2MASS cf. for throughput measures | [5 empty] | 0.05 |  | 0.05
local calibration frames for detector monitoring | [5 empty] | 0.05 |  | 0.05
-o- co-located list driven photometry:
test methods for master catalogue generation | [5 empty] | 0.15
develop basic WCS based WFCAM list driven photometer | [5 empty] | 0.15
externally driven WCS co-located photometry+params | [7 empty] | 0.2
GRID enable cross-photometry on non-WFCAM 2D datasets | [8 empty] | 0.5
-o- stacking and mosaicing:
develop benchmark simple stacking/mosaicing framework | [5 empty] | 0.1
nearest neighbour algorithm with simple rejection | [5 empty] | 0.1
more sophisticated rejection dealing with pixellation | [7 empty] | 0.25
stacking with optimum weighting and defect rejection | [7 empty] | 0.25
advanced stacking/image restoration for variable PSF | [8 empty] | 0.5
-o- continuum subtraction and basic difference imaging:
simple WCS based subtraction techniques | [5 empty] | 0.05 |  | 0.05
investigate different interpolation methods | [5 empty] | 0.05 |  | 0.05
develop adaptive kernel matching option | [8 empty] | 0.25
transient event detection | [8 empty] | 0.25
-o- interpolation techniques and PSF modelling:
find out what do other groups do | [5 empty] | 0.1
implications for different stacking methods | [5 empty] | 0.1
implications for deriving catalogues and parameters | [5 empty] | 0.1
oversampled PSF generation per detector | [5 empty] | 0.1 |  | 0.1
develop oversampled spatially varying PSF mdel | [7 empty] | 0.1
-o- modelling and simulations:
assessment of image processing cf. with interactive | [5 empty] | 0.1
assessment of image catalogue parameter reliability | [5 empty] | 0.1
modelling and simulations of further processing stages | [7 empty] | 0.2 | 0.1
-----------------------------------------------------------------------------------
WFCAM/VISTA | [5 empty] | 4 |  | 5.02 | 5.5
-----------------------------------------------------------------------------------
ESO specific (VISTA only)
-o- ESO VISTA software interface deliverables and documention: | [5 empty] | 0.5 |  | 0.5 | 0.5
interface control document (ICD) ESO/ATC/CASU
further development of DQC measures
specification of calibration procedures for ESO
calibration plan document for ESO
instrument specification and interface documents
delivery software modules exposure time calculator
liaise with VISTA IR camera development team
DFS user requirements document
[ESO stuff needs its own time framework - its not V1 or V2 or anything
that is WFCAM specific. Note that V1 was originally designed to
coincide with WFCAM science commissioning. When realistically is that ?]
-----------------------------------------------------------------------------------
ESO specific (VISTA only) | [5 empty] | 0.5 |  | 0.5 | 0.5
-----------------------------------------------------------------------------------
I've only detailed V1 and V2 stuff for WFCAM/VISTA and some of these naturally
carry over into V3 activities.
General things still to do:
- define more detailed timelines for all tasks
- set up discussion/information distribution forum on internal web page
- establish points of contact for various issues arising ??
- software distribution, other than JAC and WFAU do we ??
-----------------------------------------------------------------------------------
WFCAM/VISTA
Version 1: Ready for last quarter of 2003 with some continuation
Version 2: Develop during year after survey operations begin and
finalise by notionally end of 2004
Version 3. Rollout sometime (TBD) later though some developments
will be concurrent. V3's noted but not complete yet
just broad brush estimates for now.

## whole_jpe
WP # | WP Title | WP Start event | WP end Event |  |  | WP M'ger | Org'n'n Res'ble | WP Aims | Inputs | Outputs | Tasks | CW | SW | Matl£
[11 empty] | Total resource needed | 0 | 571.5 | 0
| Survey Parameters Definition |  | v1 |  |  |  | SPG/ VISTA
S1 | [Survey Planning Tools - ESO] |  | v1 |  |  |  | TBD
S1.1 |  |  | v1 |  |  |  | VISTA |  |  |  | agree nature with ESO
S1.2 |  |  | v1 | [7 empty] | Liason with IR Camera WP 6.8.4 Observation Software
S1.3 |  |  | v1 |  |  | Beard | TBD |  |  |  | do work
C2 | [Interaction with ESO/JAC]
C2.1 | DQC measures |  | v1 |  |  |  | CASU |  |  |  | Further development of DQC measures at telescope (UKIRT/VISTA) |  | 2.5
|  |  | v1 |  |  |  | CASU |  |  |  | Further development of DQC measures near telescope (JAC/Garching) |  | 1
C2.2 | Calibration Processing at JAC/Garching |  | v1 | [7 empty] | Interaction with ESO |  | 22.5
|  | v1 | v2 | [7 empty] | Interaction with ESO |  | 22.5
ICD | Data Interface to Camera |  | v1 |  |  |  | CASU/ATC /RAL
C2 | Telescope DQC and overseas Calibration pipelines |  | v1 |  |  |  | CASU
C2.1 | DFS User Requirements document |  | v1
C2.2 | Calibration Plan document |  | v1
C2.2.1 |  |  | v1 |  |  |  |  | definition of all N templates available for the instrument,
C2.2.2 |  |  | v1 |  |  |  |  | definition of formats of all raw data frames produced,
C2.2.3 |  |  | v1 |  |  |  |  | definition of data and procedures required for calibration,
C2.2.4 |  |  | v1 |  |  |  |  | definition of observing programs to acquire calibration data,
C2.2.5 |  |  | v1 |  |  |  |  | definition of procedures required for verification of instrument performance.
C2.3 | Template Signatures |  | v1 |  |  |  | Camera
C2.3.1 |  |  | v1 |  |  |  |  | one Template Signature file for each of the N templates defined in the Calibration Plan including detailed descriptions its function and parameters.
C2.4 | Instrument Description and Calibration Database |  | v1 |  |  |  | Camera
C2.4.1 |  |  | v1 |  |  |  |  | one file for each detector or optical component defining its properties,
C2.4.2 |  |  | v1 |  |  |  |  | one file for each physical data set defined in the Calibration Plan
C2.5 | Exposure Time Calculator |  | v1 |  |  |  | Camera
C2.5.1 |  |  | v1 |  |  |  |  | one instrument setup template including the associated dictionary,
C2.5.2 |  |  | v1 |  |  |  |  | one source code file for each component including full documentation,
C2.5.3 |  |  | v1 |  |  |  |  | one source code file of the instrument model with documentation
C2.5.4 |  |  | v1 |  |  |  |  | one file for each instrument setup with a verification procedure.
C2.6 | Data Interface Dictionary |  | v1
C2.6.1 |  |  | v1 |  |  |  |  | one file defining the Data Interface Dictionary for the instrument conforming to the DICB standard.
C2.7 | Data Reduction Specifications |  | v1 |  |  |  | CASU
C2.7.1 |  |  | v1 |  |  |  |  | Data Reduction Specifications document
C2.8 | Data Reduction Procedures |  | v1 |  |  |  | CASU
C2.8.n |  |  | v1 | [7 empty] | for each data reduction procedure 1 to N
C2.8.n.1 |  |  | v1 | [7 empty] | one source code file including documentation,
C2.8.n.2 |  |  | v1 | [7 empty] | one set of test data
C2.8.n.3 |  |  | v1 | [7 empty] | one verification procedure
C2.9 | Test and Calibration Data |  | v1
C2.9.1 |  |  | v1 |  |  |  |  | one full set of raw data frames produced by each of the N templates,
C2.9.2 |  |  | v1 |  |  |  |  | one full data set required to generate each calibration frame defined by the Calibration Plan.
ESO# | Build above into summit and overseas pipelines |  | v1 |  |  |  | ESO/ JAC
ICD | Data Interface to ESO/JAC (defined in 2 above) |  | v1
C3 | UK Pipeline |  | v1 |  |  |  | CASU
C3.1 | Simulated Data (for tests) |  | v1 |  |  |  | CASU
D0 | Management & definition of project responsibilities |  |  |  |  | Irwin
| report to VISTA, UKIDSS, JAC, ATC, WFAP, GSC |  | 0.05 | 0.1 | 0.07
| ICD between JAC and CASU |  | 0.06
| ICD between CASU and WFAU |  | 0.06
| FITS headers and data definition |  | 0.05
| define observing protocols |  | 0.06
| liaise on observing strategy and survey planning |  | 0.06 | 0.1 | 0.07
| liaise with JAC on DB progress monitoring |  | 0.06 | 0.1 | 0.06
D7 | Liason ESO/JAC WFCAM/VISTA WFAU/Other Projects | [5 empty] | all
D7.C.1 | Liason with IR Camera WP 6.8.4 Observation Software (including data header)
C3.2 | Pipeline Infrastructure & pipeline progress monitoring tools | [5 empty] | CASU |  |  |  | Software
| interactive tools for running pipeline |  | 0.16 | 0.08
| develop high level scripts to interrogate headers |  | 0.17
| progress results to web page interface |  |  | 0.07
| automate checks to spot failures of pipeline |  |  | 0.07
| tools for fixing problem datasets |  |  | 0.08
| group documentation for above |  | 0.17
| reprocessing after bug fixes, new trials |  |  |  | 0.2
Hardware
Logging
22.5
C3.3 | set up & manage raw science archive | [5 empty] | CASU
| extend current UKIRT archive to cope with WFCAM |  | 0.1 | 0.1
| ingest and verify WFCAM data |  |  | 0.1 | 0.1
D0.CH | set up and manage data processing system hardware | [5 empty] | CASU
| further investigate alternatives |  | 0.1
| buy hardware and install software |  | 0.1
| manage day-to-day, maintenance and upgrades |  |  | 0.1 | 0.1
| hardware additions for further data processing system |  |  | 0.1 | 0.1
9
4.5
C3.4 | Visualisation tools |  | v1 |  |  |  | CASU
C3.5 | DQC measures at CASU |  | v1 |  |  |  | CASU
|  |  | v1 | [7 empty] | Further development of DQC measures at Cambridge |  | 1
| 2d Processing | [9 empty] | Development and testing of standard 2d processing |  | 22.5
C3.6 | Single chip processing |  | v1 |  |  |  | CASU |  |  |  | Non-linearity correction
|  |  | v1 |  |  |  | CASU |  |  |  | Master calibration frame maintenance
|  |  | v1 |  |  |  | CASU |  |  |  | Bad pixel replacement
|  |  | v1 |  |  |  | CASU |  |  |  | Dark correction
|  |  | v1 |  |  |  | CASU |  |  |  | Fatfield correction
|  |  | v1 |  |  |  | CASU |  |  |  | Confidence map
|  |  | v1 |  |  |  | CASU |  |  |  | Defringe correction
|  |  | v1 |  |  |  | CASU |  |  |  | Sky subtraction
|  |  | v1 |  |  |  | CASU |  |  |  | Reset Anomaly correction
|  |  | v1 |  |  |  | CASU |  |  |  | Image Retention correction
C3.7 | Combinations of dithers/microsteps |  | v1 |  |  |  | CASU
|  |  | v1 |  |  |  | CASU |  |  |  | Interleave
|  |  | v1 |  |  |  | CASU |  |  |  | Rough WCS
|  |  | v1 |  |  |  | CASU |  |  |  | WCS Fit (pass 1)
C3.8 | Combinations of detectors
|  |  | v1 |  |  |  | CASU |  |  |  | Gain correction
|  |  | v1 |  |  |  | CASU |  |  |  | Tiling
|  |  | v1 |  |  |  | CASU |  |  |  | Tile Object Catalogues (pass 1)
|  |  | v1 |  |  |  | CASU |  |  |  | WCS Fit (pass 2)
|  |  | v1 |  |  |  | CASU |  |  |  | Tile Object Catalogues (pass 2)
|  |  | v1 | [7 empty] | Development and testing of standard catalogue products |  | 22.5
|  | v1 | v2 | [7 empty] | Source extraction options on any specified subset or stack of pixel data |  | 18
|  | v1 | v2 | [7 empty] | Simple methods for LSBGs, nebulosity detection and parameterisation |  | 22.5
C3.9 | Astrometric calibration |  | v1 |  |  |  | CASU
|  | v1 | v2 | [7 empty] | Refine and improve astrometric calibrtation scheme |  | 4.5
C3.10 | Photometric calibration |  | v1 |  |  |  | CASU
|  |  | v1 | [7 empty] | Setting up photometric standard calibration fields |  | 9
|  |  | v2 | [7 empty] | Maintain, extend photometric secondary standard calibrators |  | 9
|  |  | v2 | [7 empty] | Assess direct, secondary and other extinction monitoring methods |  | 9
|  |  | v2 | [7 empty] | Investigate photometric calibration field position systermatics |  | 4.5
C3.11 | Integration and Test |  | v1 |  |  |  | CASU
|  |  | v1 | [7 empty] | Tuning and science verification during commissioning and after |  | 22.5
C4 | UK Pipeline Operations Plan |  | v1 |  |  |  | CASU
C4.1 | Production pipeline | v1 | v2 | [7 empty] | Ingestion of data, verification, running standard pipeline |  | 45
ICD | Data Interface to Science Archive (WFAU) |  | v1 |  |  |  | CASU/WFAU
C6.1 | Software deliverable to Science Archive |  | v1 |  |  |  | CASU
C4 | Data Interface to Raw Data Users | v1 | v2 |  |  |  | CASU
|  | v1 | v2 | [7 empty] | Setting up and managing raw science data archive |  | 9
|  | v1 | v2 | [7 empty] | Analysis of archive pixel data at arbitrary positions defined by an input list |  | 18
C5 | Functional Development |  | v1 |  |  |  | CASU
| Algorithm developments |  | v1 |  |  |  | CASU
|  |  | v1 | [7 empty] | Co-located list photometry
|  |  | v1 | [7 empty] | Master catalogue generation, co-located list driven photometry |  | 13.5
|  | v1 | v2 | [7 empty] | Externally driven WCS co-located phtometry |  | 9
|  | v1 | v2 | [7 empty] | Cross photometry on non-WFCAM 2d datasets - GRID enabled processing |  | 22.5
|  |  | v1 | [7 empty] | Parameter estimation
|  |  | v1 | [7 empty] | Modelling and simulations for assessment of parameter reliability |  | 13.5
|  | v1 | v2 | [7 empty] | More modeling and simulations parameter reliability assessment |  | 9
|  |  | v1 |  |  |  | CASU |  |  |  | PSF fitting algorithms
|  |  | v1 | [7 empty] | Development and testing of further processing options 1,2 psf fitting |  | 9
|  | v1 | v2 | [7 empty] | Develop oversampled spatially varying PSF characterisation |  | 9
|  | v1 | v2 | [7 empty] | Further development and assessment of psf fitting options 1,2 |  | 13.5
|  | v1 | v2 | [7 empty] | Develop PSF deconvolved Sersic profile fits for galaxies |  | 13.5
|  |  | v1 |  |  |  | CASU |  |  |  | Resampling algoritms
|  |  | v1 | [7 empty] | Interpolation techniques, implications for different stacking methods |  | 9
|  |  | v1 |  |  |  | CASU |  |  |  | Stacking algorithms
|  |  | v1 | [7 empty] | Further development of benchmark simple stacking algorithm |  | 4.5
|  | v1 | v2 | [7 empty] | Stacking with optimum weigthing and defect rejection |  | 22.5
|  | v1 | v2 | [7 empty] | User-specified options for stacking pixel data |  | 40.5
|  |  | v1 |  |  |  | CASU |  |  |  | Difference algorithms
|  |  | v1 | [7 empty] | Continuum subtraction and basic difference imaging |  | 4.5
|  | v1 | v2 | [7 empty] | Generalised difference imaging (and subsequent source analysis) |  | 18
|  |  | v1 |  |  |  | CASU |  |  |  | Extraction of Variables
|  |  | v1 |  |  |  | CASU |  |  |  | Mosaicing algorithms
|  |  | v1 | [7 empty] | Further development of benchmark simple mosaicing algorithm |  | 4.5
|  | v1 | v2 | [7 empty] | Arbitrary sized, mosaiced images |  | 40.5
Development pipeline
|  | v1 | v2 | [7 empty] | Setting up and trialing of further processing pipeline |  | 13.5
A6 | Archive |  | v1 |  |  |  | WFAU
| Software delivered from Pipeline (CASU) |  | v1 |  |  |  | CASU
| see separate WBS for archive |  | v1
Note | for each WP the general approaqch will be: | [9 empty] | Check Definition and understanding of Requirements, Design including test plan, Check interfaces to other components, Plan, review and Approval, Code & document, Implement test Plan, Release code & documentation, maintain