## 03Q2_casu_deliverables2
WP | CASU WP name /sub task / 04Q3 deliverable | V.I.F. | name | date | end of month report | %sub | % task
#
1 | Management and definition of project responsibilities | 3
1.1 | report to VISTA, UKIDSS, JAC, ATC, GSC | [5 empty] | 87
| provide fornightly meeting minutes, monthly reports on progress + quarterly review reports and planning, attend VDUC meetings, have regular telecons with JAC, attend ESO VDFS FDR |  | STH, MJI
| prepare for and attend grant review |  | STH, MJI
1.2 | interface control document between CASU and JAC |  |  |  | completed |  | 100
1.3 | interface control document between CASU and WFAU |  |  |  | completed |  | 100
| liaise with WFAU for design of VISTA ICD |  | MJI
1.4a | define WFCAM data structures and FITS headers |  |  |  | completed |  | 100
1.4b | update proposed VISTA FITS headers as necessary
1.5a | define WFCAM observing protocols | [5 empty] | 87
| monitor and help update MSB guidelines |  | MJI + STH
| check first pass survey MSBs |  | STH
1.5b | define VISTA observing protocols
| help finish defining science and user requirements |  | MJI + PSB
1.6a | liaise with UKIDSS&JAC on WFCAM obs strategy, surveys planning | [5 empty] | 87
| liaise and monitor progress |  | DWE
1.6b | liaise with Project Scientist on VISTA observing strategy & survey planning
| liaise and monitor progress |  | PSB
1.7a | liaise with VDUC on VDFS products for WFCAM | [5 empty] | 87
| liaise and monitor progress |  | STH + MJI
| prepare report on results from WFCAM comissioning |  | JRL
| involve Simon Dye with commissioning analysis progress |  | JRL
1.7b | liaise with VDUC on VDFS products for VISTA
| liaise and monitor progress |  | MJI + STH
| assess and prioritise work required for extra UK VDFS products |  | MJI + STH
prepare functional specification for UK review (see VDMT A0501-05)
1.8a | liaise with UKIDSS and JAC on survey progress DB |  | JRL |  |  |  | 87
| maintain OMP database mirror to be used with survey progress database, including user interface |  | JRL
1.9 | system documentation | [5 empty] | 87
| update and maintain web pages of system docs |  | DWE
2 | ESO VISTA software interface deliverables and documentation | 4
2.1 | VDFS user requirements document | [5 empty] | 70
| respond to RIXs, update documents as appropriate |  | PSB
2.2 | data reduction specification document | [5 empty] | 70
| respond to RIXs, update documents as appropriate |  | PSB
2.3 | calibration plan document | [5 empty] | 70
| respond to RIXs, update documents as appropriate |  | PSB
2.4 | Specification of calibration procedures for ESO |  |  |  | subsumed into 2.3
2.5 | ICD ESO/VPO | [5 empty] | 60
| update FITS header docs and DID/DIC and submit data dictionary files for FDR, update as necessary |  | PSB
2.7 | Delivery software modules for exposure time calculator | [5 empty] | 0
| submit V1.0 with calculation forms for FDR |  | STH
| respond to RIXs, update document as appropriate |  | STH
| debug and update ETC software modules |  | MJI
2.8 | liaise with VISTA IR camera development team | [5 empty] | 75
| continue liaising with VISTA IR camera development team |  | PSB
2.9 | Development of DQC measures
| respond to RIXs, update QC measures as required |  | PSB
3 | Pipeline infrastructure and pipeline progress monitoring tools | 3.5
3.1 | interactive tools for running pipeline | [5 empty] | 60
| develop tools and document |  | JRL
3.2 | high level scripts to interrogate headers |  | STH, JMI |  | paused |  | 50
3.3 | automatic progression of results to web pages |  | STH, JMI |  | paused |  | 50
3.4 | automatic checks to spot failure of pipeline |  | JMI, STH |  | paused |  | 0
3.5 | Tools for fixing problem datasets |  | JRL, JMI |  | paused
3.6 | group documentation on pipeline infrastructure | [5 empty] | 60
| stress test documentation and update as necessary |  | STH, JRL
3.7 | Oversee reprocessing WFCAM data after bug fixes/improvements |  |  |  | awaiting WFCAM science data
4 | Set up and manage raw science archive | 0
4.1 | extend UKIRT archive to cope with WFCAM data | [5 empty] | 50
| finish creating version 1 of WFCAM raw data archive |  | JRL
4.2 | Ingest and verify WFCAM data
| ingest and verify Phase I commissioning data |  | JRL
| ingest and verify Phase II commissioning data |  | JRL
5 | Set up and manage data processing system hardware | 2
5.1 | Investigate alternatives (benchmarking, reliability etc) |  |  |  | completed |  | 100
5.2 | buy hardware and install | [5 empty] | 80
| purchase and install RAID disk storeage and backup LTO tape unit |  | PSB, JMI
| move all computer kit back to APM building and re-install |  | PSB, JMI
5.3 | integrating and testing | [5 empty] | 70
| integrate and test entire VDFS system |  | PSB, JMI
5.4 | Manage day-to-day maintenance and upgrades | [5 empty] | 50
| continue maintenance and upgrade programme |  | JMI, PSB
6 | Run standard pipeline | 2.5
6.1 | Update WFCAM master calibration frames
| ingest and verify WFCAM on-sky test data |  |  | JRL, MJI
6.2 | Monitor detector performance WFCAM |  |  |  | awaiting WFCAM science data
6.3 | Oversee standard processing WFCAM |  |  |  | awaiting WFCAM science data
6.4 | Astrometric calibration WFCAM |  |  |  | awaiting WFCAM science data
6.5 | Photometric Calibration WFCAM |  |  |  | awaiting WFCAM science data
6.6 | Verify Science products and monitor DQC measures WFCAM |  |  |  | awaiting WFCAM science data
6.7 | Monitor data product transfer to WFAU |  |  |  | awaiting WFCAM science data
6.8 | Reprocess WFCAM data |  |  |  | awaiting WFCAM science data
7 | Development work for summit pipeline | 1
7.1 | Interface test pipelines in ORAC-DR |  | JRL |  | completed |  | 100
7.2a | implement WFCAM pipeline at summit | [5 empty] | 75
| demonstrate catalogue and non-catalogue DQCs |  | JRL
| update & maintain + commissioning enhancements |  | JRL
| develop recipes for dealing with crosstalk, non-linearity, reset anomalies and persistence when test data on these effects become available |  | JRL
7.3a | documentation for ORAC-DR interface | [5 empty] | 60
| update and deliver documentation as development proceeds |  | JRL
7.4a | upgrade and maintain summit pipeline WFCAM
| upgrade and maintain |  | JRL
8 | Development and testing of standard 2d processing | 4
8.1a | further development of standard pipeline for WFCAM | [5 empty] | 80
| finish implementing new version of imcore to include full param set |  | JRL
8.2a | liaison with WFCAM development team | [5 empty] | 75
| continue discussion on reset anomaly, crosstalk and linearity |  | JRL
| assess science array test data for above problems and report |  | JRL
8.2b | liaison with Project Scientist & VISTA development team
| assess any new detector engineering test data |  | MJI
8.3a | partake in planning WFCAM commissioning observations | [5 empty] | 80
| continue liaising with ATC/JAC |  | STH
8.3b | partake in planning VISTA comissioning observations
| liaise and discuss with camera PS and VISTA PS |  | STH
8.4a | Participate directly in commissioning WFCAM
| take part in second stage of WFCAM on-sky commissioning |  | JRL, STH
8.5 | Tuning pipeline during commissioning and after
| use commissioning data to tune processing strategy |  | MJI
| assess the quality and stability of the master calibration data |  | JRL
8.6 | documentation for 2D processing software | [5 empty] | 50
| updates docs as necessary |  | JRL
8.7 | Comparison between automated and manual data products | [5 empty] | 75
| compare FIRES with published results and write report |  | STH
| assess CASU processed WFCAM commissioning data in conjunction with CSV |  | STH
9 | Development and testing of standard catalogue products | 4
9.1 | add in new measures requested | [5 empty] | 60
| finish testing and debugging new catalogue parameter measures |  | MJI
9.2 | refine astrometric calibration model |  | MJI |  | paused |  | 85
9.3 | generate model simulations of expected data |  | STH, JMI |  | finished |  | 100
9.4 | assess catalogue parameter reliability | [5 empty] | 70
| refine parameter error estimates and check for systematics in new params, finish in conjunction with 9.1 |  | MJI
9.5 | intercomparison of catalogue products with other packages |  | JMI |  | stopped - subsumed into 9.4 |  | 60
9.6 | Completeness and error estimates
| design and report on completeness model |  | MJI
9.7 | documentation of catalogue software and products | [5 empty] | 55
| update catalogue products documentation |  | MJI
10 | Setup trial and run further processing pipeline | 3
10.1 | Manage and run further processing stages |  |  |  | placeholder (start in Q3)
10.2 | development and assessment of PSF options 1,2 | [5 empty] | 50
| produce prototype for PSF level 2 |  | MJI
10.3 | develop 1D/2D PSF-deconvolved Sersic profile fits |  |  |  | paused awaiting real WFCAM data (start in Q2)
10.4 | Develop LSBG/nebulosity detection/parameterisation |  |  |  | placeholder (start in Q2)
10.5 | Full iterative profile fitting for stellar images |  |  |  | paused
10.6 | Develop and optimize Bayesian image classification |  |  |  | placeholder (start in Q2)
10.7 | Modelling and simulations of further processing steps |  |  |  | placeholder (start in Q2)
11 | Photometric standards and calibration | 3
11.1 | agree on primary standards | [5 empty] | 90
| complete narrow band filter calibration plan and update document |  | STH
11.2 | choose secondary standard fields | [5 empty] | 80
| refine/shorten list |  | STH
11.3 | take part in commissioning observations WFCAM |  | JRL, STH
phase II on-sky characterisation
11.4a | Reduce data, compute zero points and colour equations WFCAM
| compute ZPs from comissioning data |  | STH
| measure colour terms relative to 2mass |  | STH
11.5 | Update, maintain and extend secondary standards system
| begin building secondary standard fields system |  | STH
11.6 | Investigate photometric calibration field systematics WFCAM+VISTA
| investigate photometric calibration systematics - use 2MASS to check global systematics |  | STH
11.7 | assess extinction monitoring methods and develop measures | [5 empty] | 50
| use 2MASS comparison to get first order estimate and assess expected accuracy |  | STH
12 | Further development of DQC measures at summit and Cambr | 2
12.1 | develop extra systematic noise measures | [5 empty] | 50
| trial using WFCAM commissioning data |  | MJI
12.2 | Refine current measures for WFCAM/VISTA data | [5 empty] | 20
| trial using WFCAM commissioning data |  | JRL
12.3 | implement 2mass for throughput measurement | [5 empty] | 75
| implement local access version at summit |  | JRL
12.4 | master calibration frames for detector monitoring | [5 empty] | 35
| assess and report using commissioning data |  | JRL
13 | Co-located list driven photometry | 3
13.1 | test methods for master catalogue generation |  |  |  | completed |  | 100
13.2 | develop basic WCS-based list driven photometer | [5 empty] | 90
| extend to full 80 parameter set |  | MJI
13.3 | externally driven WCS photometry and define parameter set | [5 empty] | 75
| extend to full 80 parameter set |  | MJI
14 | Stacking and mosaicing | 4
14.1 | develop benchmark simple stacking/mosaicing framework |  | MJI |  | completed |  | 100
14.2 | NN algorithm with simple rejection |  | MJI |  | completed |  | 100
14.3 | More sophisticated rejection dealing with pixellation |  | MJI |  | completed |  | 100
14.4 | Stacking with optimum wighting and defect rejection | [5 empty] | 25
| refine and test current seeing weighting method on FIRES data |  | MJI
14.5 | Advanced stacking/image restoration for variable PSF
| TBD as part of UK design review |  | MJI
15 | Continuum subtraction and basic difference imaging | 4
15.1 | Simple WCS-based subtraction techniques |  | MJI |  | completed |  | 100
15.2 | investigate and apply different interpolation methods |  | MJI |  | completed |  | 100
15.3 | develop adaptive kernel matching option | [5 empty] | 80
| continue debugging and enhancements to adaptive kernel package |  | MJI
15.4 | transit event detection | [5 empty] | 0
| continue with WASP, INT WFC and APT datasets |  | STH
16 | Interpolation techniques and PSF modeling | 4
16.1 | investigate alternative interpolation/PSF schemes |  |  |  | completed |  | 100
16.2 | implications for different stacking methods |  |  |  | paused awaiting stage II of WFCAM commissioning |  | 20
16.3 | implications for deriving catalogues and parameters | [5 empty] | 70
| finish development and testing of astrometric refinement code |  | DWE
16.4 | oversampled PSF generation per detector |  |  |  | finished |  | 100
16.5 | develop oversampled spatially varying PSF model | [5 empty] | 0
| finish development of spatially varying PSF model |  | DWE
| final tuning on WFCAM on-sky data |  | DWE