## ESO Deliverables
WP # | WP Title | Responsibility | 2003 V1 |  |  |  | 2004 V2 |  |  |  | 2005 V3 |  |  |  | FTE V1 | FTE V2 | FTE V3 | dwe 2003 | dwe 2004 | jrl 2003 | jrl 2004 | mji 2003 | mji 2004 | rwa 2003 | rwa 2004 | sth 2003 | sth 2004 | mtb 2003 | mtb 2004 | psb 2003 | psb 2004 | mr new 2003 | mr new 2004 | VDFS ESO factor | VDFS FTE V1 | VDFS FTE V2 | VDFS FTE V3 | VISTA commsisioning
|  |  | JFM | AMJ | JAS | OND | JFM | AMJ | JAS | OND | JFM | AMJ | JAS | OND | [19 empty] | 0-4
1 | ESO VISTA software deliverables and documentation
|  | PSB | [12 empty] | 0.5 | 0.5 | 0.5 | [12 empty] | 0.5 | 0.5 |  |  | 4 | 0.5 | 0.5 | 0.5 | 0.25
1.1 | DFS user requirements document
PSB | bar: 2003 V1 JFM to 2003 V1 OND
1.2 | Data reduction specification
PSB | bar: 2003 V1 JFM to 2003 V1 OND
1.3 | Calibration plan document for ESO
PSB | bar: 2003 V1 JFM to 2003 V1 OND
1.4 | Specification of calibration procedures for ESO
PSB | bar: 2003 V1 JFM to 2003 V1 OND
1.5 | Interface control document ESO/VPO
PSB | bar: 2004 V2 JFM to 2004 V2 OND
1.6 | Instrument specification and interface documents
PSB | bar: 2004 V2 JFM to 2004 V2 OND
1.7 | Delivery software modules Exposure Time Calculator
PSB | bar: 2004 V2 JFM to 2004 V2 OND
1.8 | Liase with VISTA IR camera development team
PSB | bar: 2003 V1 JFM to 2004 V2 OND
1.9 | Development of DQC measures
PSB | bar: 2004 V2 JFM to 2004 V2 OND
2 | Management and Definition of Responsibilities
|  | MJI | [12 empty] | 0.4 | 0.2 | 0.2 | 0.1 | 0.1 | 0.1 |  | 0.1 | 0.1 |  |  | 0.1 | [7 empty] | 2 | 0.2 | 0.1 | 0.1 | 0.05
2.1 | Report to VISTA Board, GSC
MJI
2.2 | Interface Control Document between CASU and JAC
MJI | bar: 2003 V1 JFM to 2003 V1 OND
2.3 | Interface Control Document between CASU and WFAU
MJI | bar: 2003 V1 JFM to 2003 V1 AMJ
2.4 | Define data structures and FITS headers
JRL | bar: 2003 V1 JFM to 2003 V1 AMJ
2.5 | Define observing protocols
STH | bar: 2003 V1 JFM to 2003 V1 AMJ
2.6 | Liaise with UKIDSS & JAC on observing strategy
DWE
2.7 | Liaise with UKIDSS & JAC on survey planning
DWE
2.8 | Liaise with UKIDSS & JAC on survey progress database
JRL
2.9 | System Documentation
STH
3 | Pipeline Infrastructure and Progress Monitoring Tools
|  | JRL | [12 empty] | 0.4 | 0.2 | 0.2 |  |  | 0.2 | 0.1 |  |  |  |  | 0.2 | 0.1 |  |  |  |  | 0.1 | 0.1 | 0 | 0 | 0 | 0
3.1 | Interactive tools for running pipeline
JRL | bar: 2003 V1 JAS to 2004 V2 AMJ
3.2 | High level scripts to interrogate headers
STH | bar: 2003 V1 JFM to 2003 V1 AMJ
3.3 | Develop automatic progression of results to WWW pages
STH | bar: 2003 V1 OND to 2004 V2 JAS
3.4 | Automate checks to spot failures of pipeline
STH | bar: 2003 V1 OND to 2004 V2 JAS
3.5 | Tools for fixing problem datasets
JRL | bar: 2004 V2 JFM to 2004 V2 OND
3.6 | Group Documentation for above
JRL | bar: 2003 V1 JFM to 2004 V2 OND
3.7 | Reprocessing after bug fixes or improvements to algorithms
RWA | bar: 2005 V3 JFM to 2005 V3 OND
4 | Set up and Manage Raw Science Archive
|  | RWA | [12 empty] | 0.1 | 0.2 | 0.1 |  |  | 0.1 | 0.1 |  |  |  | 0.1 | [8 empty] | 0 | 0 | 0 | 0
4.1 | Extend current UKIRT archive to cope with WFCAM
JRL | bar: 2003 V1 OND to 2004 V2 JAS
4.2 | Ingest and verify WFCAM data
RWA | bar: 2004 V2 JFM to 2005 V3 OND
5 | Set up and Manage Data Processing System Hardware
|  | MTB | [12 empty] | 0.2 | 0.2 | 0.2 | [10 empty] | 0.2 | 0.2 |  |  |  |  | 0 | 0 | 0 | 0
5.1 | Investigate alternatives (benchmarking, reliability etc)
MTB | bar: 2003 V1 JFM to 2003 V1 JAS
5.2 | Buy hardware and install software
MTB | bar: 2003 V1 JAS to 2003 V1 OND
5.3 | Integration and testing
MTB | bar: 2003 V1 OND to 2004 V2 JFM
5.4 | Manage day-to-day, maintenance and upgrades
MTB | bar: 2004 V2 JFM to 2005 V3 OND
5.5 | Hardware additions for further data processing system
MTB | bar: 2004 V2 JFM to 2005 V3 OND
6 | Run Standard Pipeline / Experiment for VISTA
|  | RWA | [12 empty] | 0 | 0.9 | 1 |  | 0.1 |  | 0.1 |  |  |  | 0.6 |  | 0.1 | [5 empty] | 0.1 | 2 | 0 | 0.45 | 0.5 | 0.25
6.1 | Ingest and verify data
RWA | bar: 2004 V2 JFM to 2005 V3 OND
6.2 | Update master calibration frames
JRL | bar: 2004 V2 JFM to 2005 V3 OND
6.3 | Monitor detector performance
JRL | bar: 2004 V2 JFM to 2005 V3 OND
6.4 | Oversee standard processing
RWA | bar: 2004 V2 JFM to 2005 V3 OND
6.5 | Astrometric calibration
DWE | bar: 2004 V2 JFM to 2005 V3 OND
6.6 | Photometric calibration
STH | bar: 2004 V2 JFM to 2005 V3 OND
6.7 | Verify science products and monitor DQC measures
RWA | bar: 2004 V2 JFM to 2005 V3 OND
6.8 | Monitor product data transfer to WFAU
JRL | bar: 2004 V2 JFM to 2005 V3 OND
7 | Development Work for Summit Pipelines
|  | JRL | [12 empty] | 0.2 | 0.1 | 0.2 |  |  | 0.2 | 0.1 | [12 empty] | 2 | 0.1 | 0.05 | 0.1 | 0.05
7.1 | Interface test pipelines to observing systems
JRL | bar: 2003 V1 JFM to 2003 V1 AMJ
7.2 | Implement WFCAM/VISTA pipelines at summit
JRL | bar: 2003 V1 JAS to 2003 V1 OND
7.3 | Documentation of interfaces
JRL | bar: 2003 V1 JFM to 2003 V1 OND
7.4 | Upgrade and maintain summit pipelines
JRL | bar: 2004 V2 JFM to 2005 V3 OND
8 | Development and Testing of Standard 2D Processing
|  | STH | [12 empty] | 0.4 | 0.2 | 0.2 |  |  | 0.2 | 0.1 | 0.1 | 0.1 |  |  | 0.1 | [5 empty] | 0.1 |  | 3 | 0.3 | 0.15 | 0.15 | 0.075
8.1 | Further development of standard pipelines
JRL | bar: 2003 V1 JFM to 2003 V1 OND
8.2 | Liaison with WFCAM/VISTA development teams
JRL | bar: 2003 V1 JFM to 2003 V1 OND
8.3 | Partake in planning commissioning observations
STH | bar: 2003 V1 AMJ to 2003 V1 OND
8.4 | Participate directly in commissioning
STH | bar: 2003 V1 OND to 2004 V2 JFM
8.5 | Tuning pipeline during commissioning and after
JRL | bar: 2003 V1 OND to 2004 V2 JAS
8.6 | Documentation of 2D processing software
JRL | bar: 2003 V1 JFM to 2003 V1 OND
8.7 | Comparison between automated and manual data products
STH | bar: 2003 V1 AMJ to 2003 V1 OND; 2004 V2 AMJ
9 | Development and Testing of Standard Catalogue Products
|  | DWE | [12 empty] | 0.5 | 0.2 | 0.2 | 0.1 |  | 0.1 |  | 0.1 | 0.1 |  |  | 0.2 | 0.1 | [6 empty] | 1 | 0.125 | 0.05 | 0.05 | 0.05
9.1 | Add in new measures requested
MJI | bar: 2003 V1 AMJ to 2003 V1 OND
9.2 | Refine astrometric calibration model
MJI | bar: 2003 V1 JAS to 2004 V2 OND
9.3 | Generate model simulations of expected data
STH | bar: 2003 V1 AMJ to 2003 V1 OND
9.4 | Assess catalogue parameter reliability
DWE | bar: 2003 V1 AMJ to 2003 V1 OND
9.5 | Intercomparison of catalogue products with other packages
STH | bar: 2003 V1 JFM to 2004 V2 OND
9.6 | Completeness and error estimates
MJI | bar: 2003 V1 JAS to 2004 V2 OND
9.7 | Documentation of catalogue software and products
MJI | bar: 2003 V1 JFM to 2004 V2 OND
10 | Set up, Trial, and Run Further Processing Software
|  | MJI | [12 empty] | 0.1 | 0.3 | 1.5 |  |  |  | 0.1 | 0.1 | 0.1 |  |  |  | 0.1 | [5 empty] | 0.2 | 0 | 0 | 0 | 0
10.1 | Manage and run further processing stages
MJI | bar: 2004 V2 JFM to 2005 V3 OND
10.2 | Development and assessment of PSF options 1,2
MJI | bar: 2003 V1 JAS to 2004 V2 OND
10.3 | Develop 1D/2D PSF-deconvolved Sersic profile fits
MJI | bar: 2004 V2 JFM to 2004 V2 OND
10.4 | Develop LSBG/nebulosity detection/parameterisation
MJI | bar: 2004 V2 JFM to 2005 V3 OND
10.5 | Full iterative profile fitting for stellar images
TBD | bar: 2005 V3 JFM to 2005 V3 OND
10.6 | Develop and optimise Bayesian image classification
TBD | bar: 2005 V3 JFM to 2005 V3 OND
10.7 | Modelling and simulations of further processing steps
STH | bar: 2004 V2 AMJ to 2005 V3 JFM
11 | Photometric Standards and Calibration
|  | STH | [12 empty] | 0.2 | 0.3 | 0.2 |  | 0.1 | [6 empty] | 0.2 | 0.2 | [6 empty] | 3 | 0.15 | 0.225 | 0.15 | 0.075
11.1 | Agree on primary standards
STH | bar: 2003 V1 JFM to 2003 V1 OND
11.2 | Choose secondary standard fields
STH | bar: 2003 V1 JFM to 2003 V1 OND
11.3 | Take part in commissioning observations
STH | bar: 2004 V2 JFM
11.4 | Reduce data, compute zero points and colour equations
STH | bar: 2004 V2 JFM to 2004 V2 AMJ
11.5 | Update, maintain and extend secondary standards system
STH | bar: 2004 V2 AMJ to 2005 V3 OND
11.6 | Investigate photometric calibration field systematics
STH | bar: 2004 V2 JFM to 2004 V2 JAS
11.7 | Assess extinction monitoring methods and develop measures
DWE | bar: 2003 V1 OND to 2004 V2 OND
12 | Further Development of DQC Measures at Summit and Cam
|  | JRL | [12 empty] | 0.2 | 0.2 | 0.2 |  |  | 0.1 | 0.1 | 0.1 | 0.1 | [10 empty] | 2 | 0.1 | 0.1 | 0.1 | 0.05
12.1 | Develop extra systematic noise measures
MJI | bar: 2003 V1 JAS to 2004 V2 AMJ
12.2 | Refine current measures for WFCAM/VISTA data
JRL | bar: 2003 V1 OND to 2004 V2 JAS
12.3 | Implement 2MASS - cf. for throughput measures
MJI | bar: 2003 V1 JFM to 2003 V1 AMJ; 2004 V2 JFM to 2004 V2 AMJ
12.4 | Master calibration frames for detector monitoring
JRL | bar: 2003 V1 JFM to 2004 V2 JFM
13 | Co-Located List Driven Photometry
|  | MJI | [12 empty] | 0.1 | 0.2 | 0.5 |  |  |  |  | 0.1 | 0.1 |  |  |  | 0.1 |  |  |  |  | 0.1 |  | 0 | 0 | 0 | 0
13.1 | Test methods for master catalogue generation
MJI | bar: 2003 V1 JFM to 2003 V1 AMJ
13.2 | Develop basic WCS-based list driven photometer
MJI | bar: 2003 V1 JFM to 2003 V1 OND
13.3 | Externally driven WCS photometry and define parameter set
MJI | bar: 2004 V2 JFM to 2004 V2 OND
14 | Stacking and Mosaicing
|  | MJI | [12 empty] | 0.1 | 0.2 | 0.5 |  |  |  | 0.1 | 0.1 | 0.1 | [8 empty] | 0.1 | 0.1 | 0 | 0 | 0 | 0
14.1 | Develop benchmark simple stacking/mosaicing framework
MJI | bar: 2003 V1 JFM to 2003 V1 AMJ
14.2 | Nearest neighbour algorithm with simple rejection
MJI | bar: 2003 V1 AMJ to 2003 V1 JAS
14.3 | More sophisticated rejection dealing with pixellation
MJI | bar: 2003 V1 OND to 2004 V2 JAS
14.4 | Stacking with optimum weighting and defect rejection
MJI | bar: 2004 V2 JFM to 2004 V2 OND
14.5 | Advanced stacking/image restoration for variable PSF
TBD | bar: 2005 V3 JFM to 2005 V3 OND
15 | Continuum Subtraction and Basic Difference Imaging
|  | STH | [12 empty] | 0.1 | 0.1 | 0.5 |  | 0.1 |  |  | 0.1 | [11 empty] | 0 | 0 | 0 | 0
15.1 | Simple WCS-based subtraction techniques
MJI | bar: 2003 V1 AMJ to 2003 V1 JAS; 2004 V2 AMJ
15.2 | Investigate and apply different interpolation methods
DWE | bar: 2003 V1 JFM to 2003 V1 JAS; 2004 V2 AMJ
15.3 | Develop adaptive kernel matching option
TBD | bar: 2005 V3 JFM to 2005 V3 OND
15.4 | Transient event detection
STH | bar: 2004 V2 JAS; 2005 V3 JFM to 2005 V3 OND
16 | Interpolation Techniques and PSF Modelling
|  | DWE | [12 empty] | 0.4 | 0.2 | 0 | 0.4 | 0.2 | [14 empty] | 0 | 0 | 0 | 0
16.1 | Investigate alternative interpolation/PSF schemes
DWE | bar: 2003 V1 JFM to 2003 V1 AMJ
16.2 | Implications for different stacking methods
DWE | bar: 2003 V1 JAS to 2003 V1 OND
16.3 | Implications for deriving catalogues and parameters
DWE | bar: 2003 V1 JFM to 2003 V1 OND
16.4 | Oversampled PSF generation per detector
DWE | bar: 2003 V1 JFM to 2004 V2 OND
16.5 | Develop oversampled spatially varying PSF model
DWE | bar: 2004 V2 JFM to 2004 V2 OND
[15 empty] | 3.9 | 4.2 | 5.7 | 0.6 | 0.6 | 1 | 0.8 | 0.8 | 0.7 | 0 | 0.7 | 0.8 | 0.7 | 0.2 | 0.2 | 0.5 | 0.5 | 0.4 | 0.5 |  | 1.475 | 1.625 | 1.65 | 0.85
| Staff Costs (£k) | [13 empty] | 70 | rate/dsy | [18 empty] | 103.25 | 113.75 | 115.5 | 59.5
| Hardware (£k) | [33 empty] | 2.5 | 2.5 | 2.5 | 2.5
| Travel (£k) | [33 empty] | 10 | 10 | 10 | 30
[35 empty] | 115.75 | 126.25 | 128 | 92 | 462
| pre-VDFS near IR & optical pipeline development and prototyping - CIRSI etc | [13 empty] | 3 | dsy | [22 empty] | 210
| TOTAL (£k) | [37 empty] | 672