## WPs
WP # | WP Title | 2003 V1 |  |  |  | 2004 V2 |  |  |  | 2005 V3 |  |  |  | FTE V1 | FTE V2 | FTE V3 | Responsibility
|  | JFM | AMJ | JAS | OND | JFM | AMJ | JAS | OND | JFM | AMJ | JAS | OND
1 | ESO VISTA softwares deliverables and documentation
PSB
1.1 | Interface control document ESO/ATC/JAC
1.2 | Development of DQC Measures
1.3 | Specification of calibration procedures for ESO
1.4 | Calibration plan document for ESO
1.5 | Instrument specification and interface documents
1.6 | Delivery software modules Exposure Time Calculator
1.7 | Liase with VISTA IR camera development team
1.8 | DFS user requirements document
2 | Management and Defenition of Responsibilities
[14 empty] | 0.4 | 0.2 | 0.2 | MJI
2.1 | Report to VISTA, UKIDSS, JAC, ATC, WFAP, GSC
MJI
2.2 | Interface Control Document between CASU and JAC
MJI | bar: 2003 V1 JFM to 2003 V1 OND
2.3 | Interface Control Document between CASU and WFAU
MJI | bar: 2003 V1 JFM to 2003 V1 OND
2.4 | Define data structures and FITS headers
JRL | bar: 2003 V1 JFM to 2003 V1 OND
2.5 | Define observing protocols
STH | bar: 2003 V1 JFM to 2003 V1 OND
2.6 | Liaise with UKIDSS & JAC on observing strategy
DWE
2.7 | Liaise with UKIDSS & JAC on survey planning
DWE
2.8 | Liaise with UKIDSS & JAC on survey progress database
JRL
3 | Pipeline Infrastructure and Progress Monitoring Tools
[14 empty] | 0.5 | 0.3 | 0.2 | JRL
3.1 | Interactive tools for running pipeline
JRL | bar: 2003 V1 JAS to 2004 V2 AMJ
3.2 | High level scripts to interrogate headers
STH | bar: 2003 V1 JFM to 2003 V1 AMJ
3.3 | Develop automatic progression of results to WWW pages
STH | bar: 2003 V1 OND to 2004 V2 JAS
3.4 | Automate checks to spot failures of pipeline
STH | bar: 2003 V1 OND to 2004 V2 JAS
3.5 | Tools for fixing problem datasets
JRL | bar: 2004 V2 JFM to 2004 V2 OND
3.6 | Group Documentation for above
JRL | bar: 2003 V1 JFM to 2004 V2 OND
3.7 | Reprocessing after bug fixes or improvements to algorithms
RWA | bar: 2005 V3 JFM to 2005 V3 OND
4 | Set up and Manage Raw Science Archive
[14 empty] | 0.1 | 0.2 | 0.1 | RWA
4.1 | Extend current UKIRT archive to cope with WFCAM
JRL | bar: 2003 V1 OND to 2004 V2 JAS
4.2 | Ingest and verify WFCAM data
RWA | bar: 2004 V2 JFM to 2005 V3 OND
5 | Set up and Manage Data Processing System Hardware
[14 empty] | 0.2 | 0.2 | 0.2 | MJI
5.1 | Investigate alternatives (benchmarking, reliability etc)
NEW | bar: 2003 V1 JFM to 2003 V1 JAS
5.2 | Buy hardware and install software
NEW | bar: 2003 V1 JAS to 2003 V1 OND
5.3 | Manage day-to-day, maintenance and upgrades
NEW | bar: 2004 V2 JFM to 2005 V3 OND
5.4 | Hardware additions for further data processing system
NEW | bar: 2004 V2 JFM to 2005 V3 OND
6 | Run Standard Pipeline
[14 empty] | 0 | 1 | 1 | RWA
6.1 | Ingest and verify data
RWA | bar: 2004 V2 JFM to 2005 V3 OND
6.2 | Update master calibration frames
JRL | bar: 2004 V2 JFM to 2005 V3 OND
6.3 | Monitor detector performance
JRL | bar: 2004 V2 JFM to 2005 V3 OND
6.4 | Oversee standard processing
RWA | bar: 2004 V2 JFM to 2005 V3 OND
6.5 | Astrometric calibration
DWE | bar: 2004 V2 JFM to 2005 V3 OND
6.6 | Photometric calibration
STH | bar: 2004 V2 JFM to 2005 V3 OND
6.7 | Verify science products and monitor DQC measures
RWA | bar: 2004 V2 JFM to 2005 V3 OND
6.8 | Monitor product data transfer to WFAU
JRL | bar: 2004 V2 JFM to 2005 V3 OND
7 | Development Work for Summit Pipeline
[14 empty] | 0.2 | 0.1 | 0.1 | JRL
7.1 | Interface test pipelines to ORAC-DR
JRL | bar: 2003 V1 JFM to 2003 V1 AMJ
7.2 | Implement WFCAM pipeline at summit
JRL | bar: 2003 V1 JAS to 2003 V1 OND
7.3 | Documentation of interface
JRL | bar: 2003 V1 JFM to 2003 V1 OND
7.4 | Upgrade and maintain summit pipeline
JRL | bar: 2004 V2 JFM to 2005 V3 OND
8 | Development and Testing of Standard 2D Processing
[14 empty] | 0.5 | 0.2 | 0 | STH
8.1 | Further development of standard pipeline
JRL | bar: 2003 V1 JFM to 2003 V1 OND
8.2 | Liaison with WFCAM development team
JRL | bar: 2003 V1 JFM to 2003 V1 OND
8.3 | Partake in planning commissioning observations
STH | bar: 2003 V1 AMJ to 2003 V1 OND
8.4 | Participate directly in commissioning
STH | bar: 2003 V1 OND to 2004 V2 JFM
8.5 | Tuning pipeline during commissioning and after
JRL | bar: 2003 V1 OND to 2004 V2 JAS
8.6 | Documentation of 2D processing software
JRL | bar: 2003 V1 JFM to 2003 V1 OND
8.7 | Comparison between automated and manual data products
STH | bar: 2003 V1 AMJ to 2003 V1 OND; 2004 V2 AMJ
9 | Development and Testing of Standard Catalogue Products
[14 empty] | 0.5 | 0.2 | 0 | DWE
9.1 | Add in new measures requested
MJI | bar: 2003 V1 AMJ to 2003 V1 OND
9.2 | Refine astrometric calibration model
MJI | bar: 2003 V1 JAS to 2004 V2 OND
9.3 | Generate model simulations of expected data
STH | bar: 2003 V1 AMJ to 2003 V1 OND
9.4 | Assess catalogue parameter reliability
DWE | bar: 2003 V1 AMJ to 2003 V1 OND
9.5 | Intercomparison of catalogue products with other packages
STH | bar: 2003 V1 JFM to 2004 V2 OND
9.5 | Completeness and error estimates
MJI | bar: 2003 V1 AMJ to 2004 V2 OND
9.6 | Documentation of catalogue software and products
MJI | bar: 2003 V1 JFM to 2004 V2 OND
10 | Set up, Trial, and Run Further Processing Software
[14 empty] | 0.1 | 0.5 | 1.5 | MJI
10.1 | Manage and run further processing stages
MJI | bar: 2004 V2 JFM to 2005 V3 OND
10.2 | Development and assessment of PSF options 1,2
MJI | bar: 2003 V1 JFM to 2004 V2 OND
10.3 | Develop 1D/2D PSF-deconvolved Sersic profile fits
MJI | bar: 2004 V2 JFM to 2004 V2 OND
10.4 | Develop LSBG/nebulosity detection/parameterisation
MJI | bar: 2004 V2 JFM to 2005 V3 OND
10.5 | Full iterative profile fitting for stellar images
TBD | bar: 2005 V3 JFM to 2005 V3 OND
10.6 | Develop and optimise Bayesian image classification
TBD | bar: 2005 V3 JFM to 2005 V3 OND
10.7 | Modelling and simulations of further processing steps
STH | bar: 2004 V2 AMJ to 2005 V3 JFM
11 | Photometric Standards and Calibration
[14 empty] | 0.2 | 0.3 | 0.1 | STH
11.1 | Agree on primary standards
STH | bar: 2003 V1 JFM to 2003 V1 OND
11.2 | Choose secondary standard fields
STH | bar: 2003 V1 JFM to 2003 V1 OND
11.3 | Take part in commissioning observations
STH | bar: 2004 V2 JFM
11.4 | Reduce data, compute zero points and colour equations
STH | bar: 2004 V2 JFM to 2004 V2 AMJ
11.5 | Update, maintain and extend secondary standards system
STH | bar: 2004 V2 AMJ to 2005 V3 OND
11.6 | Investigate photometric calibration field systematics
STH | bar: 2004 V2 JFM to 2004 V2 JAS
11.7 | Assess extinction monitoring methods and develop measures
DWE | bar: 2003 V1 OND to 2004 V2 OND
12 | Further Development of DQC Measures at Summit and Cam
[14 empty] | 0.2 | 0.2 | 0 | JRL
12.1 | Develop extra systematic noise measures
MJI | bar: 2003 V1 JAS to 2004 V2 AMJ
12.2 | Refine current measures for WFCAM/VISTA data
JRL | bar: 2003 V1 OND to 2004 V2 JAS
12.3 | Implement 2MASS - cf. for throughput measures
MJI | bar: 2003 V1 JFM to 2003 V1 AMJ; 2004 V2 JFM to 2004 V2 AMJ
12.4 | Master calibration frames for detector monitoring
JRL | bar: 2003 V1 JFM to 2004 V2 JFM
13 | Co-Located List Driven Photometry
[14 empty] | 0.2 | 0.2 | 0.5 | MJI
13.1 | Test methods for master catalogue generation
MJI | bar: 2003 V1 JFM to 2003 V1 AMJ
13.2 | Develop basic WCS-based list driven photometer
MJI | bar: 2003 V1 JFM to 2003 V1 OND
13.3 | Externally driven WCS photometry and define parameter set
MJI | bar: 2004 V2 JFM to 2004 V2 OND
14 | Stacking and Mosaicing
[14 empty] | 0.2 | 0.3 | 0.5 | MJI
14.1 | Develop benchmark simple stacking/mosaicing framework
MJI | bar: 2003 V1 JFM to 2003 V1 AMJ
14.2 | Nearest neighbour algorithm with simple rejection
MJI | bar: 2003 V1 AMJ to 2003 V1 JAS
14.3 | More sophisticated rejection dealing with pixellation
MJI | bar: 2003 V1 OND to 2004 V2 JAS
14.4 | Stacking with optimum weighting and defect rejection
MJI | bar: 2004 V2 JFM to 2004 V2 OND
14.5 | Advanced stacking/image restoration for variable PSF
TBD | bar: 2005 V3 JFM to 2005 V3 OND
15 | Continuum Subtraction and Basic Difference Imaging
[14 empty] | 0.1 | 0.1 | 0.5 | STH
15.1 | Simple WCS-based subtraction techniques
MJI | bar: 2003 V1 AMJ to 2003 V1 JAS; 2004 V2 AMJ
15.2 | Investigate and apply different interpolation methods
MJI | bar: 2003 V1 JFM to 2003 V1 OND; 2004 V2 AMJ
15.3 | Develop adaptive kernel matching option
TBD | bar: 2005 V3 JFM to 2005 V3 OND
15.4 | Transient event detection
STH | bar: 2004 V2 JAS; 2005 V3 JFM to 2005 V3 OND
16 | Interpolation Techniques and PSF Modelling
[14 empty] | 0.4 | 0.2 | 0 | DWE
16.1 | Investigate alternative interpolation/PSF schemes
DWE | bar: 2003 V1 JFM to 2003 V1 AMJ
16.2 | Implications for different stacking methods
DWE | bar: 2003 V1 JAS to 2003 V1 OND
16.3 | Implications for deriving catalogues and parameters
DWE | bar: 2003 V1 JFM to 2003 V1 OND
16.4 | Oversampled PSF generation per detector
DWE | bar: 2003 V1 JFM to 2004 V2 OND
16.5 | Develop oversampled spatially varying PSF model
DWE | bar: 2004 V2 JFM to 2004 V2 OND
[14 empty] | 3.8 | 4.2 | 4.9
YEAR |  | DWE | JRL | MJI | NEW | PSB | RWA | STH |  | Total
2003 | VDFS funded | 2003 V1 JFM: 0.6; 2003 V1 AMJ: 1; 2003 V1 JAS: 0.8; 2003 V1 OND: 0.6; 2004 V2 JFM: 0.5; 2004 V2 JAS: 0.8; 2005 V3 JFM: 4.3
2004 | VDFS funded | 0.6 | 0.9 | 0.7 | 0.6 | 0.5 | 0.7 | 0.7 |  | 4.7

## Resource
|  | available | 180 | 74.4658 | 105.5342
0 | men available | 0.4 | 18 | 7.4466 | 10.5534
1 | men available | 0 | 0 | 0 | 0
2 | men available | 1.3 | 58.5 | 24.2014 | 34.2986
3 | men available | 0.7 | 31.5 | 13.0315 | 18.4685
4 | men available | 0.5 | 22.5 | 9.3082 | 13.1918
5 | men available | 1 | 45 | 18.6164 | 26.3836
6 | men available | 0 | 0 | 0 | 0 | 0
7 | men available | 0.1 | 4.5 | 1.8616 | 2.6384
| Total mp available man yrs | 4 | 180 | 74.4658 | 105.5342
|  | from | 2002-10-01 | 2002-10-01 | 2002-10-01 | 2003-03-01 | 2003-10-01
|  | to | 2003-10-01 | 2003-10-01 | 2003-03-01 | 2003-10-01 | 2003-10-01
| 45 | works weeks to calendatr year |  | wks | pro rata | pro rata
|  | weeks to Mar 03 to Sep 03 |  | 52.1429 | 21.5714 | 30.5714 | 0
2 | Pipeline infrastructure and database progress monitoring development | [6 empty] | 22.5 | 9.3082 | 13.1918 | 13.2